## Rule 101B (5)(b)
NGR Part 10, Rule 101B 5(b) - Service and Access Information: Matters Expected to Affect Capacity (Last Reviewed 07/09/2026)
This table contain matters (projects or matinenance activities) that have the potential to affect the capacity of JGN's Large Distribution Mains (Defined as a pipeline which has a flowrate equal to or greater than 10TJ/day and a maximum operating pressure equal to or above 4 MPa as defined by the AEMC Energy Rules Website). For completion, other significant projects that do not affect capacity may also be included.
Status | Indentifier | Date From | Date to | Project Name | Asset Effected | Matters Effecting Capacity | Expected impact on capacity during the period (TJ) | Commentary | Last Updated
Open or Closed | YY-### | Date DD/MM/YY | Date DD/MM/YY | Project Name | List one or more assets | What is causing the change to capacity or where no change to capacity | TJ (if known) | Further explanation | Date DD/MM/YY
Closed | 25-001 | 2025-04-26 | -- | JGN Trunk pressure increase project | Wilton PLS to Wollongong PRS facilities and Wilton PLS to Kooragang Island TRS facilities | New operating pressure. The operating pipeline pressure will be required to be increased to meet the demand at Kurri Kurri Offtake Meter Station (KKOMS) On going increase. | 16 | Increase in capacity expected due to the pressure increase project. | 2025-05-05
Closed | 25-002 | 2025-10-20 | 2025-11-30 | Northern Trunk Validation Digs | Licence 7 | No pressure reduction is planned, however may be required. | N/A | During works no pressure reduction was required. | 2025-12-02
Closed | 26-001 | 2026-01-05 | 2026-04-24 | MSP S8 S9 Pressure Reduction | JGN Trunk | JGN max set point is 4.8MPa but operating pressure is based upon APA pressure. APA has reduced Wilton inlet pressure to 4.2MPa (for normal maintenance) or 3.8MPa (in case of rectification work) for the purpose of integrity digs (identifying defects) along MSP. | CLP from 4.8MPa to 4.2MPa = ~19 TJ CLP from 4.2MPa to 3.8MPa = ~13 TJ CLP from 4.8MPa to 3.8MPa = ~32 TJ | Work have been completed. Not within our control. Modelling still being completed. Notice to market may be required. Planned reinstatement of ROP is 10th of Apri, 2026. Will change planned date once it has occurred. | 2026-05-04
Closed | 26-002.1 | 2026-05-04 | 2026-06-30 | Validation Digs | Canberra Primary Main | No pressure reduction is planned, however may be required. | N/A | Works have been completed. | 2026-07-07
Open | 26-002.2 | 2026-08-10 | TBC | Validation Digs | Licence 1 | No pressure reduction is planned, however may be required. | N/A | First validation dig completed. Second validation dig is planned for end of September. Targetted closure date for Q1, 2027. | 2026-09-07
Closed | 26-003 | 2026-02-04 | 2026-02-11 | MSP S8 S9 Pressure Reduction | JGN Trunk | JGN max set point is 4.8MPa but operating pressure is based upon APA pressure. APA will reduce Wilton inlet pressure to 3.8MPa in order to perform integrity digs and rectification works along the MSP. | CLP from 4.2MPa to 3.8MPa = ~13 TJ CLP from 4.8MPa to 3.8MPa = ~32 TJ | Temporary rectification works have been completed. Not within our control. Modelling still being completed. Notice to market may be required. | 2026-03-13
Open | 26-004 | 2026-08-24 | 2026-10-31 | Validation Digs | Licence 7 | No pressure reduction is planned, however may be required. | N/A | Projects for Licence 7 & 8 separated due to different schedules (26-004 staying as Licence 7 and 26-009 opened for Licence 8B). First validation dig started on 7th of September with estimated completion on end of September. Second validation dig scheduled to start early October. | 2026-09-07
Open | 26-005 | 2026-07-10 | 2027-05-31 | Bend Inspection | Licence 1 | No capacity limitation expected. | N/A | Mobilsation expected in October with project completion by May 2027. | 2026-09-07
Closed | 26-006 | 2026-04-24 | 2026-07-31 | MSP Pigging of S5, S6 and S7 | JGN Trunk | JGN max set point is 4.8MPa but operating pressure is based upon APA pressure. APA is currently operating at a reduced pressure. | N/A |  | 2026-08-03
Open | 26-007 | 2026-07-01 | 2026-09-30 | Third Party Works Digs (M1 Cooranbong) | Licence 7 & 8 | No pressure reduction is planned, however may be required. | N/A | Works ongoing with completion expected by end of September. | 2026-09-07
Open | 26-008 | 2026-10-07 | 2026-10-31 | Pigging | Licence 8C | No pressure reduction is planned, however may be required. | N/A |  | 2026-09-07
Open | 26-009 | 2027-04-01 | 2027-05-31 | Validation Digs | Licence 8B | No pressure reduction is planned, however may be required. | N/A | Expected site mobilisation in April 2027 with expected completion in May 2027. | 2026-09-07
Note on D14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Original date 31/08/2027