## 20.0 High St Pit (hidden)
20.0 High St Pit
IDENTIFY THE TASK or PROCEDURE, DESCRIBE THE HAZARDS AND RISKS, LIST THE CONSEQUENCES AND WHAT ARE THE EXISTING CONTROLS. | [5 empty] | EXISTING RISK |  |  | Recommendations | Responsibility | RISIDUAL RISK |  |  | STATUS | DATE Closed
ID | TASK or PROCEDURE What are the Job Steps | HAZARDS and RISKS What are they | CONSEQUENCES Resulting in | EXISTING CONTROLS | Consultation Method | Consequence | Likelihood | Level Of Risk |  |  | Consequence | Likelihood | Level Of Risk
20.1 | General | Refer tab 0.0
20.2 | Mobilisation | Refer tab 1.0
20.3 | Creating the site | 1. Mobile Power Plant - Collision - Vehicle - Pedestrians. | Medical Treatment Injury, Collision, Damage to Property/Equipment, Damage to Reputation, Lack of Attention - Error, Vehicle Incident | 1. Reversing Alarms, Beacons, VOC'd operators, Magnetic ID with UHF channel, Exclusion Zones - Barriers as required, Signage, Flagging. Designated pedestrian walkways | Traffic Management Plan, JSA, Prestart, Toolboxes, Toolbox | D | 5 | L
|  | 2. Foreign Service Strike. | Medical Treatment Injury, Damage to Asset, Damage to Property/Equipment, Lack of Attention - Error | 2. Services positively identified and marked. DBYD Overhead power tiger tails installed Spotter in place. |  | D | 5 | L
|  | 3. Working in road reserve | Medical Treatment Injury, Collision, Damage to Property/Equipment, Lack of Attention - Error, Vehicle Incident | 3. Traffic Control in place as required (Traffic Management Plan) - including water filled barriers with appropriate end treatments, signage, anti climb fence. Site specific JSA. Permit from council with stipulated controls. |  | C | 4 | M
20.4 | Installing 'tiger tails' on overhead power lines (by power company) | [7 empty] | Power Company (Jemena) to be engaged
20.5 | Access site, unload equipment, supplies etc. | 1. Poor ground conditions (slips and trips). | First Aid Injury, Lack of Attention - Error | 1. Be observant “look first”. Lace up safety boots., Housekeeping Where possible unload or load on flat, smooth surfaces | Induction, Prestart, Toolboxes, JSA, PTW, VOC, TMP | E | 4 | L
|  | 2. Overhead powerlines and buried services. | Fatality, Damage to Property/Equipment, Impact on Third Party Relationship, Project Stopped | 2. Line list, dial before you dig service, alignment sheets, permits required to proceed, signage. Look up – be observant. Erect catenaries. |  | A | 5 | M
|  | 3. Manual handling injuries (lifting heaving equipment) | Lost Time Injury | 3. Team lift for heavy / awkward items. PPE including gloves (cut and puncture proof rated) to prevent splinters and lacerations. Unload supplies close to worksite to reduce carrying distance. |  | C | 3 | M
|  | 4. Powered equipment operator error. | Medical Treatment Injury, Collision, Damage to Asset, Damage to Property/Equipment, Lack of Attention - Error, Vehicle Incident | 4. All operators of powered mobile plant must be competent (VOC) to operate. Where licenses are available these must be held by the operator/. Prestart, Toolboxes inspections must be completed and documented where a logbook is provided prior to use daily. No unauthorized use of powered equipment permitted. |  | D | 4 | L
20.6 | Survey | refer tab 3.0
20.7 | Service Proving | refer tab 5.0
20.8 | Service Removal 1. Exploratory hole to establish if safe 2. Cut / remove pipe out | 1. Potential unknown content - causing engulfment / explosion / fire / hazardous atmosphere | Fatality, Permanent Disability, Lost Time Injury, Medical Treatment Injury | 1. Trace lines to establish ownerships 2. Consultation with known asset owners 3. DBYD 4. Permit to work from Mobil / asset owner 5. Confined space working conditions 6. PPE | Induction, Prestart, Toolboxes, JSA, PTW, VOC, TMP | A | 5 | M | Once desktop investigation completed detailed procedure to be developed | Mobil
20.9 | Service Relocation (City West Water water pipe) | 1. Potential engulfment of excavation | Fatality, Permanent Disability, Lost Time Injury, Medical Treatment Injury | 1. City West Water consultant (GHD) to design re-route 2. Approval from CWW before commencing 3. Approval from Licensed Pipeline owners within 3m (SPJV / BP) 3. City West Water approved contractor to be engaged to perform re-route | Induction, Prestart, Toolboxes, JSA, PTW, VOC, TMP | B | 5 | M | City West Water approved contractor to be engaged Must seek Pipelines Act Approvals before commencing | Mobil / Nacap
20.1 | Installation of shoring | 1. Striking foreign services. | Fatality, Damage to Asset, Damage to Property/Equipment, Medical Treatment Injury, Damage to Asset, Damage to Property/Equipment, Impact on Third Party Relationship, Loss of Production, Production Delays, Project Stopped | 1. Check for tiger tails and signage when working near overhead, spotter required at all times. Follow PTW requirements. Hand dig within specified required distances. Foreign services to be located and identified – install barricading for exclusion zones. Most of excavation work has been completed by others. Service protection/shielding to be installed (Rock shield for line pipe) 2. Review and approve lift plan | Induction, Prestart, Toolboxes, JSA, PTW, VOC, TMP | A | 5 | M | Detailed procedure to be developed once finalised plan for shoring has been completed. All WAPs and JSAs to be sent to SPJV prior to commencement. SPJV requirements are no mechanical excavation within 1m. SPJV also require notification if another asset has been damaged in the area. | Nacap / Mobil
|  | 2. Striking / discovering unknown foreign services. | Fatality, Damage to Asset, Damage to Property/Equipment, Medical Treatment Injury, Damage to Asset, Damage to Property/Equipment, Impact on Third Party Relationship, Loss of Production, Production Delays, Project Stopped | 2. DBYD completed, all known services located prior to mechanical excavation, inspection of the site to check for signs of other assets, competent and experienced spotters and operators |  | B | 4 | M
|  | 3. Environmental impact - Burst Hoses. | Spill | 3. Spill kits to be available for all machines. Report all spills to Project Manager. |  | E | 3 | L
|  | 4. Other vehicles passing through work area. | Damage to Property/Equipment, Vehicle Incident | 4. Operator ID magnets displayed on all machines, vehicles to call up on radio channel #TBA prior to entering and passing through area slowly. Traffic management plan implemented (barriers and signage in place) |  | D | 5 | L
20.11 | Excavate with Excavator | 1. Attachment falling off – striking personnel/equipment or causing damage. | Fatality, Crush Injury | 1. Quick hitch pins installed / check quick hitch engaged. Operate within equipment parameters. Inspection of equipment for metal fatigue and wear. Exclusion zone in and around immediate work area | Induction, Prestart, Toolboxes, JSA, PTW, VOC, TMP | A | 5 | M
|  | 2. Striking personnel/equipment in work area with bucket, blind spots. | Fatality, Crush Injury, Damage to Property/Equipment | 2. Inductions. Exclusion zone communicated at Prestart, Toolboxes and to visiting personnel, eye contact to be made with operator prior to approaching, confirm eye contact with operator established. Spotter in place. |  | A | 5 | M
|  | 3. Environmental impact - Burst Hoses. | Spill | 3. Spill kits to be available for all machines. Report all spills to Project Manager. |  | E | 3 | L
|  | 4. Other vehicles passing through work area. | Damage to Property/Equipment, Vehicle Incident | 5. Operator ID magnets displayed on all machines, vehicles to call up on radio channel #TBA prior to entering and passing through area slowly. Traffic management plan implemented |  | D | 5 | L
|  | 5. Striking foreign services. | Fatality, Damage to Asset, Damage to Property/Equipment, Medical Treatment Injury, Damage to Asset, Damage to Property/Equipment, Impact on Third Party Relationship, Loss of Production, Production Delays, Project Stopped | 1. Check for tiger tails and signage when working near overhead, spotter required at all times. Follow PTW requirements. Hand dig within specified required distance. Foreign services to be located and identified – install barricading for exclusion zones. Most of excavation work has been completed by others. Service protection/shielding to be installed (Rock shield for line pipe) 2. Review and approve lift plan 3. Review depths of pipelines and complete API 1102 calculation to determine protection requirements. |  | A | 5 | M | Refer 19.9 -2 above
|  | 6. Striking / discovering unknown foreign services. | Fatality, Damage to Asset, Damage to Property/Equipment, Medical Treatment Injury, Damage to Asset, Damage to Property/Equipment, Impact on Third Party Relationship, Loss of Production, Production Delays, Project Stopped | 7. DBYD completed, all known services located prior to mechanical excavation, inspection of the site to check for signs of other assets, competent and experienced spotters and operators |  | B | 4 | M | Consider what-if within ERP. | Mobil
|  | 7. Excavator sliding/falling into excavation. | Damage to Property/Equipment | 8. Experienced VOC'd operators, JSA, work methodology. |  | E | 3 | L
|  | 8. Excavation collapse / instability. | Crush Injury, Environmental Impact, Impact on Third Party Relationship, Production Delays | 9. Excavation to be shored or benched. |  | E | 3 | L
20.12 | Excavations in built up areas | 1. Unauthorised access by a member of the public, e.g. children, falling into excavation. | Fatality, Damage to Reputation, Impact on Third Party Relationship, Project Stopped | 1. Fencing off site - Site to be secured with anti climb fencing at end of shift or when not manned. Minimise open excavations in the vicinity of areas with risk of public access. Signage. Public/land owner consultation. Security fencing in place and locked at end of shift / when not manned. | Induction, Prestart, Toolboxes, JSA, PTW, VOC, TMP | A | 5 | M
20.13 | Changing Teeth on buckets / servicing | 1. Clip shattering when removing – eye injury, cuts. | First Aid Injury, Eye Injury | 1. Double eye protection worn, gloves, sleeves rolled down, correct toll used (Circlip pliers). | Induction, Prestart, Toolboxes, JSA, PTW | C | 4 | M
|  | 2. Hot surfaces – burns from teeth, chain, bucket | First Aid Injury, Burns to skin | 2. Gloves to be worn at all times, long sleeve shirt and pants and safety boots. |  | C | 5 | L
|  | 4. Sprains from attempting to remove teeth that are stuck. | First Aid Injury | 4. Call a fitter to remove and replace stuck teeth. |  | D | 4 | L
|  | 5. Cuts and crushing from using incorrect tools. | First Aid Injury, Crush Injury | 5. Use of good condition hammer, Pry Bar, Screwdriver and pliers only. Gloves, double eye protection to be worn. |  | E | 4 | L
|  | 6. Crushing , entanglement from moving parts, fall from heights during maintenance / servicing. | Lost Time Injury, Crush Injury | 6. All maintenance and servicing to be completed by project fitter / mechanic – JSA developed by Mechanics. |  | C | 4 | M
20.14 | Working near / in excavations | 1. Falling in excavation. | Medical Treatment Injury | 1. Visual inspect excavation at start of each shift, do not stand close to edge of excavation. Handrailing to be in place to protect leading edge. Use of measuring staff extender to ensure no encroaching on edge of excavation. | Induction, Prestart, Toolboxes, JSA, PTW, VOC, TMP | C | 5 | L
|  | 2. Uneven ground – trips. | First Aid Injury | 2. Check for any obstacles, holes at edge of excavation / travel path. |  | E | 4 | L
|  | 3. Un-planned collapse. | First Aid Injury, Medical Treatment Injury | 3. Excavation shored or benched once greater than 1.5m or less if ground conditions require. |  | D | 5 | L
|  | 4. Engulfment / ingress of flamable or hazardous substance (ie. leaking line) | First Aid Injury, Medical Treatment Injury | 4. Gas monitorring / PID monittoring - risk assessment |  | B | 5 | M | Confined space risk assessment to be completed to fully define controls. | Nacap
|  | 5. Slips trips and falls whilst entering / exiting excavation | First Aid Injury, Medical Treatment Injury, Lost Time Injury | 5. Proposed access points to be at longintudal ends of excavation via benched sections which will have ramps / steps cut with hand rails. Once pit walls in place / formwork gantry's with ladders will be used. |  | D | 3 | M | Investigate whether portable stairs / scaffold can be used to access pit once walls are up. | Nacap
20.15 | Using Rock Breakers | 1. Noise. | Permanent Disability, Community Complaints, Fatigue | 1. Hearing protection worn by operator and crew (also approved visitors to work area). EPA guidelines to be adhered to. Signage with zones. (Background noise assessment to be completed) | Induction, Prestart, Toolboxes, JSA, PTW, VOC, TMP | C | 4 | M
|  | 2. Eye injury, cuts from flying rock / debris. | Medical Treatment Injury, Eye Injury | 2. Exclusion zone communicated at Prestart, Toolboxes to crew and to visitors ( exclusion zone to be determined based on location). |  | C | 4 | M
|  | 3. Damage to existing assetts | Medical Treatment Injury, Eye Injury | Third party asset owner approval required Mechanical protection required over / around existing assets once exposed |  | A | 5 | M | If breaking with excavator required separate procedure to be developed and approval sought from third party asset owner | Nacap
20.16 | Breaking rock by hand (jack hammers) | 1. Noise. | Permanent Disability, Community Complaints, Fatigue | 1. Hearing protection worn by operator and crew (also approved visitors to work area). EPA guidelines to be adhered to. Signage with zones. (Background noise assessment to be completed) | Induction, Prestart, Toolboxes, JSA, PTW | C | 4 | M
|  | 2. Eye injury, cuts from flying rock / debris. | Medical Treatment Injury, Eye Injury | 2. Exclusion zone communicated at Prestart, Toolboxes to crew and to visitors ( exclusion zone to be determined based on location). |  | C | 4 | M
|  | 3. Injury to foot | Medical Treatment Injury | Jack hammers to be used in appropriate positions and good access |  | C | 4 | M
|  | 3. Hand arm vibration syndrome (white knuckle finger etc) | Permanent Disability | 3. Detailed risk assessment to be completed to ensure tool limits are understood and workers are rotated when using jack hammers |  | C | 4 | M
|  | 4. Damage to third party asset / pipe | Permanent Disability, Damage to Asset | Third party asset owner approval required Mechanical protection required over / around existing assets once exposed |  | C | 4 | M
20.17 | Working in the vicinity of existing underground services | 1. Damage to existing services causing engulfment or electrocution | Fatality, Permanent Disability, Medical Treatment Injury, Damage to Asset | 1. Services to be exposed and excavated in accordance with asset owners requirements. All exposed services to be supported where appropriate. Excavation emergency / escape plan to be in place (including with training) | Induction, Prestart, Toolboxes, JSA, PTW, VOC, TMP | B | 5 | M
|  | 2. Ageing assets crumble when exposed leaking unknown fluids / gas into excavation. | Medical Treatment Injury | 2. All existing assets to be exposed carefully first and protection installed. Refer item 19.8 above existing assets identified and contents understood prior to commencement. Pre-condition survey to be completed prior to major Works commencing to understand condition of services and any additional safety measures required (permit conditions). If required asset owners will be requested to remocve the services if deemed unsafe. |  | B | 5 | M
20.18 | End of Day – Pack Up | 1. Open excavation – Plant, personnel, fauna fall in trench. | Fatality, Damage to Property/Equipment, Impact on Third Party Relationship, Project Stopped, Stock Loss, Vehicle Incident, Wildlife Injury/Fatality | 1. Fence open excavation at all times, Full time traffic management in place (water filled barriers and signage). Site assessment in areas of public access (children) to ensure site security and protection to the public. | Induction, Prestart, Toolboxes, JSA, PTW, VOC, TMP | B | 5 | M
|  | 2. Crushing from suspended boom / buckets. | Fatality, Crush Injury | 2. All booms and buckets to be lowered to ground at end of day. |  | A | 5 | M
|  | 3. Waste/Contamination. | Environmental Impact | 3. Remove all waste and dispose of in designated bins. |  | E | 3 | L
20.19 | Formwork, steel fixing and concreting. | 1. Finger / hand injuries | Medical Treatment Injury | 1. Trained and experienced crew engaged Mandatory PPE requirements Communication with other trades and barricading where required. Housekeeping maintained. | Induction, Prestart, Toolboxes, JSA, Lift Plans, PTW, VOC, TMP | C | 3 | M
|  | 2. Eye injuries - use of hammers, nips and small hand tools. | Medical Treatment Injury | 2. Trained and experienced crew engaged Mandatory PPE requirements Communication with other trades and barricading where required. Housekeeping maintained. |  | C | 3 | M
|  | 3. Manual handling injuries (lifting heaving equipment) | Medical Treatment Injury | 3. Team lift for heavy / awkward items. PPE including gloves (cut and puncture proof rated) to prevent splinters and lacerations. Unload supplies close to worksite to reduce carrying distance. |  | C | 4 | M
|  | 4. Uneven surfaces and exposed Reo bar causing injury to legs. | First Aid Injury | 1. Trained and experienced crew engaged Mandatory PPE requirements Communication with other trades and barricading where required. Housekeeping maintained. Spotter engaged as required (no person to stand behind reversing vehicle) Hold down bolts, exposed reo to be capped and monitored Agi truck fitted with reversing alarm / flashing beacon and spotter No Agi washout on site |  | D | 4 | L
|  | 5. Personnel in close proximity to Agi Truck movements | Fatality, Crush Injury, Damage to Property/Equipment |  |  | D | 5 | L
|  | 6. Chemical exposure to cement and lime based products | Burns to skin |  |  | C | 5 | L
|  | 7. Lifting / working over existing live pipelines causing damage | Damage to Asset | Refer to 19.21 |  | C | 5 | L
20.2 | Supply of Imported sand / backfill | 1. Volume of delivered loads of imported sand | Production Delays | 1. Project Engineer to order quantities | Driver Induction, JSA, PTW, TMP | E | 4 | L
|  | 2. Tipping of sand from trucks - tip-over(truck and dog) | Damage to Pipe , Damage to Property/Equipment, Injury, Vehicle Incident | 2. Only truck and dogs allowed, no semi trailers. Competent operator and clear communication between spotter and driver at all times. |  | E | 4 | L
|  | 3. Non-inducted delivery drivers arrive at site | Damage to Pipe , Damage to Property/Equipment, Environmental Impact, Injury, Vehicle Incident | 3. All delivery drivers to be put through the Nacap Delivery Driver Induction prior to entering Nacap work site. |  | E | 4 | L
20.21 | Placement of Imported stabilised sand / backfill | 1. Interaction with other plant and equipment with reduced site and increased traffic | Damage to Pipe , Damage to Property/Equipment, Eye Injury, Injury, Vehicle Incident | 1. Spotter for loading of flo-con / Agi or other placement machinery. Communication with other plant. | Induction, Prestart, Toolboxes, JSA, PTW, VOC, TMP | D | 4 | L
|  | 2. Soft ground conditions causing instability/ trench collapse | Crush Injury, Damage to Pipe , Damage to Property/Equipment, Environmental Impact | 2. Trained operators and JSA |  | C | 4 | M
|  | 3. Damage to pipe from foreign object in sand (rock etc.) | Damage to Pipe | 3. Spotter checking quality of material |  | E | 4 | L
20.22 | Crane Lifts (including excavators) | 1. Material falling causing injury or damage to plant and equipment | Fatality, Medical Treatment Injury | 1. Instruction given by dogman during crane movements All lifting equipment is to be tagged and/ or up to date inspections carried out. Exclusion zone established. Approved lift plan identifying lifting requirement and exclusion zones. Working Tier 1 BP guidelines and approval requirements (including PTW). | Induction, Prestart, Toolboxes, JSA, Lift Plans, PTW, VOC, TMP | A | 5 | M | Lifting Procedure and JSA to be provided to SPJV | Mobil
20.23 | Installation of Structural Steel (including gatic lid) | 1. Inexperienced / unqualified persons engaged causing injury | Lost Time Injury, Medical Treatment Injury, Collision, Crush Injury, Damage to Asset, Damage to Property/Equipment | Trained and competent personnel engaged. Only qualified crane drivers to operate cranes and qualified riggers to select and apply rigging and direct crane driver All plant to be inspected on daily basis and records kept Maintenance to be carried out in accordance with manufactures guidelines . SWL not exceeded Spotters engaged as required Tool selection appropriate for tasks No working on leading edges without fall protection (ie. handrails or clipped on) Portable scaffold towers to be erected by trained and competent persons only. Frame / protection system to be installed over live pipelines in pit before lifting overhead. | Induction, Prestart, Toolboxes, JSA, Lift Plans, PTW, VOC, TMP | D | 4 | L
|  | 2. Incorrect procedures used or procedures not followed causing injury | Lost Time Injury, Medical Treatment Injury, Collision, Crush Injury, Damage to Asset, Damage to Property/Equipment |  |  | D | 4 | L
|  | 3. Use of Defective, Incorrect tools causing injury | Lost Time Injury, Medical Treatment Injury, Collision, Crush Injury |  |  | E | 4 | L
|  | 4. Working at heights | Lost Time Injury, Medical Treatment Injury, Collision, Crush Injury |  |  | C | 4 | M
|  | 5. Hand and finger injuries - trapped / pinched between steelwork | Medical Treatment Injury, First Aid Injury |  |  | C | 4 | M
|  | 6. Damage to existing / live asset | Medical Treatment Injury, First Aid Injury, Fatality, Damage to Property/Equipment |  |  | A | 5 | M | Provide details of protection system to SPJV | Nacap / Mobil
20.24 | Reinstatement | refer tab 17.0
* any procedures / JSAs developed to be issued to SPJV prior to commencement

## Jemena Cover Sheet (hidden)
Document Cover Sheet
[5 empty] | Supplier PO/Contract No: |  | 4600009903
[5 empty] | Supplier Item Description: |  | N/A
[5 empty] | Equipment/Tag No: |  | N/A
Project Name: |  |  | Port Kembla Pipepline Project
Supplier Document Title: |  |  | HSE Risk Register (HIRAC Register)
Supplier Document No: |  |  | GAS-599-RG-HSE-004 |  |  |  | Supplier Rev No: | B
Jemena Document No: |  |  | GAS-599-RG-HSE-004 |  |  |  | Jemena Rev No: | B
[7 empty] | Total No of Pages (incl cover page) |  | 25
Rev | Issue Date | Key Reason for Issue (as above table) |  |  | Approved By/ Signature | Company Name |  | Notes (if not applicable N/A)
A | 2022-04-05 | Issued for Information |  |  | Jason Heard | NACAP |  | N/A
B | 2022-10-14 | Issued for Information |  |  | Jason Heard | NACAP |  | N/A
IFR- Issued for Review |  |  |  | IFI- Issued for Information |  | IFU- Issued for Use
IFP- Issued for Purchase |  |  |  | IFC- Issued for Construction |  | AB- As Built

## Attendees (Early Wks))
Attendees List
Project | Port Kembla Pipeline Project
Contract # | 4600009903
Activity: | Mobilisation & Early Works
Date | Name | Position | Company | Location | Phone | Email | Signature
refer Teams meeting attendance list opposite
2022-03-22
2022-03-22
2022-03-22
2022-03-22
2022-03-22
2022-03-22
2022-03-22
2022-03-22
2022-03-22
2022-03-22
2022-03-22
2022-03-22
2022-03-22
2022-03-22
2022-03-22
2022-03-22
2022-03-22
2022-03-22
2022-03-22
2022-03-22
2022-03-22
2022-03-22
2022-03-22
2022-03-22

## Attendees (Const.)
Attendees List
Project | Port Kembla Pipeline Project
Contract # | 4600010171
Activity: | Construction
Date | Name | Position | Company | Location | Phone | Email | Signature
2022-09-08 | Jason Heard (Presenter) | Project Manager | Nacap | MS Teams | - | j.heard@nacap.com.au | Refer to MS Teams
2022-09-08 | Paul Whyte (Presenter) | Corporate Safety Manager | Nacap | MS Teams | - | p.whyte@nacap.com.au | Refer to MS Teams
2022-09-08 | Andrew Petch | Project Engineer | AIE | MS Teams | - | andrew.petch@ausindenergy.com | Refer to MS Teams
2022-09-08 | James Jimenez | Safety | AIE | MS Teams | - | james.jimenez@ausindenergy.com | Refer to MS Teams
2022-09-08 | Pete Wheelwright | Construction Manager | Jemena | MS Teams | - | pete.wheelwright@zinfra.com.au | Refer to MS Teams
2022-09-08 | Steven Hopkins | General Manager | UEA (Nacap) | MS Teams | - | shopkins@uea.com.au | Refer to MS Teams
2022-09-08 | Pham, Bach | Project Engineer | Nacap | MS Teams | - | b.pham@nacap.com.au | Refer to MS Teams
2022-09-08 | Jordan Moeser | Project Manager | UEA (Nacap) | MS Teams | - | jmoeser@uea.com.au | Refer to MS Teams
2022-09-08 | Thomas Toleman | Pipeline Project Engineer | Jemena | MS Teams | - | thomas.toleman@zinfra.com.au | Refer to MS Teams
2022-09-08 | Craig Davis | Superintendent | Nacap | MS Teams | - | c.davis@nacap.com.au | Refer to MS Teams
2022-09-08 | David Hawks | HSE Manager | Jemena | MS Teams | - | david.hawks@jemena.com.au | Refer to MS Teams
2022-09-08 | Justin Anderson | Project Manager | Jemena | MS Teams | - | Justin.Anderson@zinfra.com.au | Refer to MS Teams
2022-09-08 | Jodi Wood | Stakeholder / Approvals Manager | Jemena | MS Teams | - | jodi.wood@jemena.com.au | Refer to MS Teams
2022-09-08 | Jonathan de Vos | Operations Manager | UEA (Nacap) | MS Teams | - | jdevos@uea.com.au | Refer to MS Teams
2022-09-08 | Povey, James | Operation Director | Nacap | MS Teams | - | j.povey@nacap.com.au | Refer to MS Teams
2022-09-08 | Marcus Agnos | HSE | Jemena | MS Teams | - | marcus.agnos@jemena.com.au | Refer to MS Teams
2022-09-08 | Rohan Corbett | Construction Management | AIE | MS Teams | - | rohan.corbett@ausindenergy.com | Refer to MS Teams
2022-09-08 | Mike Crandell | Construction Manager | AIE | MS Teams | - | mike.crandell@ausindenergy.com | Refer to MS Teams

## Revision
Rev | Issued/ | Checked/ | Approved/ | Description of change
| Date | Date | Date
A | 2022-03-23 | 2022-03-23 |  | Rev A Early Works
B | 2022-10-14 | 2022-10-14 |  | Rev B Construction
APPLIED METHODOLOGY: | 1. The process followed in assessing risks considered for this register was a Quantitative analysis consistent with the Risk Assessment and Control procedure. 2. Hazards considered include those identified presenting a risk to the health and safety of people, integrity of environmental damage. 3. Hazard identification includes - team based brain storming by people with appropriate skills, expertise and experience - input from incident investigations, risk assessments and internal organisational learning streams 4. Terms of Reference (TOR): CHSMP Contractors Health and Safety Management Plan Section 10: HIRAC
ASSUMPTIONS & LIMITATIONS: | 1. The quantitative descriptors used for assessments are those detailed in Nacap's HSE MS 2. Control measure criteria applied is consistent with Nacap MS Procedures 3. Risk outcomes based on most probable, reasonable estimate of injury, damage or environmental impact, 4. To minimise the affect of 'assessment uncertainty' elements, assessment activities 'erred on the side of safety' 5. Residual risk levels are based on the condition that all proposed risk controls are implemented and fully effective. 6. Controls are nominated with reducing the consequence the first priority 7. The focus of the HAZID shall be scopes of work that potentially pose a fatality or serious injury level of risk to personnel. 8. Controls focus on the critical controls to be used whilst onsite.
LEGISLATION REQUIREMENTS: | Project : Port Kembla Pipeline Project State: NSW Acts: Work Health and Safety Act 2011 (NSW) Heavy Vehicle (Adoption of National Law) Act 2013 (NSW) Pipelines Act 1967 (NSW) Dangerous Goods (Road and Rail Transport) Act 2008 (NSW) Explosives Act 2003 (NSW) Radiation Control Act 1990 (NSW) Workers Compensation Act 1987 (NSW) Regulations: Refer to contract documents Codes of Practice: Refer to contract documents

## Rec - Actions
ACTIONS REGISTER
No. | Report Date | Item ID No. | Action Required | Internal/External | Action By | Action Taken | Anticipated Close Out Date | Status | Evidence | Evaluation
1 | 2022-03-22 | General 0.1 | add in at Existing Controls 'Daily BrAC testing of all personnel.' | int | JCU | done | 2022-03-22 | closed | refer relevant HAZID tab and item number
2 | 2022-03-22 | General 0.9 | add in at Hazards & Risks 'including when service proving' | int | JCU | done | 2022-03-22 | closed | refer relevant HAZID tab and item number
3 | 2022-03-22 | General 0.11 | add in at Existing Controls '- no unauthorised modification of hand tools; no use of makeshift hand tools' | int | JCU | done | 2022-03-22 | closed | refer relevant HAZID tab and item number
4 | 2022-03-22 | General 0.12 | add in at Existing Controls 'Use of gators where risk assessment deems necessary' | int | JCU | done | 2022-03-22 | closed | refer relevant HAZID tab and item number
5 | 2022-03-22 | General 0.13 | add in at Existing Controls 'keep noisy activiites to short duration where possible. comply with land acccess agreements; use of Nacap LECH Form 2' | int | JCU | done | 2022-03-22 | closed | refer relevant HAZID tab and item number
6 | 2022-03-22 | General 0.16 | add in at Existing Controls 'Implementation of Nacap Safe Plant Interaction (SPIN) Program' | int | JCU | done | 2022-03-22 | closed | refer relevant HAZID tab and item number
7 | 2022-03-22 | General 0.19 | add in at Existing Controls 'Use of tilt-tray and low-loaders for machine transport. ' | int | JCU | done | 2022-03-22 | closed | refer relevant HAZID tab and item number
8 | 2022-03-22 | General 0.22 | this item to be revisited at a later date as and if it becomes relevant | int | JCU | done | 2022-03-22 | closed | refer relevant HAZID tab and item number
9 | 2022-03-22 | General 0.22a | this item to be revisited at a later date as and if it becomes relevant | int | JCU | done | 2022-03-22 | closed | refer relevant HAZID tab and item number
10 | 2022-03-22 | Mobilisation 1.2 | this item to be revisited at a later date as and if it becomes relevant | int | JCU | done | 2022-03-22 | closed | refer relevant HAZID tab and item number
11 | 2022-03-22 | Mobilisation 1.3 | this item to be revisited at a later date as and if it becomes relevant | int | JCU | done | 2022-03-22 | closed | refer relevant HAZID tab and item number
12 | 2022-03-22 | Mobilisation 1.4 | this item to be revisited at a later date as and if it becomes relevant | int | JCU | done | 2022-03-22 | closed | refer relevant HAZID tab and item number
13 | 2022-03-22 | Survey 3.1 | remove 'Hearing damage from hammering in stakes' item from Hazards & Risks column | int | JCU | done | 2022-03-22 | closed | refer relevant HAZID tab and item number
14 | 2022-03-22 | Survey 3.2 | non-applicable items at 3.2 struck out | int | JCU | done | 2022-03-22 | closed | refer relevant HAZID tab and item number
15 | 2022-03-22 | FSL 5.1 | include 'double eye protection' in Existing Controls | int | JCU | done | 2022-03-22 | closed | refer relevant HAZID tab and item number
16 | 2022-03-22 | FSL 5.1 | include 'appropriate cleaning mechanism for blockages' in Existing Controls | int | JCU | done | 2022-03-22 | closed | refer relevant HAZID tab and item number
17 | 2022-03-22 | FSL 5.1 | include 'Pneumatic, machine compaction.' in Existing Controls | int | JCU | done | 2022-03-22 | closed | refer relevant HAZID tab and item number
18 | 2022-03-22 | GCW 6.2 | include 'Suitably competent/VOC'ed operators' in Existing Controls | int | JCU | done | 2022-03-22 | closed | refer relevant HAZID tab and item number
19 | 2022-03-22 | GCW 6.2 | remove 'Cuts from wire' from Hazards & Risks | int | JCU | done | 2022-03-22 | closed | refer relevant HAZID tab and item number
20 | 2022-03-22 | GCW 6.3 | JHE to advise further on Hazard & Risk item no. 4 | int | JHE | JHE to advise further on Hazard & Risk item no. 4 | 2022-04-05 | closed | refer relevant HAZID tab and item number
21 | 2022-03-22 | Reinstatement | to be reviewed at future Hazid session | int | All | to be reviewed at future Hazid session | TBA | open | refer relevant HAZID tab and item number
22 | 2022-03-22 | Approval Authority & Notification Requirements | PM sign-off of moderate (M) risks with potential Long term injury or illness consequence. Responsible for ensuring the relevant higher authority is notified of the high consequence risks i.e OD and EMT. | int | PM (JHE) | relevant items to be reviewed and signed off as per the Delegation of Authority flow. Completion of this process to be evidenced by the PM signature in the 'Evaluation' column of this table. | TBA | closed | refer to relvant HAZID tab column (DATE Closed/Sign Off)
23 | 2022-03-22 | Approval Authority & Notification Requirements | OD sign-off of moderate (M) risks with potential Fatality or permanent disability consequence. Responsible for ensuring the relevant higher authority is notified of the high consequence risks i.e. EMT. | int | OD (JPO) | relevant items to be reviewed and signed off as per the Delegation of Authority flow. Completion of this process to be evidenced by the OD signature in the 'Evaluation' column of this table. | TBA | closed | refer to relvant HAZID tab column (DATE Closed/Sign Off)
24 | 2022-09-08 | 12.0 HDD | 12.3 – Update to include. Access via Seawall Road HDD1 – Traffic Control Plans in place (Reviewed and Approved) | int | PWY | done | 2022-09-09 | closed | refer relevant HAZID tab and item number
25 | 2022-09-08 | 12.0 HDD | 12.15 – Update to Include - Applicable Management Plans Approved prior to commencement of works | int | PWH | done | 2022-09-09 | closed | refer relevant HAZID tab of item number
26 | 2022-09-08 | 7.0 Welding | 7.9 – Add in Safety Essentials #3 Mobile Plant, #9 Foreign Services, #6 Lifting Equipment & VRD (Voltage Reduction Device) must be used | int | PWH | done | 2022-09-09 | closed | refer relevant HAZID tab be item number
27 | 2022-09-08 | 7.0 Welding | 7.10 – Updated item 4 to LTI and Item 6 to LTI/MTI | int | PWH | done | 2022-09-09 | closed | refer relevant HAZID tab LTI item number
28 | 2022-09-08 | 4.0 Pipe Handling | 4.4 Add in 2. Licenced drivers and experienced and Use only designated access points and existing pipeline cross-over points | int | PWH | done | 2022-09-09 | closed | refer relevant HAZID tab over item number
29 | 2022-09-08 | 4.0 Pipe Handling | 4.1 – Added in Use of slings permitted, but must be rated and tested and tagged and inspected prior to use | int | PWH | done | 2022-09-09 | closed | refer relevant HAZID tab to item number
30 | 2022-09-08 | 4.0 Pipe Handling | 4.10 Added in 2. Tools to be used to safely remove end caps. Soft mallets to be used for re-installation (not to be installed by banging on with hands) | int | PWH | done | 2022-09-09 | closed | refer relevant HAZID tab with item number
31 | 2022-09-08 | 10.0 Excavation | 10.1 added in Hazard - External Road Users / General Public | int | PWH | done | 2022-09-09 | closed | refer relevant HAZID tab General item number
ACTIONS: Is there a need to liaise with/notify client/public/other entities to implement a HIRAC process for any hazards impacting any of the parties?
no specific third party actions identified as being required at this particular juncture.

## Reference Documents
Reference Documents
Acts & Regulations | Codes of Practice / Guidelines
|  | Document Number | Nacap Standard Procedures | NSW Codes of Practice (https://www.safework.nsw.gov.au/resource-library/list-of-all-codes-of-practice): | Publisher | Designation | AUSTRALIAN STANDARDS Title
|  | 3902-CORP-002-3 | Internal Audit Procedure | Abrasive Blasting Code of Practice | AS | 1319 | Signs for the occupation environment
|  | 3902-CORP-004-3 | Principles of Change Management | Confined Spaces Code of Practice | AS | 1353.2 | Flat synthetic webbing slings – Care and use
|  | 3903-HR-002-2 | Code of Conduct | Construction Work Code of Practice | AS | 1418.1 | Cranes, hoists and winches – General requirements
|  | 3903-HR-007-3 | Discrimination, Harassment and Bullying Prevention Procedure | Demolition Work Code of Practice | AS | 1418.5 | Cranes, hoists and winches – Mobile cranes
|  | 3905-HSE-003-3 | Health and Safety Legal Compliance | Excavation Work Code of Practice | AS | 1418.8 | Cranes, hoists and winches – Special purpose appliances
|  | 3905-HSE-001-3 | Fitness for Work Procedure | First Aid in The Workplace Code of Practice | AS | 1418.1 | Cranes, hoists and winches – Mobile elevating work platforms
|  | 3905-HSE-002-3 | Incident Reporting and Investigation Procedure | Hazardous Manual Tasks Code of Practice | AS | 1418.11 | Cranes, hoists and winches – Vehicle loading cranes
|  | 3905-HSE-007-3 | Procedure for Health Risk Assessment and Monitoring | Managing Electrical Risks in The Workplace Code of Practice | AS | 1742.3 | Manual of uniform traffic control devices
|  | 3905-HSE-008-3 | Coronavirus Management Plan | Managing Noise and Preventing Hearing Loss at Work Code of Practice | AS | 1885.1 | Measurement of occupational health and safety performance
|  | 3904-OPS-001-3 | Safe Driving and Light Vehicle Management Procedure | Managing the Risk of Falls at Workplaces Code of Practice | AS | 1892.5 | Portable ladders – Selection, safe use and care
|  | 3904-OPS-002-3 | Verification of Competency Procedure | Managing Risks of Hazardous Chemicals in The Workplace Code of Practice | AS | 1940 | The storage and handling of flammable and combustible liquids
|  | 3904-OPS-003-3 | Heavy Vehicle Operations | Managing the Risks of Plant in The Workplace Code of Practice | AS | 2294.1 | Earthmoving machinery – Protective structures – General
|  | 3904-OPS-004-3 | Hazardous Chemicals – Storage, Handling and Use | Welding Processes Code of Practice | AS | 2397 | Safe use of lasers in the building and construction industry
|  | 3904-OPS-005-3 | Mobile Crane Operations | Work Near Overhead Power Lines Code of Practice | AS | 2550.1 | Cranes, hoists and winches – Safe use – General requirements
|  | 3904-OPS-006-3 | Dangerous Goods Transport | Moving Plant on Construction Sites Code of Practice | AS | 2550.5 | Cranes, hoists and winches – Safe use – Mobile cranes
|  | 3904-OPS-007-3 | Subcontract Management Procedure |  | AS | 2550.1 | Cranes, hoists and winches – Safe use – Mobile elevating work platforms
|  | 3904-OPS-009-3 | Vendor Assessment Procedure | Safe Work Australia Model Codes of Practice (https://www.safeworkaustralia.gov.au/resources-publications/model-codes-of-practice): | AS | 2550.11 | Cranes, hoists and winches – Safe use – Vehicle loading cranes
|  | 3904-OPS-010-3 | Management of Design | Construction Work Code of Practice | AS | 2550.15 | Cranes, hoists and winches – Safe use – Concrete placing equipment
|  | 3904-OPS-012-3 | Safe Working with Electricity Procedure |  | AS | 2550.19 | Cranes, hoists and winches – Safe use – Telescopic handlers
|  | 3904-OPS-013-3 | Foreign Services Procedure | National Transport Commission (https://www.ntc.gov.au/codes-and-guidelines/load-restraint-guide): | AS | 2759 | Steel wire rope – Use, operation and maintenance
|  | 3904-OPS-014-3 | Working at Heights Procedure | Load Restraint Guide 2018 | AS | 2865 | Confined spaces
|  | 3904-OPS-016-3 | Safe Excavation Procedure | Load Restraint Guide for Light Vehicles 2018 | AS | 3775.2 | Chain slings for lifting purposes – Grade T(80) and Grade V(100) – Care and use
|  | 3905-HSE-010-3 | Chain of Responsibility Procedure |  | AS | 4326 | The storage and handling of oxidising agents
|  | 3904-OPS-019-3 | Confined Space Procedure |  | AS | 4497 | Roundslings – Synthetic fibre
|  | 3904-OPS-018-3 | Permit to Work Procedure |  | AS | 4603 | Flashback arrestors – Safety devices for use with fuel gases and oxygen or compressed air
|  | 3904-OPS-017-3 | Traffic Management (Construction in Public Thoroughfares) |  | AS | 4772 | Earthmoving machinery – quick hitches for excavators and backhoe loaders
|  | 3907-PLA-002-3 | Management of Plant on Projects |  | AS | 4839 | The safe use of portable and mobile oxy-fuel gas systems for welding, cutting, heating and allied processes
|  | Safety Essential 1 | Senior Management Commitment |  | AS | 4991 | Lifting devices
|  | Safety Essential 2 | Excavation |  | AS/NZS | 1269 | Occupational noise management – overview and general requirements
|  | Safety Essential 3 | Mobile Plant |  | AS/NZS | 1269.1 | Occupational noise management – measurement and assessment of noise emission and exposure
|  | Safety Essential 4 | Safe Driving & LV Management |  | AS/NZS | 1269.2 | Occupational noise management noise control management
|  | Safety Essential 5 | Mobile Crane |  | AS/NZS | 1269.3 | Occupational noise management – hearing protector program
|  | Safety Essential 6 | Lifting Equipment |  | AS/NZS | 1270 | Acoustics – Hearing protectors
|  | Safety Essential 7 | Safe Working with Electricity |  | AS/NZS | 1336 | Eye and face protection - Guidelines
|  | Safety Essential 8 | Isolation of Plant-Equipment-Services |  | AS/NZS | 1337.1 | Personal eye protection – Eye and face protectors for occupational applications
|  | Safety Essential 9 | Foreign Services |  | AS/NZS | 1337.6 | Personal eye protection – Prescription eye protectors against low and medium impact
|  | Safety Essential 10 | Worksite Traffic |  | AS/NZS | 1715 | Selection, use and maintenance of respiratory protective equipment
|  | Safety Essential 11 | Traffic (Construction in Public Thoroughfares) |  | AS/NZS | 1768 | Lightning protection
|  | Safety Essential 12 | Hazardous Chemicals - Storage, Handling & Use |  | AS/NZS | 1800 | Occupational protective helmets – Selection, care and use
|  | Safety Essential 13 | Dangerous Goods Transport |  | AS/NZS | 1801 | Occupational protective helmets
|  | Safety Essential 14 | Emergency Preparedness and Response |  | AS/NZS | 2210.1 | Safety, protective and occupational footwear – Guide to selection, care and use
|  | Safety Essential 15 | Heat Stress |  | AS/NZS | 2210.4 | Occupational protective footwear – Specification for protective footwear
|  | Safety Essential 16 | Hazard Identification Risk Assessment and Control (HIRAC) |  | AS/NZS | 3000 | Electrical installations (Australian / New Zealand Wiring Rules)
|  | Safety Essential 17 | Safe Working at Heights |  | AS/NZS | 3010 | Electrical installations – Generating sets
|  | Safety Essential 18 | Chain of Responsibility |  | AS/NZS | 3012 | Electrical installations - Construction and demolition sites
|  | Safety Essential 19 | Training Management |  | AS/NZS | 3017 | Electrical installations – Verification guidelines
|  | Safety Essential 20 | Project Performance Management |  | AS/NZS | 3760 | In-service safety inspection and testing of electrical equipment
|  | Safety Essential 21 | Hydrostatic Pressure Testing Operations |  | AS/NZS | 3845.1 | Road safety barrier systems and devices – Road safety barrier systems
|  | Safety Essential 22 | Incident Investigation & Corrective Action |  | AS/NZS | 3845.2 | Road safety barrier systems and devices – Road safety devices
[5 empty] | AS/NZS | 4853 | Safe working on or near low-voltage electrical installations and equipment

## 0.0 General
0.0 General
IDENTIFY THE TASK or PROCEDURE, DESCRIBE THE HAZARDS AND RISKS, LIST THE CONSEQUENCES AND WHAT ARE THE EXISTING CONTROLS. | [6 empty] | EXISTING RISK |  |  | Recommendations | Responsibility | RISIDUAL RISK |  |  | STATUS | DATE Closed/Sign Off
ID | TASK or PROCEDURE What are the Job Steps | HAZARDS and RISKS What are they | CONSEQUENCES Resulting in | EXISTING CONTROLS | Consultation Method | 3rd Party Liaison? | Consequence | Likelihood | Level Of Risk |  |  | Consequence | Likelihood | Level Of Risk
0.1 | Presenting fit for work. | 1. All personnel - under the influence of alcohol and/or drugs causes incident resulting in injury to personnel. | Lost Time Injury, Damage to Asset, Damage to Pipe , Exposure, Injury | 1. Adopting a zero drugs and alcohol policy for work related driving. Drug and alcohol screening prior to employment, random and suspect testing during Project. Fit for work screening. Peer Assessment. Daily BrAC testing of all personnel. | Safe Driving Procedure, Driver Induction, Driver Approval, EBA, Employee Assistance Program, Induction, Prestart, Toolboxes, JSA, Lift Plans, PTW, VOC, TMP | Y | A | 5 | M
|  | 2. Fatigue, Personal Illness, prescription medication. | Fatality, Lost Time Injury, Damage to Asset, Damage to Pipe , Fatigue, Injury | 2. Taking into account the influence of medications before driving. Monitoring through Nacap's Fatigue Assessment form. EBA. Medical Clearance. Site Induction and clear expectations around prescribed medicines. |  |  | A | 5 | M
|  | 3. Noncompliance with driving rules. | First Aid Injury, Damage to Property/Equipment, Impact on Third Party Relationship, Lack of Attention - Error, Vehicle Incident | 3. Driver education training and induction. Discipline procedure will be implemented. Approved driver, driver declaration Community interface and awareness |  |  | E | 3 | L
|  | 4. Personal issues/problems. | First Aid Injury, Damage to Property/Equipment, Impact on Third Party Relationship, Lack of Attention - Error, Vehicle Incident | 4. Use of Employee Assistance Program. Open communication / peer support within work crew members Awareness through toolbox talks, pre starts |  |  | E | 3 | L
0.2 | Checking vehicle prior to use daily. | 1. Mechanical failure causes accident owing to checks not completed. | Permanent Disability, Damage to Property/Equipment, Vehicle Incident | 1. Daily checks (weekly recorded) of vehicles i.e. fuel, water, oils, brakes and lights by driver. Scheduled service and maintenance by vehicle provider. DO NOT USE vehicles with safety related faults present (i.e. brakes, steering, etc.). Safety Walks. Daily 360 walk-around. Fit for purpose vehicles and nominated drivers for project. | Weekly Inspection, Certification, LOTO Procedure, Induction, Prestart, Toolboxes, JSA, Lift Plans, PTW, VOC, TMP |  | D | 4 | L
|  | 2. Personal injury during pre-start checks including entanglement – belts and fan, crush injuries, safety related fault and hot fluids/burns i.e. water/oil. | First Aid Injury, Burns to skin, Crush Injury, Eye Injury, Lack of Attention - Error, Spill | 2. Motor fluid checks completed while engine is switched off and cooled down. Handbrake applied whilst conducting checks. Refill radiator using the water reservoir. |  |  | E | 3 | L
|  | 3. Mechanically unsuitable. | Medical Treatment Injury, Vehicle Incident | 3. Tag out vehicle and replace with suitable alternative vehicle. |  |  | D | 4 | L
0.3 | Prestart checks of equipment | 1. Slips, trips, fall when checking oils, fluids and greasing. Slippery surfaces ( dust, wet) | Medical Treatment Injury | 1. Clean surfaces of excessive dust / dirt: - 3 points of contact when climbing access steps. - Clean steps and platforms. | JSA, Prestart Checklists, VOC, PHA, Prestarts, Toolboxes | Y | D | 4 | L
|  | 2. Exposure to Dangerous Goods / Hazardous Substances | First Aid Injury, Allergic Reaction, Burns to skin, Respiratory Issues | 2. Review SDS , handle, store Dangerous Goods / Hazardous substances and wear PPE in accordance with SDS. |  |  | E | 4 | L
|  | 3. Environmental Hazard as a result of leaks (including Oil and Fuel) | Environmental Impact, Spill | 3. Contain leaks with spill kit advise Construction Superintendent of all spills. Spill kits to be readily available. |  |  | E | 3 | L
|  | 4. Injury due to poor ground conditions – uneven ground. Leg injuries | First Aid Injury | 4. Check for any obstacles or potholes when walking around machine. Park plant in area that enables inspection without obstacles in way, where practicable |  |  | E | 4 | L
|  | 5. Damaged/dangerous equipment causing injury to personnel from guards / handrails / E-stop / lights, Electrocution from generators, etc. | Lost Time Injury, Medical Treatment Injury | 5. Prestart log book to be completed daily, PHA to be read by operator and signed. Competent operator to conduct checks. LOTO and report unsuitable equipment. Electrical Test and Tag, RCD operational. |  |  | D | 4 | L
|  | 6. Other vehicles driving through work area – no call up | Damage to Property/Equipment, Impact on Third Party Relationship, Vehicle Incident | 6. Operator ID Magnets placed on each machine with UHF Channel displayed. |  |  | E | 3 | L
|  | 7. Inadequate firefighting equipment | Damage to Property/Equipment, Environmental Impact, Fire, Impact on Third Party Relationship | 7. Ensue firefighting equipment is adequate i.e. 9kg extinguishers. |  |  | E | 3 | L
|  | 8. Untrained / inexperienced operators. | First Aid Injury, Lack of Attention - Error, Production Delays | 8. Only qualified , VOC’d and supervisor approved operators to inspect and operate any machines. |  |  | E | 4 | L
0.4 | Working in Hot Conditions | 1. Heat related illness. | Fatality, Lost Time Injury, First Aid Injury, Exposure, Heat Stress/Stroke, Injury | 1. Heat Cramps, Exhaustion & Stroke - all personnel trained of the dangers, symptoms, and treatment of heat illness (project induction, tool box talks and pre-start meetings). All vehicles to carry sufficient quantities of potable water per person.All personnel to carry water when working remote from potable water source. Hard hats brim extension is supplied. Majority of vehicles are fitted with air conditioning. Monitor ambient temperatures via BOM website and convey to work personnel of expected and anticipated temperatures for that particular day. Shade provisions as practicable Site-specific risk assessment of potential heat stress hazards Heat Stress Induction Where a high or extreme heat stress risk is identified, some of the exposure controls as follows: - acclimatisation periods - cool rest areas - relocation of tasks to a cooler area or reschedule work to cooler times of the day or night shift where practicable - provision of cooling vest / collars Risk management for extreme heat risk activities will include personal hydration testing (urine specific gravity) and the implementation of suitable work / rest regimes based on measurements taken by a competent person | Induction, Prestart, Toolboxes, JSA, PTW, TMP | Y | B | 5 | M
0.5 | Working in Cold / Wet Conditions | 1. Cold related illness. | Fatality, First Aid Injury, Exposure, Health Effects | 1. Weather specific PPE provided to work personnel; management of change; review weather forecast from BOM website; Toolbox meetings; daily JSA review |  |  | B | 5 | M
0.6 | Working in Windy Conditions | 1. Equipment stability, damage, airborne particles | First Aid Injury, Community Complaints, Damage to Pipe , Damage to Property/Equipment, Damage to Reputation, Eye Injury, Health Effects, Object Across Road, Dust | 1. PPE - eye protection Dust suppression on open excavations, soil stockpiles, housekeeping Equipment operating envelopes Weather forecasting and work planning |  |  | D | 4 | L
0.7 | Working Near / With Electricity and Electrical Equipment | 1. Contact with overhead electrical conductors or services. | Community Complaints, Damage to Asset, Damage to Property/Equipment, Damage to Reputation, Eye Injury, Impact on Third Party Relationship, Production Delays, Project Stopped | 1. Power lines identified with catenaries, warning signs and hazard tape. Catenaries shall be set at a height that ensures minimum clearances to conductors are maintained. Site supervision, right personnel and qualifications including first aid certificate. Asset owner approval / representative onsite liaison Qualified Safety Observers are required when: a) there are works in the vicinity of overhead power lines. b) there is a risk of contact or break of the specified minimum separation to the conductor. c) where required, personnel shall comply with permit to work requirements of asset owners. d) whenever the work activity is likely to be performed in the Accredited Person Zone e) whenever a crane, mobile plant or load is in motion and is likely to come closer than the approach distances f) carrying out ‘tree and vegetation management’ near live overhead power lines Safety Observer: means an accredited person specifically assigned the duty of observing and warning against unsafe approach to overhead power lines and associated electrical apparatus, or other unsafe conditions. Must have received training for work near overhead power lines conducted by a Registered Training Organisation. Must have successfully completed an appropriate training course (eg Crane and Plant Electrical Safety Course) | Induction, Prestart, Toolboxes, JSA, Lift Plans, PTW, VOC, TMP, Working with Electricity Procedure | Y | A | 5 | M
|  | 2. Electric shock due to faulty equipment or installation. | Damage to Property/Equipment, Disability, Fatigue, Injury, Loss of Production | 2. Personnel to be made aware of hazards and safety measures at project induction and pre-start meetings. Electrical equipment to be installed and stripped out by qualified electricians. Electrical system to be fitted with earth leakage circuit breakers (ELCB). Equipment and appliances to be checked and tagged for use as per Australian Standards by an electrician. Equipment found to be defective to be tagged ‘Out of Service’. |  |  | A | 5 | M
0.8 | Activities Where There Is Risks Of Falls | 1. Personnel Trips – Slips. | Fatality, Lost Time Injury, Medical Treatment Injury, First Aid Injury, Disability, Eye Injury, Fatigue, Loss of Production | 1. Personnel to be made aware of trip and slip hazards in induction process. Personnel encouraged to be observant in their construction activities. Lighting to be adequate for work. Rubber soled ¾ laced up steel capped safety boots to be worn by all personnel when on site. Lay out of work area to be designed to minimise creation of trip hazards. Existing trip hazards to be identified where possible and removed or highlighted. Correct ingress and egress of vehicles - maintain 3 points of contact at all times | Induction, Prestart, Toolboxes, JSA, Lift Plans, PTW, TMP |  | E | 3 | L
|  | 2. Personnel fall into watercourse/river. | Fatality, Lost Time Injury, Medical Treatment Injury, First Aid Injury, Exposure, Health Effects | 2. Personnel to be instructed on dangers and safe work methods for working near water. Personnel working immediately adjacent to flowing watercourses to wear life vest or harness. Personnel working near water course(s) to have a spotter on standby. If required a specific JSA for working near / in watercourses shall be produced for personnel. Working platform adequate and suitable for tasks |  |  | B | 5 | M
|  | 3. Personnel fall from height. | Fatality, Permanent Disability, Lost Time Injury, First Aid Injury, Damage to Asset, Injury, Loss of Production | 3. Personnel only to work at height when task the task cannot be eliminated or avoided. Only Personnel trained in the dangers and safe work methods for working at height. Use of Nacap PTW system. Harness and safety line to be worn by all personnel working at 2m or more in height. Personnel wearing harnesses and safety lines must be trained and competent in using the equipment. Work at height equipment must be inspected before and after use and only operated by those licenced and competent to do so. Ladders (inspected prior to use and recorded on register) or stairs to be used to climb to height, 3 points of contact maintained at all times. No personnel to ride lifted loads or in machine buckets (cranes, forklifts or excavator). |  |  | A | 5 | M
0.9 | Using Hand Tools | 1. Personnel injury due to strike using hand tools. | Lost Time Injury, Medical Treatment Injury, First Aid Injury, Eye Injury | 1. Operator to be experienced in operating hand tools. - Advised on dangers and safe work methods for working with hand tools. - First aid trained personnel to be accessible by all personnel on site (names and contact details in ERP in vehicle glove box and site offices / crib hut) - Correct PPE to be worn when using hand tools (i.e. gloves and eye protection when using hammers). - Always stop and think, is this the correct tool for the job. If not ensure the right tool is available. - well maintained and tools in serviceable condition -If flogging spanners are to be used then a flogger holder tool must be used to prevent injury to hands or fingers - no unauthorised modification of hand tools; no use of makeshift hand tools | Induction, Prestart, Toolboxes, JSA, Lift Plans, PTW, VOC, TMP |  | D | 4 | L
0.1 | Disposal Of Waste | 1. Rubbish and waste on site. | Community Complaints, Environmental Impact | 1. No waste allowed to be buried in pipeline trench left on site except in recognised collection point. - Waste bins provided at nominated locations - Waste to be disposed of by licensed waste disposal contractor. - Contaminated materials categorised and disposed of in accordance with environmental and CEMP conditions | Induction, Prestart, Toolboxes, JSA, PTW, TMP | Y | E | 4 | L
0.11 | Working In Dust (refer 0.6 also) | 1. Eye / Respiratory irritation (including when service proving) | Medical Treatment Injury, Allergic Reaction, Community Complaints, Exposure, Eye Injury, Respiratory Issues | 1. Personnel to wear safety glasses on the site. - Goggles to be available. - Personnel to wear dust masks or bandannas in dusty conditions. - Dust masks and bandannas available from the store. - Dust suppression to be carried out so far as reasonably practicable (Water trucks). - Personnel on foot to move out of travel area (dusty area). | Induction, Prestart, Toolboxes, JSA, PTW, VOC, TMP | Y | D | 4 | L
0.12 | Working On Site | 1. Insect Bites and Stings | First Aid Injury, Allergic Reaction | 1. Sprays for treatment of bites and stings to be available from project store. | Induction, Prestart, Toolboxes, JSA, Lift Plans, PTW, VOC, TMP |  | E | 4 | L
|  | 2. Snakes | Fatality, Lost Time Injury, Allergic Reaction, Security Breach | 2. Long Pants and correct PPE First aid (and snake bite) kits and ERP details Use of gators where risk assessment deems necessary |  |  | A | 5 | M
|  | 3. Sharps / syringes | Medical Treatment Injury, First Aid Injury, Health Effects | 3. Sharps check at start of each shift - to be included within SWMS for safe cleanup using stab resistant gloves and sharps bin. |  |  | C | 5 | L
0.13 | Noisy Activities | 1. Excessive Noise. | Community Complaints, Damage to Reputation, Impact on Third Party Relationship, Project Stopped | 1. Personnel to be considerate of noise generated near third parties whilst performing work activities. Personnel educated about the dangers of working in noisy areas (toolbox talks). Ear plug and ear muff PPE to be provided. Personnel in noisy areas to be minimised. Exposure time to be limited where possible. Conform to EPA requirements. EM notification to local residents / community on construction works commencing and associated noise. Keep noisy activiites to short duration where possible. comply with land acccess agreements; use of nacap LECH Form 2 | Induction, Prestart, Toolboxes, JSA, Lift Plans, PTW, VOC, TMP | Y | D | 4 | L
0.14 | Manual Handling | 1. crushing, pinches. | Lost Time Injury, Crush Injury, Fire, Hand Injury | 1.Inductions, Worksafe hand campaign, no knife policy Right glove for the right job Use equipment to lift wherever possible. Employ correct methods for safe lifting (manual handling) and be aware of personnel lifting limits . Consider the size and weight of the load. Ensure stable footing. Keep your back straight when lifting. Bend your knees and lift with your legs. Keep the load in close to your body, turn your body and do not twist from the waist. | Induction, Prestart, Toolboxes, JSA, Lift Plans, PTW, VOC, TMP |  | D | 4 | L
0.15 | Securing loads | 1. Load shift related incident. Falling objects from vehicles. | Fatality, Lost Time Injury, First Aid Injury, Crush Injury, Eye Injury, Injury, Lack of Attention - Error | 1. Securing of all vehicle contents prior to driving off including locking of canopies, toolboxes and using small holed cargo nets on all light vehicles (check rating of restraints used). Use appropriate loading and lifting technique (i.e. mechanical lifting/3rd party, two person lift) 2. Maintain three point of contact for access/egress to tray area. use designated access point to gain access to tray 3. Load or unload a vehicle in a manner that does not obstruct your vision of other vehicles and complies with legislation. | Induction, Prestart, Toolboxes, JSA, Lift Plans, PTW, VOC, TMP |  | E | 3 | L
0.16 | Driving / Operating near public, infrastructure and plant. | 1. Colliding with infrastructure, noncompliance with driving rules and ignoring barriers. | Medical Treatment Injury, Collision, Damage to Property/Equipment, Damage to Reputation, Environmental Impact, Fire, Injury, Vehicle Incident | 1. Inductions and Permit to enter (where required) Awareness of construction in area. Traffic control plans/s developed (location specific where required). Council approval where required Barricading, signage, restricted speed as per driving rules. Flagging hazards on site i.e. poles, adjacent to valves, catenaries for power lines and signs. Exclusion zones where required for foreign services. Start and end points of excavation to be barricaded. | Induction, Prestart, Toolboxes, JSA, Lift Plans, PTW, VOC, TMP Nacap Traffic Management (Construction in Public Thoroughfares) 3904-OPS-017-3 Nacap Safety Essential #10 Worksite Traffic |  | D | 4 | L
|  | 2. Collision with plant or excavations on site. | Medical Treatment Injury, Collision, Damage to Property/Equipment, Vehicle Incident | 2. Inductions and site specific requirements carried out Slow to maximum of 10km/h or walking pace when within 50m of plant. Refer to Plant/Operator Identification Decal on Plant. Use radio and/or horn to get plant operator attention and permission to pass. Establish eye contact. Implementation of Nacap Safe Plant Interaction (SPIN) Program |  |  | D | 4 | L
0.17 | Car park, muster point access and egress from site office | 1. Collisions with other vehicles, infrastructure and pedestrian. | Fatality, Permanent Disability, Lost Time Injury, First Aid Injury, Collision, Exposure, Vehicle Incident | 1. Reverse parking and drive through unless otherwise signposted. Park in designated car park. Survey surroundings prior to exiting car park. Segregated / delineated access for pedestrians Construct designated walkways where practicable. Project team to risk assesses car park, muster point areas for adequacy. Project manager to address community needs. | TMP, nominated drivers for project Nacap Safety Essential #10 Worksite Traffic |  | E | 3 | L
0.18 | Reversing | 1. Collisions with other vehicles, infrastructure and pedestrian. | First Aid Injury, Collision, Damage to Property/Equipment, Lack of Attention - Error, Vehicle Incident | 1. When the driver of a vehicle is required to manoeuvre in a tight space or reverse a vehicle, a guide is to be used whenever practicable. While the guide is responsible for the safety of the vehicle, the driver is not absolved from their duty of care to other road users. The driver must have a clear view of the guide at all times. Should the driver’s view of the guide become obscured, the driver is to stop the vehicle immediately. Where no guide is available, and where practical, the driver is to dismount and physically check clearance before reversing. A driver who strikes an object/person whilst reversing may face administrative/disciplinary proceedings for driving without due care and attention. Clean windows and mirrors. | Safe Driving Procedure, Driver Induction, Driver Approval, Induction, Prestart, Toolboxes, TMP |  | E | 3 | L
0.19 | Walking Machines between work site | 1. Other vehicles – collision. | Fatality, Collision, Damage to Property/Equipment, Impact on Third Party Relationship, Vehicle Incident | 1. Relocate vehicle out of travel path, communicate with UHF. | Induction, Prestart, Toolboxes, JSA, Lift Plans, PTW, VOC, TMP | Y | A | 5 | M
|  | 2. Hitting pipe. | Damage to Asset, Damage to Pipe , Damage to Property/Equipment, Impact on Third Party Relationship, Lack of Attention - Error | 2. Check travel path and move clear of pipe. |  |  | D | 4 | L
|  | 3. Crushing – other personnel. | Fatality, Crush Injury, Damage to Reputation, Impact on Third Party Relationship, Project Stopped | 3. Use UHF to communicate, travel slow, toot horn, rotating beacon on. Reversing Alarm, Exclusion Zones stipulated within JSA, procedural Video. Ensure that operator ALWAYS has escort in line of sight, if unable to then operator to stop vehicle/plant |  |  | A | 5 | M
|  | 4. Overhead services. | Fatality, Damage to Property/Equipment, Damage to Reputation, Impact on Third Party Relationship, Project Stopped | 4. Check and look for catenaries and signage , spotter to be used. |  |  | E | 2 | M
|  | 5. Crossing Roads - Damage to Road and Material on Roads. | Community Complaints, Damage to Asset, Damage to Reputation, Impact on Third Party Relationship, Production Delays | 5. Use rubber based protection (eg: tyres), clean up dropped material immediately. Traffic Control - Traffic Management Plan. Use of tilt-tray and low-loaders for machine transport. |  |  | D | 4 | L
0.2 | Permit Close out | 1. Failure to properly secure site causing disruption to service owners and road users 2. Carrying out works not permitted on permit and not written in approved JSA | Community Complaints, Damage to Asset, Damage to Property/Equipment, Damage to Reputation, Environmental Impact, Lack of Attention - Error, Production Delays, Project Stopped, Vehicle Incident | 1. Permit holder training, clear conduit of information and defined requirements prior to carrying out task. Liaison with Permit issuing officer to ensure no delays. Community notified in advance where potential impact to routine activities are impacted. 2. Walk through and familiarise with site and works to be conducted for the day - If its not on the permit or JSA permit, then permit is required to be revalidated and re-issued. | Inductions, Toolboxes, JSA, Prestart | Y | C | 3 | M
0.21 | Escorted Visitors | 1. Unauthorised entry to restricted area causing damage to property and personnel 2. Refuelling truck (mini tankers) not following site regulations. | Community Complaints, Damage to Asset, Damage to Property/Equipment, Damage to Reputation, Environmental Impact, Lack of Attention - Error, Project Stopped, Spill, Vehicle Incident | 1.Escort visitors for the entire duration whilst onsite. Driver induction (briefing) prior to entry to site. 2. Provided information with contact numbers given to delivery companies prior to arriving onsite. | Inductions, Toolboxes, JSA Prestart | Y | C | 3 | M
0.22 | Working in excavations | 1. Confined Space | Fatality | 1. All bell holes will be treated as CSE, unless assessement has been carried out by compenetent person deeming no CSE for bellhole exists | Induction, Prestart, Toolboxes, JSA, Lift Plans, PTW, VOC, TMP |  | B | 4 | M
0.22a | Access site. | 4. Falling objects from canopy | First Aid Injury | 1. Be observant “look first”. Lace up safety boots. | Induction, Prestart, Toolboxes, JSA, Lift Plans, PTW, VOC, TMP |  | E | 4 | L
|  | 5. Burns/Radiation/Hot welding rods | Fatality, Project Stopped | 2. Line list, dial before you dig service, alignment sheets, permits required to proceed, signage. Look up – be observant. Erect catenaries. |  |  | A | 5 | M
|  | 6. Noxious fumes when welding | Fire, Flooding | 3. Emergency Response Plan (ERP). Weather conditions monitored. Radio communications. Fire extinguishers and knap sacks. |  |  | E | 3 | L
|  | 7. Moving plant from joint to joint | Heat Stress/Stroke, Hyperthermia, Hypothermia | 4. Wear sunscreen, sleeves rolled down, sun brim for helmet. Water bottles provided. Air conditioned vehicles. Jackets, Vests and Beenies. |  |  | E | 3 | L
Note on G3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is there a need to liaise with/notify client/public/other entities to implement a HIRAC process for any hazards impacting any of the parties? If so, who and what actions are required?

## 1.0 Mobilisation
1.0 Mobilisation
IDENTIFY THE TASK or PROCEDURE, DESCRIBE THE HAZARDS AND RISKS, LIST THE CONSEQUENCES AND WHAT ARE THE EXISTING CONTROLS. | [6 empty] | EXISTING RISK |  |  | Recommendations | Responsibility | RISIDUAL RISK |  |  | STATUS | DATE Closed/Sign Off | TARGET LEVEL OF RISK |  | DATE RISK ADDED
ID | TASK or PROCEDURE What are the Job Steps | HAZARDS and RISKS What are they | CONSEQUENCES Resulting in | EXISTING CONTROLS | Consultation Method | 3rd Party Liaison? | Consequence | Likelihood | Level Of Risk |  |  | Consequence | Likelihood | Level Of Risk |  |  |  | RISK REVIEW DATE
1.1 | Access site, unload equipment, supplies etc. | 1. Poor ground conditions (slips and trips). | First Aid Injury | 1. Be observant “look first”. Lace up safety boots. Where possible unload or load on flat, smooth surfaces | Induction, Prestart, Toolboxes, JSA, Lift Plans, PTW, VOC, TMP |  | E | 4 | L
|  | 2. Overhead powerlines and buried services. | Fatality, Project Stopped | 2. Line list, dial before you dig service, alignment sheets, permits required to proceed, signage. Look up – be observant. Erect catenaries. |  |  | A | 5 | M
|  | 3. Hot weather – heat stress, sunburn. | First Aid Injury, Heat Stress/Stroke, Hyperthermia | 3. Wear sunscreen, sleeves rolled down, sun brim for helmet. Water bottles provided. Air conditioned vehicles. Inductions |  |  | E | 3 | L
|  | 4. Manual handling injuries when lifting heavy equipment. | Lost Time Injury | 4. Team lift for heavy / awkward items. PPE including gloves (cut and puncture proof rated) to prevent splinters and lacerations. Unload supplies close to worksite to reduce carrying distance. Inductions |  |  | C | 3 | M
|  | 5. Powered equipment operator error. | Medical Treatment Injury, Collision, Damage to Asset, Damage to Property/Equipment, Lack of Attention - Error, Vehicle Incident | 5. All operators of powered mobile plant must be competent (VOC) to operate. Where licenses are available these must be held by the operator/. Prestart inspections must be completed and documented where a logbook is provided prior to use daily. No unauthorized use of powered equipment permitted. |  |  | D | 4 | L
1.2 | Mobilisation of Temporary site buildings / containers | 1. Entering off West Dapto Rd and traffic not expecting oversize load turning | Crush Injury, Damage to Property/Equipment, Lack of Attention - Error | 1. Traffic management and mapping conveyed delivery company prior to site delivery of building Traffic management in place (where required) | Induction, Prestart, Toolboxes, JSA, Lift Plans, PTW, VOC, TMP |  | D | 4 | L
|  | 2. Temporary building on tilt tray becomes stuck and will not 'slide' off during unloading | Damage to Property/Equipment, Damage to Reputation, Lack of Attention - Error, Project Stopped | 2. Drivers to be competent in operation of unloading temporary building use reputable company. |  |  | A | 5 | M | [6 empty] | TBA
|  | 3. Overhead Services. | Fatality, Project Stopped | 3. Look up – be observant. Erect catenaries and use electrical spotter |  |  | E | 3 | L
|  | 4. Manual handling injuries when lifting heavy items. | Lost Time Injury | 4. Team lift for heavy / awkward items. PPE including gloves (cut and puncture proof rated) to prevent splinters and lacerations. Unload supplies close to worksite to reduce carrying distance. |  |  | C | 3 | M | [6 empty] | TBA
1.3 | Installation of services to temporary building | 1. Electrical trades person not familiar with site or work to be performed | Lost Time Injury, Production Delays | 1. Work to be performed provided prior to arriving on site. Clear conduit of information and known 'go to' person on site. Qualified electrician | Induction, Prestart, Toolboxes, JSA, Lift Plans, PTW, VOC, TMP |  | E | 3 | L
|  | 2. Electric shock due to faulty equipment or installation. | Damage to Property/Equipment, Disability, Injury, Loss of Production | 2. Personnel to be made aware of hazards and safety measures at project induction and pre-start meetings. Electrical equipment to be installed and stripped out by qualified electricians. Electrical system to be fitted with earth leakage circuit breakers (ELCB). Equipment and appliances to be checked and tagged for use as per Australian Standards by an electrician. Equipment found to be defective to be tagged ‘Out of Service’. |  |  | A | 5 | M | [6 empty] | TBA
1.4 | Security of site | 1. Member of public unauthorised entry to site causing injury to themselves | Fatality, First Aid Injury, Damage to Property/Equipment, Production Delays | 1. Lockup each evening. Security cameras installed at locations of high risk. Lighting sufficient at night | Induction, Prestart, Toolboxes, JSA, TMP |  | E | 3 | L
Note on G3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is there a need to liaise with/notify client/public/other entities to implement a HIRAC process for any hazards impacting any of the parties?

## 2.0 Access & Track Maintenance
2.0 Access & Track Maintenance
IDENTIFY THE TASK or PROCEDURE, DESCRIBE THE HAZARDS AND RISKS, LIST THE CONSEQUENCES AND WHAT ARE THE EXISTING CONTROLS. | [5 empty] | EXISTING RISK |  |  | Recommendations | Responsibility | RISIDUAL RISK |  |  | STATUS | DATE Closed
ID | TASK or PROCEDURE What are the Job Steps | HAZARDS and RISKS What are they | CONSEQUENCES Resulting in | EXISTING CONTROLS | Consultation Method | Consequence | Likelihood | Level Of Risk |  |  | Consequence | Likelihood | Level Of Risk
2.1 | Create access | 1. Mobile Power Plant - Collision - Vehicle - Pedestrians. | Medical Treatment Injury, Collision, Damage to Property/Equipment, Damage to Reputation, Lack of Attention - Error, Vehicle Incident | 1. Reversing Alarms, Beacons, VOC'd operators, Magnetic ID with UHF channel, Exclusion Zones - Barriers as required, Signage, Flagging. Designated pedestrian walkways | Traffic Management Plan, SWMS, Prestart, Toolbox | D | 4 | L
|  | 2. Foreign Service Strike. (refer to section 5.0 Foreign Services Location) | Medical Treatment Injury, Damage to Asset, Damage to Property/Equipment, Lack of Attention - Error | 2. Services positively identified and marked. DBYD |  | D | 4 | L
|  | 3. Working on road verges | Medical Treatment Injury, Collision, Damage to Property/Equipment, Lack of Attention - Error, Vehicle Incident | 3. Traffic Control in place as required (Traffic Management Plan) Site specific JSA. |  | D | 4 | L
2.2 | Erecting catenaries for overhead power lines. | 1. Manual handling injuries including strains when driving in pickets. | Medical Treatment Injury | 1. Team lift. Good posture when driving in pickets – use rammer. | SWMS, Prestarts, Toolboxes, Inductions | D | 4 | L
|  | 2. Hand injury when driving in steel star pickets. | Medical Treatment Injury | 2. Gloves must be worn. Use rammer. |  | D | 4 | L
|  | 3. Noise from driving in star pickets – hearing loss. | Permanent Disability | 3. Hearing protection to be worn when driving in star pickets with rammer. |  | B | 4 | M
2.3 | Access site, unload equipment, supplies etc. | 1. Poor ground conditions (slips and trips). | First Aid Injury, Lack of Attention - Error | 1. Be observant “look first”. Lace up safety boots., Housekeeping Where possible unload or load on flat, smooth surfaces | Induction, Prestart, SWMS, PTW, VOC. | E | 4 | L
|  | 2. Overhead powerlines and buried services. | Fatality, Damage to Property/Equipment, Impact on Third Party Relationship, Project Stopped | 2. Line list, dial before you dig service, alignment sheets, permits required to proceed, signage. Look up – be observant. Erect catenaries. |  | A | 5 | M
|  | 3. Manual handling injuries (lifting heaving equipment) | Lost Time Injury | 3. Team lift for heavy / awkward items. PPE including gloves (cut and puncture proof rated) to prevent splinters and lacerations. Unload supplies close to worksite to reduce carrying distance. |  | C | 3 | M
|  | 4. Powered equipment operator error. | Medical Treatment Injury, Collision, Damage to Asset, Damage to Property/Equipment, Lack of Attention - Error, Vehicle Incident | 4. All operators of powered mobile plant must be competent (VOC) to operate. Where licenses are available these must be held by the operator/. Prestart inspections must be completed and documented where a logbook is provided prior to use daily. No unauthorized use of powered equipment permitted. |  | D | 4 | L
2.4 | Excavating / Access Maintenance Works | 1. Worker struck by plant or excavated material. | Fatality, Lost Time Injury, Crush Injury, Loss of Production | 1. Exclusion zones apply – workers to stay out of plant operating and slewing zones. Stay out of the line of fire. Workers to get operators attention (line of sight) prior to approaching operating plant. | Induction, Prestart, SWMS | A | 5 | M
|  | 2. Damage to buried or overhead services. | Fatality, Damage to Property/Equipment, Impact on Third Party Relationship, Project Stopped | 2. Permit to Work rules apply. Maintain separation distances from powerlines. Maintain catenaries and warning signs. Spotter as required i.e. when operating near powerlines. |  | A | 5 | M
|  | 3. Slips and trips, falls into excavations. | First Aid Injury | 3. Workers to keep clear of excavations where practical. No access to excavations deeper than 1.5mtrs. unless benched, shored or battered. |  | E | 4 | L
|  | 4. Oil, fuel spills from plant. | Environmental Impact, Spill | 4. Hoses and fittings checked prior to use of machinery. Spill kit on location. |  | E | 4 | L
2.5 | Erect environmental fencing. | 1. Hand and eye injuries driving in star pickets and wooden stakes etc. | First Aid Injury | 1. Teamwork and task rotation to complete the work. Cut proof rated gloves to be worn and glasses. Use steel picket driver for star pickets. Use hammer in good condition with wooden pegs/stakes. Consider use of “gaffa” tape around top of wooden stakes to prevent splitting. Be observant of hand or finger pinch and crush points. | Induction, Prestart, SWMS, VOC | E | 4 | L
|  | 2. Manual handling strains filling and positioning sandbags etc. | Medical Treatment Injury | 2. Team work and job rotation. Bend knees and keep back straight. Report any injuries immediately. |  | D | 4 | L
|  | 3. Incorrect construction of sediment and erosion control. | Environmental Impact | 3. Work to procedures and diagrams provided. Consult with Construction Supervisor for advice. |  | E | 4 | L
2.6 | Erect chainmesh fencing and gates | 1. Manual handling injuries including strains. | Lost Time Injury | 1. Use telehandler etc. to unload / move heavy or bulky items such as chain mesh. Team lift, bend from the knees, straight back. PPE including gloves to be worn. | SWMS, SDS, Prestart Checklists, VOC, PHA, Prestarts, Toolboxes, Inductions, Form 1 and Form 2 | C | 3 | M
|  | 2. Material handling (dropped load, struck by telehandler etc.) related injuries. | Fatality, Damage to Property/Equipment | 2. Only licensed and competent (VOC)person to operate telehandler/forklift. Inspect plant and lifting equipment prior to use. Slings must be correct load rating for intended lift. Pedestrians to keep clear of moving plant. Reversing alarm must be fitted and working. |  | A | 5 | M
|  | 3. Auger injuries – entanglement. | Permanent Disability | 3. 1 meter exclusion zone around auger. No loose clothing to be worn by operator. Any long hair must be tied up. Tractor PHA reviewed by operators. Ensure auger is fully isolated before attempting to remove any obstruction. |  | B | 4 | M
|  | 4. Cement injuries – chemical burn, foreign body in eye. | Lost Time Injury, Exposure | 4. Review cement SDS to check hazards and controls required. Avoid skin contact with wet cement. Safety glasses and gloves to be worn. Eyewash available on site at all cement pours. |  | C | 4 | M
|  | 5. Release of stored energy – broken strained wire, tensioned chainmesh. | Medical Treatment Injury | 5. Ensure chainmesh is not excessively tensioned. Ensure chainmesh is correctly fastened to tension puller. Experienced and competent fencer to be engaged for project. Ensure chainmesh is pre-clipped at top in case of sudden release. |  | D | 4 | L
|  | 6. Compressed air jambro clip gun- eye injuries, pinch injuries. | Medical Treatment Injury, Eye Injury | 6. Check equipment and hoses for damage prior to use. Keep fingers clear of jambro clip stable point. Safety glasses mandatory. Disconnect clip gun to make repairs or remove blockages. |  | D | 4 | L
|  | 7. Trip and slip hazards. | First Aid Injury | 7. Ensure work area is clean and tidy with offcuts collected and placed in the appropriate waste or recycling collection bin. |  | E | 4 | L
2.7 | Using angle grinder to cut and grind metal. | 1. Burns and fire from sparks and hot metal. | Lost Time Injury, Medical Treatment Injury, Burns to skin, Environmental Impact, Fire | 1. PPE – gloves and cotton clothing to be worn, shirt buttoned up and sleeves down. Fire extinguishers and knap sacks close at hand. Fire watch, ERP, first aid kit and first aid officers in crew. Position guard in appropriate location to reduce sparks striking operator or areas of dry grass. VOC'd operator | VOC, SWMS, Prestarts, Toolboxes | D | 4 | L
|  | 2. Foreign body in eye. | Medical Treatment Injury, Eye Injury | 2. Double eye protection mandatory. Report any foreign body in eye injuries / discomfort or eye irritations immediately to First Aider. |  | D | 4 | L
|  | 3. Electric shock. | Medical Treatment Injury | 3. Electrical test and tag in date. Inspect lead, plug and switch prior to use. Ensure gloves are dry. RCD is mandatory |  | D | 3 | M
|  | 4. Noise causing hearing loss. | Permanent Disability | 4. Mandatory use of hearing protection applies when using grinder. |  | B | 4 | M
|  | 5. Disc shatters causing injury | Permanent Disability, Lost Time Injury, Medical Treatment Injury, First Aid Injury, Eye Injury | 5. Source quality grinding discs. Ensure disc RPM rating is compatible for the equipment |  | B | 4 | M
|  | 6. Lacerations from disc , operator error, kickback. | Medical Treatment Injury | 6. Competent operator (VOC completed). Guard fitted and tight. Cut proof gloves worn. Adopt safe body position with head well away from grinder and out of the line of fire should a kickback occur. Always turn grinder off when not in use and ensure disc has come to a complete stop before putting the grinder down. Ensure that grinder handle is always fitted and used, if grinder handle is to be removed a further risk assessment and consultation with Supervisor must be sought. |  | D | 3 | M
|  | 3, Overhead powerlines - LFI |  | 1. Earth stake to be maintained when working under overhead high voltage powerlines until pipe is tied in.
4. Falling objects from canopy
5. Burns/Radiation/Hot welding rods
6. Noxious fumes when welding
7. Moving plant from joint to joint
8. Fatigue from welding without rest breaks
9. Dust/dirt, grinding
10. Eye injury – Arc flash
11. Exposure to bad weather/lightning

## 3.0 Survey
3.0 Survey
IDENTIFY THE TASK or PROCEDURE, DESCRIBE THE HAZARDS AND RISKS, LIST THE CONSEQUENCES AND WHAT ARE THE EXISTING CONTROLS. | [6 empty] | EXISTING RISK |  |  | Recommendations | Responsibility | RISIDUAL RISK |  |  | STATUS | DATE Closed/Sign Off | TARGET LEVEL OF RISK |  | DATE RISK ADDED
ID | TASK or PROCEDURE What are the Job Steps | HAZARDS and RISKS What are they | CONSEQUENCES (relate to Objectives) Resulting in | EXISTING CONTROLS | Consultation Method | 3rd Party Liaison? | Consequence | Likelihood | Level Of Risk |  |  | Consequence | Likelihood | Level Of Risk |  |  |  | RISK REVIEW DATE
3.1 | Peg foreign services / Alignment | 1. Hand injuries i.e. crush / pinch and lacerations from hammering wooden stakes into the ground. | Medical Treatment Injury, Crush Injury | 1. All stakes and tools to be thoroughly checked before use. Gloves to be worn (cut proof 3+). Good quality stakes to be used and suitable hammer only. | Induction, Prestart, Toolboxes, JSA, PTW, TMP |  | D | 4 | L | [7 empty] | Low
|  | 2. Eye injuries from flying debris if stake splits | Medical Treatment Injury, Eye Injury | 2. Safety glasses must be worn to protect eyes. |  |  | D | 4 | L
|  | 4. Manual handling injuries from lifting survey equipment. | Lost Time Injury | 4. Adopt good lifting technique – load onto shoulders and hip. Team lift – share the load. Take frequent rest breaks. Plan what equipment is required for the task to be undertaken and importantly what’s not required to be carried. |  |  | C | 5 | L
|  | 5. Surveyor working on road - incident with road user | Fatality, Damage to Property/Equipment, Lack of Attention - Error | 5. Traffic management in place |  |  | A | 5 | M
3.2 | As builts process | 1. Struck by mobile powered plant working on site | Fatality, Lost Time Injury, Lack of Attention - Error | 1. Check with Lowering In Supervisor any exclusion zones established. Use radio, hand signals / eye contact to communicate with operators. Maintain safe working distance from plant (stay outside operating area and operator blind spots). When working in teams spot for each other. | Induction, Prestart, Toolboxes, JSA, PTW, TMP |  | A | 5 | M | [6 empty] | n/a | Low
|  | 2. Struck by pipe string movement | Permanent Disability, Crush Injury, Hand Injury | 2. Maintain safe separation distance from lowering in activities. Especially keep clear of crush zone between pipe and plant or pipe string and trench. |  |  | D | 4 | L
|  | 3. Slip / fall into trench or bell hole | Lost Time Injury, Medical Treatment Injury | 3. Maintain safe distance from edge of excavations – use off set extension pole to survey pipe. No walking on below ground pipe permitted. |  |  | D | 4 | L
|  | 4. Slip while attempting to enter bell hole | Lost Time Injury, Medical Treatment Injury | 4. Always enter bell holes using access ramps provided. |  |  | D | 4 | L
|  | 5. Bell hole or trench wall collapse | Fatality, Crush Injury | 5. Always inspect bell hole prior to entering. Bell hole should be benched at 1mtr intervals or sloped. If in doubt seek advice from OHS Advisor or Supervisor prior to entering bell hole. No access to trenches of depths greater than 1.5mtrs. Seek input from site OHS Advisor where wider sections of trench make pipe survey from ground level difficult. Pay close attention to the stability of trench walls prior to walking near. Use designated access points. |  |  | A | 5 | M | [6 empty] | n/a
|  | 6. Lone work - more likely to get injured due to lack of supervision | Medical Treatment Injury, Injury | 6. Any lone worker to be provided with radio communications. Regular check-in’s to occur and Supervisor visual checks. Additional controls to be discussed and documented on prestart. |  |  | D | 4 | L
3, Overhead powerlines - LFI
4. Falling objects from canopy
5. Burns/Radiation/Hot welding rods
6. Noxious fumes when welding
7. Moving plant from joint to joint
8. Fatigue from welding without rest breaks
9. Dust/dirt, grinding
10. Eye injury – Arc flash
11. Exposure to bad weather/lightning
Note on G3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is there a need to liaise with/notify client/public/other entities to implement a HIRAC process for any hazards impacting any of the parties?

## 4.0 Pipe Handling
4.0 Pipe Handling
IDENTIFY THE TASK or PROCEDURE, DESCRIBE THE HAZARDS AND RISKS, LIST THE CONSEQUENCES AND WHAT ARE THE EXISTING CONTROLS. | [5 empty] | EXISTING RISK |  |  | Recommendations | Responsibility | RISIDUAL RISK |  |  | STATUS | DATE Closed | TARGET LEVEL OF RISK |  | DATE RISK ADDED
ID | TASK or PROCEDURE What are the Job Steps | HAZARDS and RISKS What are they | CONSEQUENCES (relate to Objectives) Resulting in | EXISTING CONTROLS | Consultation Method | Consequence | Likelihood | Level Of Risk |  |  | Consequence | Likelihood | Level Of Risk |  |  |  | RISK REVIEW DATE
4.1 | Lift FBE pipe from trucks and place in pipe stockpile with Vac Lift or end hooks Lift FBE pipe onto pipe trailers with Vac Lift or end hooks. | 1. Dropped pipe (vac lift) | Crush Injury, Damage to Pipe , Damage to Property/Equipment | 1. Exclusion zones to be established and adhered to. Vac lift inspection program, regular servicing. VOC's operator 2. End hooks to be tested and tagged and right inserts for pipe size to be used 3. Use of slings permitted , but must be rated and tested and tagged and inspected prior to use | Induction, Prestart, Toolboxes, JSA, Lift Plan, VAC lift Inspection Form, PTW, VOC, TMP | D | 4 | L | [7 empty] | Low
|  | 2. Personnel being crushed by falling pipe. | Fatality, Injury | 2. Binders to be removed with personnel clear of area not involved in removal – warning of heads up prior to release. Exclusion Zone established |  | A | 5 | M
4.2 | Induction bends (hot bends on pallets - oversized) | 1. Incorrect lifting equipment - dropped pipe. | Damage to Pipe | 1. Suitable material handling plant on site i.e. telescopic handler to safely load palleted bends. Bends shall be strapped to pallets. | Induction, Prestart, Toolboxes, JSA, Lift Plan, PTW, VOC, TMP | D | 4 | L
|  | 2. Loaded poorly onto trailer/truck tray. | Damage to Pipe , Damage to Property/Equipment, Vehicle Incident | 2. approriate load restraints used and compentent person installing them |  | D | 4 | L
4.3 | Load restraint and tie-down (line pipe) | 1. Inadequate load restraint method | Lost Time Injury | 1. Load restraint plan (engineered). Tie-downs in serviceable condition. Supervisor and Safety Team inspections. | Induction, Prestart, Toolboxes, JSA, Lift Plan, PTW, VOC | D | 4 | L | [7 empty] | Low
|  | 2. Working at heights when unloading pipe from trailer | Fatality, Permanent Disability, Injury | 2. Mobile platform on site. No access to loaded pipe trailer by personnel. |  | A | 5 | M
4.4 | Transport of pipe to site | 1. Transport incident (collision, etc.) | Fatality, Collision, Damage to Property/Equipment, Impact on Third Party Relationship, Vehicle Incident | 1. Transport Management Plan and Traffic Management Plan. Site specific rules apply. 2. Licenced drivers and experienced 3. Use only designated access points and existing pipeline cross-over points | Induction, Prestart, Toolboxes, JSA, Lift Plan, PTW, VOC, TMP Nacap Traffic Management (Construction in Public Thoroughfares) 3904-OPS-017-3 Nacap Safety Essential #10 Worksite Traffic Safety Essential #6 Lifting Equipment | A | 5 | M
|  | 2. Inadequate load restraint | Damage to Pipe , Damage to Property/Equipment, Vehicle Incident | 2. Load restraint plan including mandatory fitting of suitable headache racks |  | D | 4 | L
|  | 3. Travelling through built up areas. | Fatality, Damage to Property/Equipment, Impact on Third Party Relationship, Vehicle Incident | 3. Transport Management Plan and use of designated roads only. |  | A | 5 | M
4.5 | Set up skids and sawdust bags ahead of pipe delivery | 1. Manual handling injury when setting up skids. | Lost Time Injury, Hand Injury | 1. Correct lifting technique – knees bent back straight, no twisting and load close to body. PPE | Induction, Prestart, Toolboxes, JSA, PTW, TMP | D | 3 | M
|  | 2. Snake, spider bite when moving skids and sand bags. | First Aid Injury | 2. PPE and where required a Fauna handler to be engaged to remove any wildlife. Accreditation and licensed |  | E | 4 | L
|  | 3. Uneven or wet ground conditions – slips and trips. | First Aid Injury | 3. Inspect ground conditions, remove any obstacle and wear appropriate footwear for the conditions. Housekeeping |  | E | 4 | L
|  | 4. Cuts and crushing when lifting moving skids. | First Aid Injury, Crush Injury | 4. Gloves to be worn. Keep hands clear of crush points, ensure all points are identified prior to placing skids down |  | E | 3 | L
4.6 | Remove load binders from top layer. | 1. Unauthorised personnel in work area. | Fatality, Permanent Disability | 1. Exclusion zones to be assessed and implemented to prevent unauthorised personnel entry. | Induction, Prestart, Toolboxes, JSA, PTW, TMP | A | 5 | M
|  | 2. Truck moving creating unstable load. | Damage to Pipe , Damage to Property/Equipment | 2. Binders to be removed from ground level. Truck to be parked with brakes applied and engine off. |  | C | 5 | L
|  | 3. Personnel being crushed by falling pipe. | Fatality | 3. Binders to be removed with personnel clear of area not involved in removal – warning of heads up prior to release. |  | A | 5 | M
|  | 4. Fall from height when on back of truck. | Fatality | 4. No personnel to climb on back of truck. (There is no reason for this to occur.) |  | D | 4 | L
4.7 | Use slings (pre-slung) to lift pipe and place onto skids / bags at least 100mm clear of the ground. | 1. Personnel injured by dropped or moving pipe. | Fatality, Lost Time Injury, Crush Injury, Damage to Pipe , Project Stopped | 1. Only qualified and VOC personnel to operate plant, Daily prestart check on all plant and equipment. Drop and roll exclusion zones to be identified and applied. Safety Walk, Hard Hats PPE required by JSA/SWMS. | Induction, Prestart, Toolboxes, JSA, Lift Plan, PTW, VOC, TMP | C | 4 | M | [7 empty] | Low
|  | 2. Pipe roll off truck. | Damage to Pipe , Damage to Property/Equipment | 2. Simple Lift Plan to be completed prior to lift. Scalloped Bolsters to be used. |  | D | 4 | L | [7 empty] | Low
|  | 3. Contact with overhead power lines when lifting pipes. | Fatality, Project Stopped | 3. Spotter to be in place at all time when lifting pipes., Pipe to be secured correctly before lifting. |  | A | 5 | M | [7 empty] | Low
|  | 4. Other vehicles driving through work area. Unauthorised personnel in lift area. | Damage to Pipe , Damage to Property/Equipment, Vehicle Incident | 4. Exclusion zones implemented and maintained. Traffic Management Plan implemented and work area deliniated |  | D | 4 | L | [7 empty] | Low
|  | 5. Truck moving without notice. | Damage to Property/Equipment, Vehicle Incident | 5. Vehicles stopped and in park when lift is in progress by designated crew member, Truck driver to remain in cab and only move truck when communicated – two toots of horn. |  | D | 4 | L | [7 empty] | Low
|  | 6. Bolsters falling off truck. | Damage to Pipe , Damage to Property/Equipment | 6. Bolsters to be removed once layer is strung before truck moves off. Use conduit or hooks. |  | E | 4 | L | [7 empty] | Low
|  | 7. Centreline incorrectly marked causing incorrect pipe lift (e.g. pipe falling). | Damage to Pipe , Damage to Property/Equipment | 7. Centre line to be clearly marked on pipe to ensure pipe is picked up at the right point. |  | D | 4 | L | [7 empty] | Low
4.8 | Turning pipe to appropriate clock position. | 1. Unauthorised personnel in lift area. Pipe falling | Fatality | 1. Exclusion zone to be assessed and maintained for all personnel during lift. | Induction, Prestart, Toolboxes, JSA, Lift Plan, PTW, VOC, TMP | A | 5 | M
|  | 2. Crushing between two pipes. Personnel walking with raised suspended load. | Permanent Disability, Crush Injury, Project Stopped | 2. No personnel to touch pipe until below waste height and suspended approx. 100mm above skids. – Hand placed on top of pipe only guide onto skids. |  | B | 5 | M
|  | 3. Pipe rolls of Sawdust Bags/Skids. | Permanent Disability, Crush Injury, Damage to Pipe , Damage to Property/Equipment | 3. No walking between pipes until rested securely on Sawdust bags/Skids. |  | B | 4 | M
|  | 4. Injury to personnel whilst turning pipe. | Medical Treatment Injury | 4. Use the correct tool for task (Turning bar). |  | D | 4 | L
4.9 | Truck and Excavator / Crane move forward to next location. | 1. Collision with personnel. | Fatality | 1. Truck does not move forward until plant operator signal with two toots of horn and check for area is clear. | Induction, Prestart, Toolboxes, JSA, Lift Plan, PTW, VOC, TMP | A | 5 | M
|  | 2. Pipe rolling off truck. | Damage to Pipe , Damage to Property/Equipment | 2. Exclusion zone in front and side of truck when moving, Truck moves forward at no more than 10km/h. |  | D | 5 | L
4.1 | Remove pipe rope rings & End Caps | 1. Cuts from cutting tool. | First Aid Injury | 1. Snips only to be used. (Correct Tool for Task as required). | JSA / SWMS | E | 3 | L | [7 empty] | Low
|  | 1. Hand Injury from End Cap Removal | First Aid Injury | 2. Tools to be used to safely remove end caps. Soft mallets to be used for re-installation (not to be installed by banging on with hands) | JSA / SWMS | E | 3 | L | [7 empty] | Low
4.11 | Induction Bends | 1. Awkward Load causing damage due to difficulty lifting. | Damage to Pipe , Damage to Property/Equipment | 1. Induction Bends to be transported using vehicle loading crane. Experienced VOC'd operator/driver. | Induction, Prestart, Toolboxes, JSA, Lift Plan, PTW, VOC, TMP | C | 5 | L
|  | 2. Lifting On/Off Vehicle. | Fatality, Crush Injury, Damage to Pipe , Damage to Property/Equipment, Production Delays | 2. JSA/SWMS, Lift Plan, VOC'd Rigger/Dogman, Certified lifting equipment |  | A | 5 | M
4.12 | Cold Bending Pipe - sling pipe, lift with Excavator / Crane and place in pipe bender. | 1. Worker struck by plant | Crush Injury | 1. crane fitted with reversing alarm, workers to maintain exclusion zone immediately in front of and at the rear of the crane. Operator to use dogman for directions. . | Induction, Prestart, Toolboxes, JSA, Lift Plan, PTW, VOC, TMP | B | 4 | M | [7 empty] | Low
|  | 2. Pinch hazards when slinging pipe. | Lost Time Injury | 2. Loads to be rigged by qualified dogman. Keep hands and fingers clear of pinch points – sling choke point, between pipe and skid. Crane hand signals used to communicate effectively. |  | D | 4 | L
|  | 3. Pipe rolls off skid, crush injuries. | Permanent Disability, Crush Injury, Damage to Pipe | 3. Workers to be observant of positioning of pipe on skids prior to slinging load. Keep clear of downhill side in case of pipe roll |  | B | 4 | M
|  | 4. Dropped load due to faulty lifting equipment. | Fatality, Damage to Pipe , Damage to Property/Equipment | 4. All lifting equipment thoroughly checked prior to use by dogman and operator respectively. No faulty equipment (slings etc.) permitted to be used. No worker to ever stand under a suspended load. Slings to be tagged (and in date) |  | A | 5 | M
|  | 5. Worker struck by pipe (load swing) or crushed between pipe and crane | Fatality, Permanent Disability, Damage to Property/Equipment | 5. Exclusion zone to be maintained between lifted pipe and crane (crush zone). Taglines to be used in cases where pipe swing is likely to occur i.e. working on slopes. Taglines also required when pipe is hoisted to a height above waist height of workers. |  | A | 5 | M
4.13 | Bend pipe. | 1. Crush / pinch injuries between pipe and bending machine. | Permanent Disability, Crush Injury | 1. Pinch and crush points signposted hazards on bender. VOC successfully completed by operator. Guarding where practical is fitted. Gloves must be worn. Controlled lift. | Induction, Prestart, Toolboxes, JSA, Lift Plan, PTW, VOC, TMP | B | 4 | M | [7 empty] | Low
|  | 2. Noise from machinery. | Permanent Disability | 2. Hearing protection mandatory. PHA noise assessment. |  | B | 4 | M
|  | 3. Hydraulic oil pressure injection injury, oil spill | Environmental Impact, Injection Injury, Spill | 3. Hose plates and covers installed to protect operator in case of hydraulic leak from hose or fittings. Spill kit on site. |  | D | 4 | L
4.14 | Extract pipe from pipe bender and move to skids. | 1. Rolling pipe and incorrect slinging (changed centre of gravity). | Crush Injury, Damage to Pipe , Damage to Property/Equipment | 1. Qualified Dogman to sling and control load. | Induction, Prestart, Toolboxes, JSA, Lift Plan, PTW, VOC, TMP | C | 4 | M | [7 empty] | Low
4.15 | Pull mounted gauge plates through bend | 1. Crush / pinch injuries between pipe and bending machine. | Permanent Disability, Crush Injury | 1. Check pipe prior to pulling out gauge plates,. PVC pipe to be used to flush out the pipe prior. Gloves to be worn at all times. Long sleeves to be rolled down at all times. | Induction, Prestart, Toolboxes, JSA, Lift Plan, PTW, VOC, TMP | B | 4 | M | [7 empty] | Low

## 5.0 Foreign Services Location
5.0 Foreign Services Location
IDENTIFY THE TASK or PROCEDURE, DESCRIBE THE HAZARDS AND RISKS, LIST THE CONSEQUENCES AND WHAT ARE THE EXISTING CONTROLS. | [6 empty] | EXISTING RISK |  |  | Recommendations | Responsibility | RISIDUAL RISK |  |  | STATUS | DATE Closed/Sign Off | TARGET LEVEL OF RISK |  | DATE RISK ADDED
ID | TASK or PROCEDURE What are the Job Steps | HAZARDS and RISKS What are they | CONSEQUENCES (relate to Objectives) Resulting in | EXISTING CONTROLS | Consultation Method | 3rd Party Liaison? | Consequence | Likelihood | Level Of Risk |  |  | Consequence | Likelihood | Level Of Risk |  |  |  | RISK REVIEW DATE
5.1 | Locate and pothole buried services. | 1. Equipment fault when using (cuts/cracks in hose) causing injury (splash back). | Medical Treatment Injury, Damage to Property/Equipment | 1. All equipment and tools to be thoroughly checked before use each day. Check hoses for cuts or cracks. Check fittings. Report faults to Supervisor. | Induction, Prestart, Toolboxes, JSA, PTW, VOC, TMP | Y | D | 4 | L | [7 empty] | Low
|  | 2. High pressure water – water injection injuries | Injection Injury | 2. Never make contact with skin. Appropriate PPE including gloves, double eye protection safety glasses, long trousers and long sleeved shirts to be worn. Plant Hazard Assessment (PHA) reviewed by operator. Esure lance is long enough to prevent operator from being in front of tip. |  |  | E | 4 | L
|  | 3. Struck by mud and debris (splash back), eye injury | First Aid Injury, Eye Injury | 3. Eye protection. Only required personnel to be in close proximity when pot holing. Double eye protection |  |  | E | 4 | L
|  | 4. Poor ergonomics (hard to reach trigger when starting to pothole new location). | Permanent Disability, First Aid Injury | 4. Task rotation. Use appropriate sized water spheres to ensure not over reaching. |  |  | E | 4 | L
|  | 5. Material blockages in suction pipe – manual handling due to equipment design and material. | First Aid Injury | 5. Team work. Seek help from crew member if required. appropriate cleaning mechanism for blockages |  |  | E | 4 | L
|  | 6. Noise – hearing loss. | Permanent Disability | 6. Hearing plugs or muffs to be worn. |  |  | B | 4 | M
|  | 7. Slip in hole created by potholing causing ankle injury. | Medical Treatment Injury | 7. Awareness of hole. Close hole up promptly do not leave exposed/open. Ensure ground is level and compacted prior to leaving area. |  |  | E | 4 | L
|  | 8. Damage to potholed service. | Damage to Asset, Damage to Reputation, Impact on Third Party Relationship | 8. Pressure regulated to be no higher than 2000psi. Suitably competent/VOC'ed operators |  |  | D | 4 | L
|  | 9. Cutting conduit (lacerations, eye injuries). | Medical Treatment Injury | 9. Use hacksaw where required to cut conduit. Gloves and safety glasses to be worn. |  |  | D | 4 | L
5.2 | Pot holing close to roads. | 1. Struck by vehicle. | Fatality, Vehicle Incident | 1. Traffic control to be in place prior to commencing work by roadside, including signage and spotter. Qualified and experienced traffic controllers. | Induction, Prestart, Toolboxes, JSA, PTW, VOC, TMP |  | A | 5 | M | [7 empty] | Low
5.3 | Emptying vac tank. | 1. Environmental impact i.e. soil degradation. | Environmental Impact, Erosion and Heavy Dust | 1. Ensure contents of vac tank are emptied in a location approved by Project Manager. Or disposed of in accordance with waste disposal regulations (CEMP) | Induction, Prestart, Toolboxes, JSA, PTW, VOC, TMP |  | E | 4 | L
|  | 2. Crush injury from tailgate of tank. | Permanent Disability, Crush Injury | 2. Spotter to be used when empting contents of tank and to ensure operator does not close tailgate when a person is cleaning the tank out. No personnel to enter tank. Emergency stop button. |  |  | D | 4 | L | [7 empty] | Low
3, Overhead powerlines - LFI
4. Falling objects from canopy
5. Burns/Radiation/Hot welding rods
6. Noxious fumes when welding
7. Moving plant from joint to joint
8. Fatigue from welding without rest breaks
9. Dust/dirt, grinding
10. Eye injury – Arc flash
11. Exposure to bad weather/lightning
Note on G3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is there a need to liaise with/notify client/public/other entities to implement a HIRAC process for any hazards impacting any of the parties?

## 6.0 General Civil Works
6.0 General Civil Works
IDENTIFY THE TASK or PROCEDURE, DESCRIBE THE HAZARDS AND RISKS, LIST THE CONSEQUENCES AND WHAT ARE THE EXISTING CONTROLS. | [6 empty] | EXISTING RISK |  |  | Recommendations | Responsibility | RISIDUAL RISK |  |  | STATUS | DATE Closed/Sign Off | TARGET LEVEL OF RISK |  | DATE RISK ADDED
ID | TASK or PROCEDURE What are the Job Steps | HAZARDS and RISKS What are they | CONSEQUENCES Resulting in | EXISTING CONTROLS | Consultation Method | 3rd Party Liaison? | Consequence | Likelihood | Level Of Risk |  |  | Consequence | Likelihood | Level Of Risk |  |  |  | RISK REVIEW DATE
6.1 | Site Assessment | 1. Wrong off set on pegs. | Environmental Impact, Loss of Production, Production Delays | 1. Check off set pegs and alignment sheets | CEMP,LECH Form 2 PTW, JSA, ITP Safety Essential #5 Safe Working with Electricty and #6 Foreign Services |  | C | 5 | L
|  | 2. Foreign services (overhead/underground) not identified. | Fatality, Damage to Asset, Damage to Property/Equipment | 2. Check Catenaries and signage is in place, DBYD, Check Foreign service markings and barricades are in place. Spotter where required when working near overhead power lines. Ensure you have relevant PTW and Form 2 for the work area. Third Party Permits in place as required. |  |  | A | 5 | M
|  | 3. Spills, burst hose, leaks. | Environmental Impact, Spill | 3. Spill kits to be available for all machines. |  |  | E | 3 | L
|  | 4. Heat/Cold Stress. | First Aid Injury | 4. Hard hats with brims, Jackets, Vests and Beanie's and sunscreen provide, rest in cool locations, air conditioned vehicles (Heating and Cooling), Water bottles 5L and 20L for crews, regular breaks. Inductions |  |  | E | 3 | L
6.2 | Rock handling and Materials Handling | 1. Manual handling and hand crush / abrasion injuries from lifting and moving rocks. | Medical Treatment Injury, Crush Injury | 1. Consult with OHS Advisor to complete ergonomic assessment. Adopt safe lifting techniques including straight back, team work. Position rocks as safe as possible to worksite to reduce carry distance. Take rest breaks as needed. Cut proof rated gloves must be worn. Be aware of pinch and crush points i.e. between rocks. Pneumatic, machine compaction. | Induction, Prestart, JSA, Traffic Management Plan, [Safety Essentials] |  | D | 4 | L
|  | 2. Crush injuries from rolling rocks. | Crush Injury, Damage to Property/Equipment | 2. Work as a team. Communicate hazards with each other. |  |  | D | 4 | L
|  | 3. Trips and slips. | First Aid Injury | 3. Maintain safe housekeeping by removing trips hazards where practicable and remove any excess rocks. Lace up safety boots mandatory. |  |  | E | 4 | L
6.3 | Asphalting | 1. Contact with bitumen based product | Medical Treatment Injury, Burns to skin, Lost Time Injury | 1. eliminate skin contact - gloves, long sleeves, trousers etc (as per SDS) 2. Use shovels | Induction, Prestart, JSA, Traffic Management Plan, Site Security Plan |  | C | 5 | L
|  | 2. Burns from laying asphalt | Medical Treatment Injury, First Aid Injury | 3. PPE |  |  | D | 4 | L
|  | 3. Fumes from laying asphalt | First Aid Injury, Medical Treatment Injury, First Aid Injury | 4. Ensure product is at correct temperature to prevent excessive fuming |  |  | E | 4 | L
|  | 4. Use of wacker/jumping jack in close proximtry to kerbing or drop-off | First Aid Injury, Medical Treatment Injury, First Aid Injury | 5. competent operators, Maintain safe distance from edge of drop off (assess and communicate distance during toolbox and site risk assessment meeting) |  |  | E | 4 | L
3, Overhead powerlines - LFI
4. Falling objects from canopy
5. Burns/Radiation/Hot welding rods
6. Noxious fumes when welding
7. Moving plant from joint to joint
8. Fatigue from welding without rest breaks
9. Dust/dirt, grinding
10. Eye injury – Arc flash
11. Exposure to bad weather/lightning
Note on G3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is there a need to liaise with/notify client/public/other entities to implement a HIRAC process for any hazards impacting any of the parties?

## 7.0 Piling (Subcontractor) (hidden)
7.0 Piling (Subcontractor)
IDENTIFY THE TASK or PROCEDURE, DESCRIBE THE HAZARDS AND RISKS, LIST THE CONSEQUENCES AND WHAT ARE THE EXISTING CONTROLS. | [5 empty] | EXISTING RISK |  |  | Recommendations | Responsibility | RISIDUAL RISK |  |  | STATUS | DATE Closed
ID | TASK or PROCEDURE What are the Job Steps | HAZARDS and RISKS What are they | CONSEQUENCES Resulting in | EXISTING CONTROLS | Consultation Method | Consequence | Likelihood | Level Of Risk |  |  | Consequence | Likelihood | Level Of Risk
7.1 | Piling | 1. Falls, including when inspecting or maintaining piling rigs and falls into pile holes or excavations | Permanent Disability, Crush Injury, Damage to Property/Equipment, Lack of Attention - Error | 1. Excavation barricaded off. Ensure spotter is present and aware of surroundings | JSA, SDS Prestart Checklists, VOC, PHA, Prestarts, Toolboxes. | D | 4 | L
|  | 2. Being struck by powered mobile plant, including working in close proximately to Piling rig and delivery vehicles | Permanent Disability, Crush Injury, Damage to Property/Equipment, Lack of Attention - Error | 2. Isolating persons from the hazard - exclusion zone in place Specific safety training in piling activities, inductions work instructions displayed warning signs, PPE Only qualified , VOC’d and supervisor approved operators to inspect and operate any machines. |  | D | 4 | L
|  | 3. Contact with utilities services (eg overhead powerlines and underground cables or pipes | Fatality, Damage to Asset, Damage to Reputation, Project Stopped | 3. Spotter to be in place at all time when lifting pipes. Piles to be secured correctly before lifting. Foreign Service(s) to located and marked prior to commencement (refer to 5.0 Foreign Service Location) |  | A | 5 | M | 3rd party asset owners permit requirements to be fullfilled at all times | Nacap
|  | 4. Entanglement in the rotating parts of the piling rig | Fatality, Permanent Disability, Medical Treatment Injury | 4. PHA to be read by operator and signed - check all guards are in place. Competent operator to conduct checks. LOTO and report unsuitable equipment. PPE |  | A | 5 | M
|  | 5. Crushing when moving materials, including when unloading piles from trucks and stacking them onsite | Permanent Disability, Crush Injury, Damage to Property/Equipment | 5. Qualified rigger / dogman to conduct lifting. Exclusion zone setup whilst lifting is being carried out |  | E | 3 | L
|  | 6. Falling loads due to use of inappropriate lifting gear | Permanent Disability, Crush Injury, Damage to Property/Equipment | 6. Qualified rigger / dogman to conduct lifting and check all rigging Exclusion zone setup whilst lifting is being carried out |  | E | 3 | L
|  | 7.Vibration & Noise causing hearing loss | Community Complaints, Damage to Asset | 7. Community notified, where impacts may occur from piling activities. 3rd party asset owners notified of activities in proximity of assets |  | E | 3 | L
|  | 8.Overturning Plant / Plant Stability | Fatality, Damage to Property/Equipment, Damage to Reputation | 8. Piling platform to be inspected and signed off. Inspect site for damage to piling platform prior to rig mobilisation. Only qualified , VOC’d and supervisor approved operators to inspect and operate any machines. |  | B | 4 | M
|  | 9. High Energy - driven piles (large hammer) | Fatality, Crush Injury, Damage to Property/Equipment | 9. Exclusion zone setup. Experienced operator to operate machine and monitor surroundings for changes |  | A | 5 | M
|  | 3, Overhead powerlines - LFI |  | 1. Earth stake to be maintained when working under overhead high voltage powerlines until pipe is tied in.
4. Falling objects from canopy
5. Burns/Radiation/Hot welding rods
6. Noxious fumes when welding
7. Moving plant from joint to joint
8. Fatigue from welding without rest breaks
9. Dust/dirt, grinding
10. Eye injury – Arc flash
11. Exposure to bad weather/lightning

## 8.0 Pile Caps & Pre-Cast Concre (hidden)
8.0 Pile Caps & Pre-Cast Concre
IDENTIFY THE TASK or PROCEDURE, DESCRIBE THE HAZARDS AND RISKS, LIST THE CONSEQUENCES AND WHAT ARE THE EXISTING CONTROLS. | [5 empty] | EXISTING RISK |  |  | Recommendations | Responsibility | RISIDUAL RISK |  |  | STATUS | DATE Closed | TARGET LEVEL OF RISK |  | DATE RISK ADDED
ID | TASK or PROCEDURE What are the Job Steps | HAZARDS and RISKS What are they | CONSEQUENCES Resulting in | EXISTING CONTROLS | Consultation Method | Consequence | Likelihood | Level Of Risk |  |  | Consequence | Likelihood | Level Of Risk |  |  |  | RISK REVIEW DATE
8.1 | Use swift lifts to lift pre-cast concrete from truck with excavator / crane | 1. Personnel injured by dropped object. | Lost Time Injury, Crush Injury, Damage to Property/Equipment, Project Stopped | 1. Only qualified and VOC personnel to operate plant, Daily prestart check on all plant and equipment. Exclusion zones to be identified and applied. Safety Walk, Hard Hats PPE required by JSA. | Induction, JSA, VOC, Prestarts, Toolboxes | B | 4 | M | [7 empty] | Low
|  | 2. Object dropped off truck. | Damage to Property/Equipment | 2. Simple Lift Plan to be completed prior to lift. |  | D | 4 | L | [7 empty] | Low
|  | 3. Contact with overhead power lines. | Fatality, Project Stopped | 3. Dogman to be conducting lift at all times. Rigging attached (swift lift/s) to be secured correctly before lifting. |  | A | 5 | M | [7 empty] | Low
|  | 4. Other vehicles driving through work area. Unauthorised personnel in lift area. | Damage to Property/Equipment, Vehicle Incident | 4. Exclusion zones implemented and maintained. Traffic management |  | D | 4 | L | [7 empty] | Low
|  | 5. Truck moving without notice. | Damage to Property/Equipment, Vehicle Incident | 5. Vehicles stopped and in park when lift is in progress by designated crew member, Truck driver to remain in cab and only move truck when communicated |  | D | 4 | L | [7 empty] | Low
|  | 6. Load incorrectly balanced. | Collision, Crush Injury, Damage to Asset, Damage to Property/Equipment | 6. load centre and swift lifts to be clearly identified to ensure pre-cast is picked up at the right point- correct lifting points |  | D | 4 | L | [7 empty] | Low
8.2 | Placing Pre-casts on prepared platform. | 1. Manual handling cuts from concrete | First Aid Injury | 1. Gloves, correct lifting technique. – knees bent back straight, close to body | JSA, Lift Plans, VOC, PHA, Prestarts, Toolboxes, Inductions | D | 4 | L
|  | 2. Uncontrolled load (load not secure in sling). | Crush Injury, Damage to Property/Equipment | 2. Tag lines to be used and controlled by Dogman, Dogman to sling load. |  | C | 4 | M
|  | 3. Working near a suspended load | Fatality | 3. Exclusion zones maintained. No walking under a suspended load. |  | A | 5 | M
|  | 4. Pinch points (hands/fingers caught when moving load) | Medical Treatment Injury | 4. Loads to be rigged by qualified dogman. Keep hands and fingers clear of pinch points. Crane / Excavator hand signals used to communicate effectively |  | D | 4 | L
8.3 | Formwork and concreting. | 1. Uneven surfaces and exposed Reo bar causing injury to legs. | First Aid Injury | 1. Trained and experienced crew engaged Mandatory PPE requirements Communication with other trades and barricading where required. Housekeeping maintained. Spotter engaged as required (no person to stand behind reversing vehicle) Hold down bolts, exposed reo to be capped and monitored Agi truck fitted with reversing alarm / flashing beacon and spotter No Agi washout on site | JSA, Lift Plans, VOC, PHA, Prestarts, Toolboxes, Inductions | D | 4 | L
|  | 2. Personnel in close proximity to Agi Truck movements | Fatality, Crush Injury, Damage to Property/Equipment |  |  | C | 4 | M
|  | 3. Chemical exposure to concrete and products | Burns to skin |  |  | D | 4 | L
|  | 3, Overhead powerlines - LFI |  | 1. Earth stake to be maintained when working under overhead high voltage powerlines until pipe is tied in.
4. Falling objects from canopy
5. Burns/Radiation/Hot welding rods
6. Noxious fumes when welding
7. Moving plant from joint to joint
8. Fatigue from welding without rest breaks
9. Dust/dirt, grinding
10. Eye injury – Arc flash
11. Exposure to bad weather/lightning

## 9.0 Strutural Steel (inc.Scaff) (hidden)
9.0 Strutural Steel (inc.Scaff)
IDENTIFY THE TASK or PROCEDURE, DESCRIBE THE HAZARDS AND RISKS, LIST THE CONSEQUENCES AND WHAT ARE THE EXISTING CONTROLS. | [5 empty] | EXISTING RISK |  |  | Recommendations | Responsibility | RISIDUAL RISK |  |  | STATUS | DATE Closed | TARGET LEVEL OF RISK |  | DATE RISK ADDED
ID | TASK or PROCEDURE What are the Job Steps | HAZARDS and RISKS What are they | CONSEQUENCES Resulting in | EXISTING CONTROLS | Consultation Method | Consequence | Likelihood | Level Of Risk |  |  | Consequence | Likelihood | Level Of Risk |  |  |  | RISK REVIEW DATE
9.1 | Workers moving around site | 1. Slips, trips, fall resulting injury from walking on wet, uneven and different levels | Medical Treatment Injury | 1. Avoid wet areas: always use pathways, walkways, scaffold platform and stairs; do not take shortcuts when walking on the site or work area; always use handrails when accessing stairs (maintain 3 points of contact), be observant – watch out for protruding obstacles; remove excess building materials from build/work area. Correct footwear selection for works. | JSA, SDS Prestart Checklists, VOC, PHA, Prestarts, Toolboxes. | D | 4 | L
|  | 2. Collision with plant may injure workers | First Aid Injury, Crush Injury, Damage to Property/Equipment | 2. Ensure plant flashing light and reverse beeper are operating Workers not to walk behind operating plant. Where possible a barrier shall be erected to maintain separation of machine and personnel - designated walkways |  | E | 4 | L
9.2 | Working at heights | 1. A fall while installing or dismantling scaffolding may injure workers | Medical Treatment Injury | 1. Planks installed to each lift as scaffold is built to avoid working from transoms and ledgers Use ladder or stair to access scaffold where practical Scaffold constructed by licensed scaffolders or under the supervision of licensed scaffolders. 100% tie off is required whilst building scaffold (even if building internally in stages - 100% tied off) | JSA, SDS Prestart Checklists, VOC, PHA, Prestarts, Toolboxes. | D | 4 | L
|  | 2. A fall from incomplete scaffold may injure any person or workers on site | First Aid Injury, Crush Injury, Damage to Property/Equipment | 2. Warning sign(s) and/or remove access ladders and/or provide guard rails to stop access to incomplete areas Scaffolding to be rated correctly for works scope |  | E | 4 | L
|  | 3. A fall from completed scaffold may injure any person on site | Fatality, Lost Time Injury, Crush Injury | 3. Scaffold constructed by licensed scaffolders. Scaffold to have handrails, ladder or stair access and to comply with standards scaff tag and scaff plan. Use of access stairs as preference over ladder use Scaffolding to be rated correctly for works scope |  | C | 4 | M
|  | 4. Any object falling from height could injure people below | Permanent Disability, Lost Time Injury, Crush Injury, Damage to Asset, Damage to Property/Equipment | 4. Workers are prevented from working below other workers Scaffold worker to use scaffold belts to keep tools secure on their person. Lanyards to be fitted to all handtools Toe boards and kick boards to be provided to each working platform Platforms to be kept free from excessive clutter of tools or scaffolding components. |  | C | 4 | M
|  | 5. Failure of a scaffold component could injure any person on site | First Aid Injury, Crush Injury, Damage to Property/Equipment | 5. Scaffold components are checked for defects before dispatch, at installation and during dismantling by qualified and licenced person. |  | E | 4 | L
9.3 | Ties to Structure | 1. Electrocution from use of power tools | Medical Treatment Injury | 1. Check power leads are tagged with test tag with current date Check power leads to ensure they are not cut, frayed or otherwise damaged. Checking of power tool to ensure all guards and body is in servicable condition. Users must be trained in the safe use of the power tool as recommended by the manufacturer. | JSA, SDS Prestart Checklists, VOC, PHA, Prestarts, Toolboxes. | D | 4 | L
|  | 2. Incorrect placement of tie | First Aid Injury, Crush Injury, Damage to Property/Equipment | 2. Scaffolding plan in place and not modified without correct approvals and by licenced person Tie frequency is in accordance with regulations and standards Tie is fixed to a structural element that can withstand the loads applied by the scaffold. Tie design is suitable for the application - refer to scaffolding plan |  | E | 4 | L
9.4 | Working on Completed Scaffolding | 1. Unauthorised alterations causing collapse of structure | Permanent Disability, Medical Treatment Injury | 1. No alterations are permitted to scaffold or scaffold ties. No fixing of electrical leads or cables to scaffold. No tying of tarps or similar objects that may interfere with stability of scaffold. Installation of gates preferable over drop bars | JSA, SDS Prestart Checklists, VOC, PHA, Prestarts, Toolboxes. | D | 4 | L
|  | 2. Overloading of scaffold causing collapse | First Aid Injury, Crush Injury, Damage to Property/Equipment | 2. All material loaded onto scaffold must be in strict accordance with load capacities indicated on Scafftag, manufacturers recommendations and relevant sections AS/NZS 4576 and 1576. |  | E | 4 | L
9.5 | Crane Lifts | 1. Material falling causing injury or damage to plant and equipment | Fatality, Medical Treatment Injury | 1. Instruction given by dogman during crane movements All lifting equipment is to be tagged and/ or up to date inspections carried out. Exclusion zone established. Lift plan identifying lifting requirement and exclusion zones. | JSA, SDS Prestart Checklists, VOC, PHA, Prestarts, Toolboxes. | A | 5 | M
9.6 | Endangering terminal workers using shared area | 1. Terminal workers not using designated crossing access paths causing collision / injury. | Permanent Disability, Medical Treatment Injury | 1. Segregation control measures implemented and shall include but not limited to: Defined path with separation barriers and traffic control Safety fence / barrier Warning signs, cones / bollards Spotter/s providing verbal warning | JSA, SDS Prestart Checklists, VOC, PHA, Prestarts, Toolboxes. | D | 4 | L
9.7 | Installation of Structural Steel | 1. Inexperienced / unqualified persons engaged causing injury | Lost Time Injury, Medical Treatment Injury, Collision, Crush Injury, Damage to Asset, Damage to Property/Equipment | Trained and competent personnel engaged. Only qualified crane drivers to operate cranes and qualified riggers to select and apply rigging and direct crane driver All plant to be inspected on daily basis and records kept Maintenance to be carried out in accordance with manufactures guidelines . SWL not exceeded Spotters engaged as required Tool selection appropriate for tasks | JSA, SDS Prestart Checklists, VOC, PHA, Prestarts, Toolboxes. | D | 4 | L
|  | 2. Incorrect procedures used or procedures not followed causing injury | Lost Time Injury, Medical Treatment Injury, Collision, Crush Injury, Damage to Asset, Damage to Property/Equipment |  |  | D | 4 | L
|  | 3. Use of Defective, Incorrect tools causing injury | Lost Time Injury, Medical Treatment Injury, Collision, Crush Injury |  |  | E | 4 | L
9.8 | Operating Elevated Work Platform (EWP) | 1. Inexperienced / unqualified persons engaged causing injury | Lost Time Injury, Medical Treatment Injury, Collision, Crush Injury, Damage to Asset, Damage to Property/Equipment | 1. Trained and appropriately qualified personnel engaged. Only qualified person to operate, VOC'd Full Body Fall Arrest Harness and Lanyard required exclusion zones established Rescue Plan Spotter engaged at all time when EWP in use | JSA, SDS Prestart Checklists, VOC, PHA, Prestarts, Toolboxes. | A | 5 | M
|  | 2. Contact with Overhead Services | Fatality, Project Stopped | 3. Qualified spotter engaged when working around overhead services. |  | A | 5 | M
|  | 3, Overhead powerlines - LFI |  | 1. Earth stake to be maintained when working under overhead high voltage powerlines until pipe is tied in.
4. Falling objects from canopy
5. Burns/Radiation/Hot welding rods
6. Noxious fumes when welding
7. Moving plant from joint to joint
8. Fatigue from welding without rest breaks
9. Dust/dirt, grinding
10. Eye injury – Arc flash
11. Exposure to bad weather/lightning

## 7.0 Welding
7.0 Welding
IDENTIFY THE TASK or PROCEDURE, DESCRIBE THE HAZARDS AND RISKS, LIST THE CONSEQUENCES AND WHAT ARE THE EXISTING CONTROLS. | [5 empty] | EXISTING RISKS |  |  | Recommendations | Responsibility | RISIDUAL RISK |  |  | STATUS | DATE Closed | TARGET LEVEL OF RISK |  | DATE RISK ADDED
ID | TASK or PROCEDURE What are the Job Steps | HAZARDS and RISKS What are they | CONSEQUENCES (relate to Objectives) Resulting in | EXISTING CONTROLS | Consultation Method | Consequence | Likelihood | Level Of Risk |  |  | Consequence | Likelihood | Level Of Risk |  |  |  | RISK REVIEW DATE
7.1 | Pre buffing of pipe and scribe line Creating sufficient cutback for external clamp | 1. Eye injury from sparks | Eye Injury | 1. Double eye protection. Brush down prior to removal of glasses. Do not apply sunscreen to above the eyes | SWMS, SDS, Prestarts, Toolboxes, Inductions | E | 4 | L | [7 empty] | Low
|  | 2. Iron oxide dust from buffing pipe | Health Effects, Respiratory Issues | 2. Respiratory mask to be worn and changed regularly where deemed necessary |  | E | 4 | L
|  | 3. Manual handling injuries from repetitive work, vibration and being in awkward positions | First Aid Injury | 3. Worker rotation 4. Stretch and change position often |  | E | 4 | L
|  | 4. Snakes / insect bites | Lost Time Injury, Medical Treatment Injury | 5. Check bags or under pipe for wildlife. First aid kits on hand. First aid within crew |  | D | 4 | L
|  | 6. Changing buffing wheel without properly disconnecting from power supply | Lost Time Injury, Medical Treatment Injury | 6. Ensure buffer is correctly attached and rated for job - disconnect power supply, using RCD protected circuit. |  | C | 4 | M
|  | 7. Lone worker, at times no visual contact | First Aid Injury, Dehydration, Health Effects, Heat Stress/Stroke | 7. Hand held radios on person. Supervisor to check worker regularly |  | D | 4 | L
|  | 8. Hand injuries from sharp edges | First Aid Injury | 8. Good glove selection |  | A | 5 | M
|  | 9. Clothing caught on buffer causing entanglement | Medical Treatment Injury, Damage to Property/Equipment | 9. No loose clothing. Stop buffer completely before putting down |  | D | 4 | L
|  | 9. Clothing caught on buffer causing entanglement | Medical Treatment Injury, Damage to Property/Equipment | 9. No loose clothing. Stop buffer completely before putting down |  | D | 4 | L
7.2 | Pre Heat | 1. Burns from gas torch | Medical Treatment Injury, Burns to skin | 1. Appropriate glove choice, exclusion zone | SWMS, Prestart Checklists, VOC, PHA, Prestarts, Toolboxes, Inductions, Nacap PTW Procedure 3904-OPS-018-3 | D | 4 | L | [7 empty] | Low
|  | 2. Gas leak/burst hose | Medical Treatment Injury, Damage to Property/Equipment, Fire | 2. Pre check of equipment, hose check, Use flint lighter no open flame |  | D | 4 | L
|  | 3. Heat blast from gas torch | Medical Treatment Injury, Burns to skin | 3. Face shield and hood protection Turn off before placing torch down Non essential personnel to be excluded from work area |  | D | 4 | L
|  | 4. Fires from gas torch | Fire | 4. Quality housekeeping Fire extinguisher permits to use open flame - MFB permits |  | D | 4 | L
|  | 5. Hose tangle and hook up causing tripping injury | Damage to Property/Equipment | 5. Untangle hose prior to use from around bottle. Remove all kinks from hose |  | E | 4 | L
7.3 | Sling pipe | 1. Faulty sling casing dropped pipe - incorrect lifting gear | Crush Injury, Damage to Pipe , Damage to Property/Equipment | 1. Correct slings for task, Check testing date and weight rating for load, Ensure slings are hole free, no tear, VOC dogman to sling | SWMS, Lift Plans, Prestart Checklists, VOC, PHA, Prestarts, Toolboxes, Inductions Nacap Essential # 6 Lifting Equipment | C | 4 | M | [7 empty] | Low
|  | 2. Pipe falls off skids (not slung correctly) causing property damage and personnel injury | Medical Treatment Injury, Damage to Pipe , Damage to Property/Equipment | 2. Centre line markings, quality skids and sawdust bags utilised, observation in advance |  | D | 4 | L
|  | 3. Slips/ Trips from uneven ground | First Aid Injury | 3. Housekeeping and be observant “look first”. Lace up safety boots mandatory to help avoid ankle injuries |  | E | 4 | L
|  | 4. Crush/pinch Injury to hands when placing pipe | Medical Treatment Injury, Crush Injury | 4. Clear communication established between dogman and crane operator when lifting pipe. Exclusion zone established |  | D | 4 | L
|  | 5. Interaction with lifting equipment | Lost Time Injury, Damage to Pipe , Damage to Property/Equipment | 5. Awareness of other traffic and personnel and surrounds. Exclusion zone established defined zones - Plant and load swing arc |  | C | 4 | M
7.4 | Excavator / Crane lift pipe | 1. Suspended load falling causing damage/injury | Crush Injury, Damage to Pipe | 1. No person under suspended pipe | SWMS, Prestart Checklists, VOC, PHA, Prestarts, Toolboxes, Nacap Safety Essential #5 Mobile Crane, Inductions | C | 4 | M
|  | 2. Moving plant causing crushing | Permanent Disability, Crush Injury | 2. Exclusion zone maintained |  | B | 4 | M
|  | 3. Hook striking workers | Fatality | 3. Hard hats worn, exclusion zones, operator/worker observation |  | A | 5 | M
|  | 4. Uneven ground causing falls | Damage to Pipe , Damage to Property/Equipment, Injury | 4. Be aware of and traverse berms carefully |  | D | 4 | L
|  | 5. Stored energy when lifting pipe | Damage to Pipe , Damage to Property/Equipment, Injury | 5. Correct placement of lifting hook, centreline marked |  | D | 4 | L
|  | 6. Mechanical failure causing loads to fall | Damage to Pipe , Damage to Property/Equipment, Injury | 6. Regular service and maintenance |  | D | 4 | L
|  | 7. Contact with overhead power lines | Fatality, Damage to Property/Equipment, Impact on Third Party Relationship, Project Stopped | 7. Ensure lines are identified with catenaries and signage, Have trained electrical spotter present when working under or near power lines. |  | A | 5 | M
7.5 | Stab on (above and below ground) | 1. Crush injury, Burns (hot pipe) | Medical Treatment Injury, Burns to skin, Crush Injury | 1. Correct glove selection, no hands on bevel, holding around girth of pipe away from crush points | SWMS, Prestart Checklists, VOC, PHA, Prestarts, Toolboxes, Inductions, Lift Plans | D | 4 | L | [7 empty] | Low
|  | 2. Uneven ground – unexpected pipe movement | Damage to Pipe , Damage to Property/Equipment, Injury | 2. Walk on graded areas, where possible |  | D | 4 | L
|  | 3. Clear line of sight (e.g. pipe causes injury from personnel being in the line of fire) | Medical Treatment Injury, Damage to Pipe , Damage to Property/Equipment | 3. Non-working personnel out of line of fire |  | D | 4 | L
|  | 4. Slips/Trips/Falls – skids on ground | First Aid Injury | 4. Good housekeeping with skids to be stacked |  | E | 4 | L
7.6 | Pipe spacing | 1. Hand injury/incorrect choice of tools, Burns (hot pipe) | Medical Treatment Injury, Burns to skin | 1. Copper hammer only to be used, Correct glove selection for hot works | SWMS, Prestart Checklists, VOC, PHA, Prestarts, Toolboxes, Inductions | D | 4 | L | [7 empty] | Low
|  | 2. Manual handling injuries from using clamp | Medical Treatment Injury | 2. Training on use of clamp and VOC’d, if internal clamp to be used. |  | D | 4 | L
|  | 3. Pinch points from moving pipe | Medical Treatment Injury | 3. Positive communication, Awareness, removal of unnecessary personnel from work location |  | D | 4 | L
7.7 | Skids | 1. Rotten and broken skids causing unexpected movement | First Aid Injury | 1. Reject rotten and broken skids, remove from service | SWMS, Prestarts, Toolboxes, Inductions | E | 4 | L | [7 empty] | Low
|  | 2. Splinters causing injury from handling skids | First Aid Injury | 2. Glove selection for task |  | E | 4 | L
|  | 3. Manual handling injuries including strains and hand Injuries from lifting skids | Medical Treatment Injury | 3. Don’t handle skids by ends, proper lifting technique |  | D | 4 | L
|  | 4. Pipe falling from unsecure stack formation | Crush Injury | 4. Crutch pipe for better support, Secure stack formation and placement |  | C | 4 | M
|  | 5. Snakes/insect bites | Medical Treatment Injury | 5. Check skids before handling glove selection |  | D | 4 | L
7.8 | Lower Pipe | 1. Body parts crushed (hand under pipe and between skids) from poor lowering technique | Crush Injury | 1. No hand, body part under pipe and between skids, control pipe by girth |  | C | 4 | M
|  | 2. Stored energy causing pipe to move unexpectedly | Damage to Pipe , Damage to Property/Equipment, Injury | 2. Don’t lift pipe until directed by stabber |  | D | 4 | L
|  | 3. Pipe falling off skids due to unsecure stack formation | Crush Injury, Damage to Pipe , Damage to Property/Equipment | 3. Skids set at correct height, crutching of pipes |  | D | 4 | L
7.9 | Welding and capping | 1. Electrocution from touching electrified pipe | Fatality | 1. Equipment checks for leads and earth clamp. Test and Tag, welding machines fitted with RCD. VRD (Voltage Reduction Device) must be used | SWMS, SDS, Prestart Checklists, VOC, PHA, Prestarts, Toolboxes, Inductions, PTW Safety Essentials #3 Mobile Plant, #9 Foreign Services, #6 Lifting Equipment | A | 5 | M | [7 empty] | Low
|  | 2. Fire from weld sparks | Fire | 2. Fire extinguishers and ensure firefighting gear is in working order, canopy provides spark protection vegetation cleared in work area (ie. topsoil stripped) |  | D | 4 | L
|  | 3, Overhead powerlines - LFI | Lost Time Injury | 1. Earth stake to be maintained when working under overhead high voltage powerlines until pipe is tied in. |  | B | 4 | M
|  | 4. Falling objects from canopy | Crush Injury, Damage to Pipe , Damage to Property/Equipment | 3. Secure objects above head and to side of canopy |  | C | 4 | M
|  | 5. Burns/Radiation/Hot welding rods | Medical Treatment Injury | 4. Correct gloves and protective gear for job, metal buckets for rod stumps, stay clear of arc of radiation. |  | D | 4 | L
|  | 6. Noxious fumes when welding | Medical Treatment Injury, Allergic Reaction, Exposure, Respiratory Issues | 5. Use of breathing apparatus – Adflow and respired air, Extractor fan working if canopy down |  | D | 4 | L
|  | 7. Moving plant from joint to joint | Fatality, Damage to Pipe , Damage to Property/Equipment | 6. Communication with workers and awareness of surroundings |  | A | 5 | M
|  | 8. Fatigue from welding without rest breaks | Damage to Pipe , Damage to Property/Equipment, Injury | 7. Ensure rest breaks are followed |  | D | 4 | L
|  | 9. Dust/dirt, grinding | Medical Treatment Injury, Environmental Impact | 8. Splatter mats when welding, double eye protection |  | D | 4 | L
|  | 10. Eye injury – Arc flash | Medical Treatment Injury | 9. Proper selection of rated shades for safety eyewear welding screen/shuelding installed to protect the public (in public areas) - install signage, as required |  | D | 4 | L
|  | 11. Exposure to bad weather/lightning | Fatality, Fire | 10. Monitor inclement weather - no work in rain or lightning as determined by supervisor, Project manager, monitoring of BOM. Risk assess distance of influence, temporary earthing of pipe strings Consultation with permit/safety personnel |  | A | 5 | M
|  | 11. AC induced voltage causing electric shocks | Fatality | 11. Risk assess, electrical safety assessment and temporary earthing of pipe strings |  | A | 5 | M
7.1 | Use Of Grinders | 1.Fatigue from grinding without rest breaks and working in awkward positions | Permanent Disability, Fatigue | 1. Grinder size limited to 7" rotate task, take regular breaks | SWMS, Prestart Checklists, VOC, Prestarts, Toolboxes, Induction | B | 4 | M | [7 empty] | Low
|  | 2. Grinder kick back, Disc disintegrating, Operator error | Permanent Disability | 2. Only experienced and VOC’d personnel to use grinders. Handles to be present on all grinders regardless of size. If handle is to be remove further risk assessment and supervisor acknowledgement is required. Pre-start checks on all gear, including leads and power source / RCD |  | B | 4 | M
|  | 3. Incorrect disc for job | Permanent Disability, Damage to Pipe , Damage to Property/Equipment | 3. Check disc choice prior to operation. Ensure correct RPM discs are sourced for grinders. Correct disc for job selection Check that disc is in date |  | B | 4 | M
|  | 4. Disc still spinning when put down | Permanent Disability, Damage to Property/Equipment | 4. Ensure disc has completely stopped spinning before placement |  | B | 4 | M
|  | 5. Eye/hand injury | Permanent Disability | 5. Double eye protection and full glove protection MANDATORY, Brush down clothes and grit deposit area prior to changing gear. Install screen/shielding installed to protect the public (in public areas) - install signage, as required |  | B | 4 | M
|  | 6. Loose guard or absence of guard | Permanent Disability | 6. Ensure guard is properly secured, no unguarded grinding. Guards are MANDATORY and cut back guards not permitted. |  | B | 4 | M
|  | 7. Damaged cables/cord/equipment | Medical Treatment Injury | 7. Pre-start inspections, electrician test and tag |  | D | 4 | L
[6 empty] | D | 4 | L
|  | 8. Enviroment working within causing fire | Fatality, Medical Treatment Injury |  |  | D | 4 | L
7.11 | Cut pups, bevel pipe and buff pipe | 1. Foreign bodies in eyes, cuts, burns. | Medical Treatment Injury, Eye Injury | 1. Double eye protection, gloves, full length shirts and pants. | SWMS, Prestart Checklists, VOC, Prestarts, Toolboxes, Inductions | D | 4 | L
|  | 2. Electrocution due to faulty equipment | Fatality | 2. Test and tag electrical equipment, visual inspect tools. RCD to be used and tested at pre-strart (operation) |  | A | 5 | M
|  | 3. Manual handling injuries from repetitive work | Medical Treatment Injury | 3. Correct lifting technique – knees bent , back straight, avoid twisting, use mechanical lifting where possible |  | D | 4 | L
|  | 4. Unstable load – poor skid set up | Medical Treatment Injury, Damage to Pipe | 4. Ensure pipe is set up securely on skids, check skid condition. |  | D | 4 | L
7.12 | Use of External Clamp | 1. Pinch hazard when clamping pipe | First aid treatment | 1. Gloves worn. | SWMS, Prestart | E | 5 | L
|  | 2. Manual handling injuries from lifting clamp | Medical Treatment Injury | 2. Team lift or use mechanical lifting aid. |  | D | 6 | L

## 8.0 NDT
8.0 NDT
IDENTIFY THE TASK or PROCEDURE, DESCRIBE THE HAZARDS AND RISKS, LIST THE CONSEQUENCES AND WHAT ARE THE EXISTING CONTROLS. | [5 empty] | EXISTING RISK |  |  | Recommendations | Responsibility | RISIDUAL RISK |  |  | STATUS | DATE Closed | TARGET LEVEL OF RISK |  | DATE RISK ADDED
ID | TASK or PROCEDURE What are the Job Steps | HAZARDS and RISKS What are they | CONSEQUENCES Resulting in | EXISTING CONTROLS | Consultation Method | Consequence | Likelihood | Level Of Risk |  |  | Consequence | Likelihood | Level Of Risk |  |  |  | RISK REVIEW DATE
8.1 | X-Ray | 1. Radiation Exposure | Permanent Disability | 1. Relevant warning signage to be displayed where necessary, site exclusion zone/access restricted. Radiation safety plan from sub-contractor. Licenced personnel. Wear personal exposure monitors | JSA, SDS VOC, Prestarts, Toolboxes. | B | 4 | M
|  | 2. Electrocution from x-ray HV cable (410 volts). | Fatality | 2. Prestart checks on electrical equipment. Electrical tagging / inspection system (quarterly). VRDs (damp conditions) and RCD fitted. Earthing. |  | A | 5 | M
|  | 3. Trips, slips or Falls. | First Aid Injury | 3. Good housekeeping |  | E | 4 | L
8.2 | PAUT | 1. Manual Handling | Medical Treatment Injury | 1. Two person lift of AUT unit, manual handling risk assessment required | JSA, Prestart Checklists, Prestarts, Toolboxes, Inductions | D | 4 | L
|  | 2. Electrical Hazards | Medical Treatment Injury | 2. RCD on generator, LV operation, ensure hazard identification as part of subcontractor engagement |  | D | 4 | L
|  | 3. Slips Trips and Falls | First Aid Injury | 3. Clean surfaces of excessive dust / dirt: - 3 points of contact when climbing access steps. - Clean steps and platforms |  | E | 4 | L
|  | 3, Overhead powerlines - LFI |  | 1. Earth stake to be maintained when working under overhead high voltage powerlines until pipe is tied in.
4. Falling objects from canopy
5. Burns/Radiation/Hot welding rods
6. Noxious fumes when welding
7. Moving plant from joint to joint
8. Fatigue from welding without rest breaks
9. Dust/dirt, grinding
10. Eye injury – Arc flash
11. Exposure to bad weather/lightning

## 9.0 Grit Blasting Coat & Paint
9.0 Grit Blasting Coat & Paint
IDENTIFY THE TASK or PROCEDURE, DESCRIBE THE HAZARDS AND RISKS, LIST THE CONSEQUENCES AND WHAT ARE THE EXISTING CONTROLS. | [5 empty] | EXISTING RISKS |  |  | Recommendations | Responsibility | RISIDUAL RISK |  |  | STATUS | DATE Closed | TARGET LEVEL OF RISK |  | DATE RISK ADDED
ID | TASK or PROCEDURE What are the Job Steps | HAZARDS and RISKS What are they | CONSEQUENCES (relate to Objectives) Resulting in | EXISTING CONTROLS | Consultation Method | Consequence | Likelihood | Level Of Risk |  |  | Consequence | Likelihood | Level Of Risk |  |  |  | RISK REVIEW DATE
9.1 | Pre Heat Pipe prior to grit blasting (LPG torch) | 1. Damaged cylinders from transporting to site | Damage to Property/Equipment | 1. Secure cylinders with ratchet straps Replace any damaged cylinders or regulator | JSA, SDS, Nacap Essential #6 Lifting Equipment, Nacp Permit to Work Procedure 3904-OPS-018-3, Prestart Checklists, VOC, PHA, Prestarts, Toolboxes, Inductions | D | 4 | L | [7 empty] | Low
|  | 2. Leaks – Damage hose | First Aid Injury, Damage to Property/Equipment | 2. Inspect hoses regularly, replace damaged hoses |  | E | 4 | L
|  | 3. Fire /burns from torch | First Aid Injury, Damage to Property/Equipment, Fire | 3. Fire extinguisher, PPE – Glasses, appropriate gloves |  | E | 4 | L
|  | 4. Faulty Equipment | Medical Treatment Injury, Damage to Property/Equipment | 4. Inspection of genset and cables, RCD installed |  | D | 4 | L
|  | 5. Dropped Pipe | Medical Treatment Injury, Damage to Pipe | 5. Lifting procedure established |  | D | 4 | L
9.2 | Grit blasting pipe | 1. Noise causing hearing damage Dust from blasting | First Aid Injury, Community Complaints, Environmental Impact | 1. Hearing protection to be worn whilst blasting Respiratory equipment to be worn whilst blasting Noise assessments | JSA, SDS, Prestart Checklists, VOC, PHA, Prestarts, Toolboxes, Inductions, ITP's, PTW | E | 4 | L | [7 empty] | Low
|  | 2. Slips, trips and falls due to uneven ground and accessing truck | First Aid Injury | 2. Signage, Exclusion zones, call up points, 3 points of contact for access to truck, handrails |  | E | 4 | L
|  | 3. Unauthorised personnel, Other vehicles | First Aid Injury | 3. Exclusion zones and barricaded areas to prevent access |  | E | 4 | L
|  | 4. Cuts, abrasions when blasting | First Aid Injury | 4. Inspect leads, Deadman switch |  | E | 4 | L
|  | 5. Blow outs of hose | Medical Treatment Injury, Damage to Property/Equipment | 5. Competent operator Inspection regime on all hoses pre & post usage, whip checks on all connections |  | D | 4 | L
|  | 6. Manual handling / ergonomics causing injury | Medical Treatment Injury | 6. Manual handling Risk assessment, JSA |  | D | 4 | L
|  | 7. Air quality from compressor (leaks) | First Aid Injury, Allergic Reaction, Environmental Impact, Exposure | 7. Calibrated air monitoring equipment Inspection of all equipment pre start up |  | E | 4 | L
|  | 8. Dropped object (garnet loading) | Environmental Impact, Spill | 8. Lifting procedure / Hiab |  | E | 4 | L
9.3 | Grit blasting Truck traversing | 1. Dragging blaster operator, Snagged hose. | Damage to Property/Equipment | 1. Visual contact with operator and blasters / coaters while moving. | JSA, Prestart Checklists, VOC, PHA, Prestarts, Toolboxes, Inductions | E | 4 | L | [7 empty] | Low
|  | 2. Collisions with plant and personal. | Fatality | 2. VOC operators, all operations complete before moving machines, Machines to move at walking pace. |  | A | 5 | M
|  | 3. Poor visibility from dust | Fatality, Damage to Pipe , Damage to Property/Equipment | 3. Check mirrors and camera’s (where fitted) before moving |  | A | 5 | M
9.4 | Coating / painting application and remove paper | 1. Cuts from masking machine | First Aid Injury | 1. Use handle of machine | JSA, SDS, Prestart Checklists, VOC, PHA, Prestarts, Toolboxes, Inductions | E | 4 | L | [7 empty] | Low
|  | 2. Inhalation of chemicals, Fumes, Dust, Noise, Burns | Medical Treatment Injury, Allergic Reaction, Exposure, Respiratory Issues | 2. Spray mask and ninja / latex gloves to be worn, PPE. Select appropriate gloves for task |  | D | 4 | L
|  | 3. Visibility reduced when paint gets on visor | Loss of Production | 3. Visor replacement as required |  | E | 4 | L
|  | 4. Trips, Falls into trench (below ground piping) | First Aid Injury | 4. Pre inspection of work area |  | E | 4 | L
|  | 5. Struck by canopy when lowering into position | First Aid Injury | 5. Competent VOC operators |  | E | 4 | L
9.5 | Working in and around Bell Holes | 1. Condition of the bell hole causing injury or engulfment | Crush Injury | 1. Correct benching and ramps to be installed / trench shields. | JSA, Prestarts, Toolboxes, Inductions | C | 4 | M | [7 empty] | Low
|  | 2. Other plant and equipment | Permanent Disability | 2. Move other plant and equipment out of area. Clear communication with other crews. |  | B | 4 | M | [7 empty] | Low
|  | 3. Carrying of equipment in and out of bell hole | Medical Treatment Injury, Damage to Pipe , Damage to Property/Equipment | 3. Correct manual handling lifting methods to be employed |  | D | 4 | L | [7 empty] | Low
|  | 4. Working in the bell hole – heat, fumes, dust | Medical Treatment Injury, Eye Injury, Health Effects, Heat Stress/Stroke | 4. Use a spotter when employees are in bell hole (blasting, application.) Respiratory protection. Dust suppression. Hydrate and take regular breaks. |  | D | 4 | L | [7 empty] | Low
|  | 3, Overhead powerlines - LFI |  | 1. Earth stake to be maintained when working under overhead high voltage powerlines until pipe is tied in.
4. Falling objects from canopy
5. Burns/Radiation/Hot welding rods
6. Noxious fumes when welding
7. Moving plant from joint to joint
8. Fatigue from welding without rest breaks
9. Dust/dirt, grinding
10. Eye injury – Arc flash
11. Exposure to bad weather/lightning

## 10.0 Excavation
10.0 Excavation
IDENTIFY THE TASK or PROCEDURE, DESCRIBE THE HAZARDS AND RISKS, LIST THE CONSEQUENCES AND WHAT ARE THE EXISTING CONTROLS. | [5 empty] | EXISTING RISK |  |  | Recommendations | Responsibility | RISIDUAL RISK |  |  | STATUS | DATE Closed | TARGET LEVEL OF RISK |  | DATE RISK ADDED
ID | TASK or PROCEDURE What are the Job Steps | HAZARDS and RISKS What are they | CONSEQUENCES Resulting in | EXISTING CONTROLS | Consultation Method | Consequence | Likelihood | Level Of Risk |  |  | Consequence | Likelihood | Level Of Risk |  |  |  | RISK REVIEW DATE
10.1 | Excavate with Excavator | 1. Attachment falling off – striking personnel/equipment or causing damage. | Fatality, Crush Injury | 1. Quick hitch pins installed / check quick hitch engaged. Operate within equipment parameters. Inspection of equipment for metal fatigue and wear. Exclusion zone in and around immediate work area SPIN | CEMP, PTW Procedure 3904-OPS-018-3, Induction Process, VOC, JSA, Prestarts, Toolboxes Nacap Traffic Management (Construction in Public Thoroughfares) 3904-OPS-017-3 Nacap Safety Essential # 10 Worksite Traffic # 9 Foreign Services # 7 Safe Working with Electricty # 2 Excavation | A | 5 | M
|  | 2. Striking personnel/equipment in work area with bucket, blind spots. | Fatality, Crush Injury, Damage to Property/Equipment | 2. Inductions. Exclusion zone communicated at prestart and to visiting personnel, eye contact to be made with operator prior to approaching, confirm eye contact with operator established. |  | A | 5 | M
|  | 3. Environmental impact - Burst Hoses. | Spill | 3. Spill kits to be available for all machines. Report all spills to Supervisor / Project Manager. Anti burst devices installed |  | E | 3 | L
|  | 4. Hitting Pipe – damage. | Damage to Pipe , Damage to Property/Equipment | 4. Check clearance from project strung pipe (nil operation pipe), competent operator to operate (VOC). |  | D | 4 | L
|  | 5. Other vehicles passing through work area. | Damage to Property/Equipment, Vehicle Incident | 5. Operator ID magnets displayed on all machines, vehicles to call up on radio channel #TBA prior to entering and passing through area slowly. Traffic management plan implemented |  | D | 5 | L
|  | 6. Striking foreign services. | Fatality, Damage to Asset, Damage to Property/Equipment, Medical Treatment Injury, Damage to Asset, Damage to Property/Equipment, Impact on Third Party Relationship, Loss of Production, Production Delays, Project Stopped | 6. Check for Catenaries and signage when working near overhead, spotter maybe required. Spotter maybe required when excavating near underground services, public infrastructure, residential areas, follow PTW requirements. Hand dig within specified required distance. known Foreign services to be located and identified – install barricading for exclusion zones. Excavation Permit in place |  | E | 3 | L
|  | 7. Striking / discovering unknown foreign services. | Fatality, Damage to Asset, Damage to Property/Equipment, Medical Treatment Injury, Damage to Asset, Damage to Property/Equipment, Impact on Third Party Relationship, Loss of Production, Production Delays, Project Stopped | 7. DBYD completed, all known services located prior to mechanical excavation, inspection of the site to check for signs of other assets, competent and experienced spotters and operators Excavation Permit in place |  | B | 4 | M
|  | 8. Excavator sliding/falling into trench. | Damage to Property/Equipment | 8.Experienced VOC'd operators, JSA/SWMS, work methodology. |  | E | 3 | L
|  | 9. Bell hole collapse / instability. | Crush Injury, Environmental Impact, Impact on Third Party Relationship, Production Delays | 9. Trench shield to be installed |  | E | 3 | L
|  | 10. External Road Users / General Public | Collision, Community Complaints, Environmental Impact, Impact on Third Party Relationship, Production Delays | 10. Ensure work area is secure and delininated from public. Traffic Management Plans in place and traffic control personnel in operations where required. |  | E | 3 | L
10.2 | Excavating Bell holes and Trenches in built up area | 1. Unauthorised access by a member of the public, e.g. children, falling into bell hole. | Fatality, Damage to Reputation, Impact on Third Party Relationship, Project Stopped | 1. Fencing off site - fenced in areas deemed necessary. Minimise open excavations in the vicinity of areas with risk of public access. Signage, public/land owner consultation. Site security in place. As required Traffic mangement devices and signage in place 24 hours, as required in accordnace with approved TMP and Stakeholder requirements | Induction, JSA, Prestart, Toolbox, Site Security Plan, Traffic Management Plan | A | 5 | M | [7 empty] | Low
10.3 | Changing Teeth on buckets / servicing | 1. Clip shattering when removing – eye injury, cuts. | First Aid Injury, Eye Injury | 1. Double eye protection worn, gloves, sleeves rolled down, correct tool/s used (Circlip pliers). | Induction Process, JSA, Prestarts, Toolboxes | E | 4 | L
|  | 2. Hot surfaces – burns from teeth, chain, bucket | First Aid Injury, Burns to skin | 2. Gloves to be worn at all times, long sleeve shirt and pants and safety boots. |  | E | 4 | L
|  | 4. Sprains from attempting to remove teeth that are stuck. | First Aid Injury | 4. Call a fitter to remove and replace stuck teeth. |  | E | 4 | L
|  | 5. Cuts and crushing from using incorrect tools. | First Aid Injury, Crush Injury | 5. Use of good condition hammer, Pry Bar, Screwdriver and pliers only. Gloves, double eye protection to be worn. |  | E | 4 | L
|  | 6. Crushing , entanglement from moving parts, fall from heights during maintenance / servicing. | Lost Time Injury, Crush Injury | 6. All maintenance and servicing to be completed by project fitter / mechanic – JSA/SWMS developed by Mechanics. |  | E | 4 | L
10.4 | Checking Depth of Trench | 1. Falling in trench. | Medical Treatment Injury | 1. Visual inspect edge of trench for signs of cracking or potential collapse, do not stand close to edge of trench. Ensure use of measuring staff extender to ensure no encroaching on edge of trench. | Induction Process, JSA, Prestarts, Toolboxes [Safety Essentials #2 - Excavation] | D | 4 | L
|  | 2. Uneven ground – trips. | First Aid Injury | 2. Check for any obstacles, holes at edge of trench / travel path. |  | E | 4 | L
10.5 | Using Rock Breakers | 1. Noise. | Permanent Disability, Community Complaints, Fatigue | 1. Hearing protection worn by operator and crew (also approved visitors to work area). EPA guidelines to be adhered to | Induction Process, JSA, Prestarts, Toolboxes | B | 4 | M | [7 empty] | Low
|  | 2. Eye injury, cuts from flying rock / debris. | Medical Treatment Injury, Eye Injury | 2. Exclusion zone communicated at prestart to crew and to visitors ( exclusion zone to be determined based on location). |  | D | 4 | L
10.6 | End of Day – Pack Up | 1. Open trench – Plant, personnel, fauna fall in trench. | Fatality, Damage to Property/Equipment, Impact on Third Party Relationship, Project Stopped, Stock Loss, Vehicle Incident, Wildlife Injury/Fatality | 1. Barricade open trench at end of day, concrete barriers (interlocked for open trench adjacent to roads). Site assessment in areas of public access (children) to ensure site security and protection to the public. Night time TMP in place and all requiremetns installed | Induction Process, JSA, Prestarts, Toolboxes | A | 5 | M | [7 empty] | Low
|  | 2. Crushing from suspended boom / buckets. | Fatality, Crush Injury | 2. All booms and buckets to be lowered to ground at end of day. |  | A | 5 | M | [7 empty] | Low
|  | 3. Waste/Contamination. | Environmental Impact | 3. Remove all waste and dispose of in designated bins. |  | E | 3 | L | [7 empty] | Low
|  | 3, Overhead powerlines - LFI |  | 1. Earth stake to be maintained when working under overhead high voltage powerlines until pipe is tied in.
4. Falling objects from canopy
5. Burns/Radiation/Hot welding rods
6. Noxious fumes when welding
7. Moving plant from joint to joint
8. Fatigue from welding without rest breaks
9. Dust/dirt, grinding
10. Eye injury – Arc flash
11. Exposure to bad weather/lightning

## 11.0 Lower In, Pad & Backfill
11.0 Lower In, Pad & Backfill
IDENTIFY THE TASK or PROCEDURE, DESCRIBE THE HAZARDS AND RISKS, LIST THE CONSEQUENCES AND WHAT ARE THE EXISTING CONTROLS. | [5 empty] | EXISTING RISK |  |  | Recommendations | Responsibility | RISIDUAL RISK |  |  | STATUS | DATE Closed | TARGET LEVEL OF RISK |  | DATE RISK ADDED
ID | TASK or PROCEDURE What are the Job Steps | HAZARDS and RISKS What are they | CONSEQUENCES Resulting in | EXISTING CONTROLS | Consultation Method | Consequence | Likelihood | Level Of Risk |  |  | Consequence | Likelihood | Level Of Risk |  |  |  | RISK REVIEW DATE
11.1 | Check trench / work area | 2. Poor skid set up. | Damage to Pipe , Damage to Property/Equipment | 2. Check and stabilize skid set up where required, supervisor to assess string path. |  | E | 4 | L
|  | 3. Trench collapse / unstable ground. | Fatality | 3. Visual trench inspection - if trench collapse, excavators to rectify, site maintenance, (no entry into unbattered/benched/shored trench by personnel deeper than 1.5 metres). Project Non-Negotiable. |  | A | 5 | M
|  | 4. Uneven surface / poor travel path. | First Aid Injury | 4. Good housekeeping |  | E | 3 | L
|  | 5. Restricted workspace. | Environmental Impact, Loss of Production | 5. Good project planning to ensure activities are not rushed. |  | E | 3 | L
|  | 6. Vehicle parked on site in work area. | Damage to Property/Equipment, Vehicle Incident | 6. Relocate vehicles from intended travel path. |  | E | 5 | L
|  | 8. Foreign services. | Fatality, Damage to Asset, Damage to Property/Equipment | 8. Check for overhead and underground services – Catenaries, signage, identify underground (conduit), alignment sheets , spotter (overhead service). |  | A | 5 | M
|  | 9. Other Vehicles driving through. | Damage to Property/Equipment, Vehicle Incident | 9. Call up points, operator ID Magnets. |  | E | 5 | L
|  | 10. Removing debris off the bottom of the trench. | Fatality | 10. Use correct tools for task (no entry into unbattered/benched/shored trench by personnel deeper than 1.5 metres). Project Non-Negotiable. |  | A | 5 | M
11.2 | Jeep Pipe | 1. Electric shock | Medical Treatment Injury | 1. Earth Pipe end with lead and bulldog clip long enough to allow pipe to get from strung position to bellhole, earth tail attached to jeeper. | Induction, JSA, Prestart, VOC,Nacap Safety Essential # 7 Safe Working with Electricty | D | 4 | L
|  | 2. Damaged pipe not detected | Damage to Pipe | 2. Jeep Pipe |  | D | 4 | L
|  | 3. Pipe not shaded. | Damage to Pipe | 3. Before shading and padding recommences, pipe to be jeeped with half-moon brush. |  | D | 4 | L
|  | 4. Personnel in trench. | Fatality | 4. Jeeper handle and brush handle long enough to ensure personnel do not need to enter trench. Project Non-Negotiable. |  | A | 5 | M
11.3 | Lower In Pipe and CP test cables | 1. Other crews at end of string to be lowered in, other vehicles. | Lost Time Injury, Crush Injury | 1. Supervisor to drive line of string to be lowered in, and ensure all clear. | Nacap Safety Essential # 5 Mobile Crane , #6 Lifting Equipment, SWMS. | C | 5 | L | [7 empty] | Low
|  | 2. Damaged lifting equipment, dirty rollers. | Damage to Pipe , Damage to Property/Equipment, Production Delays | 2. Clean rollers, rigger to inspect lifting equipment and tag out damaged gear. |  | E | 4 | L | [7 empty] | Low
|  | 3. Lifting equipment not rated for load, not suitable for the lift being performed, machine tip over. | Damage to Property/Equipment, Damage to Reputation | 3. Lift plan developed, reviewed and signed by crew, visual inspection of ground conditions. Experienced VOC'd Intermediate Rigger and Operators. Certified, test and tagged lifting equipment. ROPS and seatbelt installed. |  | D | 5 | L | [7 empty] | Low
|  | 4. Pipe falling off skids / shock load. | Medical Treatment Injury, Damage to Pipe , Damage to Property/Equipment | 4. Check skids, catch off machine to be used when required / identified – supervisor to assess. |  | C | 5 | L | [7 empty] | Low
|  | 5. Poor communication between operators and lift coordinator ( intermediate rigger), unclear instruction. | Medical Treatment Injury, Damage to Pipe , Damage to Property/Equipment, Lack of Attention - Error, Loss of Production | 5. All operators and intermediate rigger to have radios, only intermediate rigger to coordinate lift. |  | D | 4 | L | [7 empty] | Low
|  | 6. Falling in trench, crush injuries between pipe and boom, walking under a suspended load, Unauthorised personnel in lift area. | Fatality, Crush Injury, Project Stopped | 6. No personnel to walk between pipe and trench or pipe and boom, area to be clear of all personnel during lowering in, intermediate rigger to coordinate. Unravel CP cables out and away from trench. |  | A | 5 | M | [7 empty] | Low
11.4 | Coating repairs | 1. Fall from height – into trench. | Fatality | 1. Planks to be used to work over trench (when required), check ground conditions, Pre jeep pipe on skids where possible. | Induction, JSA, SDS Prestarts, Toolboxes, Nacap Safety Essential # 12 Hazardous Chemicals (storage and handling) | A | 5 | M
|  | 2. Burns. | Medical Treatment Injury, Burns to skin | 2. Do not point light torch at other personnel, do not place on ground lit, check hose condition. |  | E | 4 | L
|  | 3. Hazardous material – skin irritation, fumes. | First Aid Injury, Allergic Reaction, Respiratory Issues | 3. PPE to be worn in accordance with SDS. |  | E | 4 | L
|  | 4. Eye injuries when sanding. | First Aid Injury, Eye Injury | 4. Eye protection to be worn. |  | E | 4 | L
|  | 5. Manual handling. | First Aid Injury | 5. Knees bent , back straight, avoid twisting , bend at knees. |  | E | 4 | L
11.5 | Lowering in within proximity of power lines | 1. Catenaries not in-place or damaged - signage down/damaged, removed. | Fatality, Damage to Property/Equipment | 1. Installation and surveillance of Catenaries and signage. Check for overhead services, alignment sheets , spotter. | Safety Essential # 7 Safe Working with Electricty, JSA, VOC, Prestart, | A | 5 | M | [7 empty] | Low
|  | 2. Site and weather conditions not suitable. | Fatality | 2. Assessment to be conduct by Superintendent prior to accessing site when weather conditions change. |  | A | 5 | M | [7 empty] | Low
11.6 | Bedding / Shading of Pipe | 1. Other personnel and vehicles, No clear communication, No line of sight, Restricted access on site | Fatality, Damage to Property/Equipment, Vehicle Incident | 1. Spotter with positive communication and line of sight. Exclusion of personnel and vehicles from padding side | JSA, Prestart Checklists, VOC, PHA, Prestarts, Toolboxes, Inductions, ITP's | A | 5 | M | [7 empty] | Low
|  | 2. Dust | Fatality, Damage to Pipe , Damage to Property/Equipment, Respiratory Issues | 2. Wait for dust to settle if line of sight restricted. Pre preparation and stabilisation of working area. |  | A | 5 | M
11.7 | Jeeping, Bedding and padding of bellholes | 1. Open bell holes - access for jeeping | First Aid Injury | 1. Ramps for access and spotter as required | JSA, Prestart Checklists, VOC, PHA, Prestarts, Toolboxes, Inductions | E | 4 | L | [7 empty] | Low
|  | 2. Damage to pipe | Damage to Pipe , Damage to Property/Equipment | 2. Careful placement of bedding and padding materials around conduit/pipe |  | E | 4 | L
|  | 3. Other machinery | Damage to Pipe , Damage to Property/Equipment, Injury | 3. Communication with other operators. |  | D | 4 | L
|  | 4. Struck by excavator | Fatality | 4. Clear communication with other vehicles on site, UHF, exclusion zones |  | A | 5 | M
11.8 | Supply of Imported sand / backfill | 1. Volume of delivered loads of imported sand | Production Delays | 1. Project Engineer to order quantities | JSA, Prestarts, Toolboxes, Inductions, Delivery Driver Induction ,Safety Essential # 10 Worksite Traffic | D | 4 | L | [7 empty] | Low
|  | 2. Tipping of sand from trucks - tip-over(truck and dog) | Damage to Pipe , Damage to Property/Equipment, Injury, Vehicle Incident | 2. Only truck and dogs allowed, no semi trailers. Competent operator and clear communication between spotter and driver at all times. |  | D | 4 | L
|  | 3. Non-inducted delivery drivers arrive at site | Damage to Pipe , Damage to Property/Equipment, Environmental Impact, Injury, Vehicle Incident | 3. All delivery drivers to be put through the Nacap Delivery Driver Induction prior to entering Nacap work site. |  | D | 4 | L
11.9 | Placement of Imported sand / backfill | 1. Interaction with other plant and equipment with reduced site and increased traffic | Damage to Pipe , Damage to Property/Equipment, Eye Injury, Injury, Vehicle Incident | 1. Spotter for loading of flo-con / Agi or other placement machinery. Communication with other plant. | JSA, Prestart Checklists, VOC, PHA, Prestarts, Toolboxes, Inductions,, Delivery Driver Induction | D | 4 | L | [7 empty] | Low
|  | 2. Soft ground conditions causing instability/ trench collapse | Crush Injury, Damage to Pipe , Damage to Property/Equipment, Environmental Impact | 2. Trained operators and JSA |  | C | 4 | M | [7 empty] | Low
|  | 3. Damage to pipe from foreign object in sand (rock etc.) | Damage to Pipe | 3. Spotter checking quality of material |  | E | 4 | L | [7 empty] | Low
11.1 | Entering bellhole to tie pipe strings together | 1. Confined space / restricted work space Potentially restricted access Potentially contaminated ground Lack of good atmosphere Welding fumes | Fatality, Lost Time Injury, Injury | 1. Permit to work system 2. Training 3. Minimise bell holes by maximising string lengths 4. Review access 5. Forced air ventilation 6. Gas check on entry and ongoing monitoring 7. PID monitors | JSA, Prestart Checklists, VOC, PHA, Prestarts, Toolboxes, Inductions, Nacap Confined Space Procedure 3904-OPS-019-3 | B | 2 | M | [7 empty] | Low
|  | 3, Overhead powerlines - LFI |  | 1. Earth stake to be maintained when working under overhead high voltage powerlines until pipe is tied in.
4. Falling objects from canopy
5. Burns/Radiation/Hot welding rods
6. Noxious fumes when welding
7. Moving plant from joint to joint
8. Fatigue from welding without rest breaks
9. Dust/dirt, grinding
10. Eye injury – Arc flash
11. Exposure to bad weather/lightning

## 12.0 HDD
12.0 HDD
| IDENTIFY THE TASK or PROCEDURE, DESCRIBE THE HAZARDS AND RISKS, LIST THE CONSEQUENCES AND WHAT ARE THE EXISTING CONTROLS. | [6 empty] | EXISTING RISK |  |  | Recommendations | Responsibility | RESIDUAL RISK |  |  | STATUS | DATE Closed | TARGET LEVEL OF RISK |  | DATE RISK ADDED
| ID | CATEGORY | TASK or PROCEDURE What are the Job Steps | HAZARDS and RISKS What are they | CONSEQUENCES Resulting in | EXISTING CONTROLS | Consultation Method | Consequence | Likelihood | Level Of Risk |  |  | Consequence | Likelihood | Level Of Risk |  |  |  | RISK REVIEW DATE
Pre-mobilisation
| 12.1 | Health & Safety | Pre-mobilisation | 1. Commencement of works without inductions, approved HDD Management Plan, completion of on-boarding [competencies/VOCs to be checked]) LECH Form 2 | Jemena / Government directive to cease works; | ▪ Nacap LECH Form 2 process , Inductions complete, HDD Plan submitted / approved, VOC's checked ▪ Subcontractor pre-mobilisation process (Nacap and Jemena) ▪ Readiness for Construction Verification (Nacap process) | Vendor assessment questionnaire; Plant inspections by Nacap; Document approval process; Inductions; Pre-mob checklist completion; | D | 4 | L
|  |  |  | 2. Failure to perform pre-inspection of equipment (cranes, mechanical status) | Mechanical failure resulting in impact to programme; Use of un-certified plant (cranes); Incident (OHS); Incident (Environment); | ▪ Plant and equipment to be nominated by subcontractor; ▪ Subcontract to detail mobilisation requirements; ▪ Pre-mobilisation inspections; |  | C | 4 | M
|  |  |  | 3. Pre-inspection identifies HDD equipment as non-compliant | Failure of subcontractor to mobilise to site on time resulting in delay to programme | ▪ Plant and equipment to be nominated by subcontractor; ▪ Subcontract to detail mobilisation requirements; ▪ Pre-mobilisation inspections; |  | D | 4 | L
|  |  |  | 4. Transport permits not in place | Jemena reputation damage; Failure of subcontractor to mobilise to site on time resulting in delay to programme | ▪ Contractual mechanisms; ▪ Pre-mobilisation checklist; ▪ Plant used on project to be nominated by subcontractor; |  | D | 4 | L
Road Transport / Loading and Unloading
| 12.2 | Health & Safety | Travel to/from site | 1. Road Hazards/ conditions | Fatality, Damage to Property/Equipment | ▪ Qualified and competent operators to operate vehicles. ▪ Driving to occur as per current road conditions. ▪ Journeys planned and managed appropriately so as to avoid unpaved roads, creek and river crossings, and remote areas in wet season. ▪ Ensure sufficient water, food is carried on board in case of an emergency. ▪ Driving at dusk and dawn is to be avoided if possible to avoid wildlife encounters. | Inductions; Driver licence obligations; Permit requirements; Subcontract requirements; Pre-mobilisation inspections; Nacap Safety Essential #18 Chain of Responsibility | C | 3 | M
|  |  |  | 2. Load shift | Damage to Property/Equipment | Load to be checked regularly when travelling for prolonged distances and readjusted if required and utlise fit for purpose and rated restraints. |  | C | 3 | M
|  |  |  | 3. Fatigue/ Driving under the influence | Fatality, Damage to Property/Equipment | ▪ Regular rest breaks to be held, at least to the requirements as outlined in current National Driver Work Diary. ▪ Zero tolerance towards working/ driving under the influence of alcohol or illicit drugs. ▪ Random Drug and daily alcohol testing on behalf of the company. |  | C | 4 | M
|  |  |  | 4. Road traffic | Fatality | ▪ All current road rules to be obeyed by, incl. wearing seatbelts, adhering to speed limit, not using mobile phone while driving. ▪ Operate roadworthy vehicle, and ensure roadworthiness before use |  | B | 4 | M
| 12.3 | Health & Safety | Loading/ unloading equipment from trailer/ trucks | 1. Lifting equipment faulty, exceeding lifting capacity or getting damaged during task. | Permanent Disability, Lost Time Injury, Damage to Property/Equipment | ▪ Pre-Start on all used equipment conducted. ▪ Only rated, inspected equipment to be used. ▪ Experienced, qualified person to conduct lifting operations. ▪ Work never to be conducted under suspended loads. | Inductions; Driver licence obligations; Permit requirements; Subcontract requirements; Pre-mobilisation inspections; Safety Essential #5 Mobile Crane and #6 Lifting Equipment | C | 3 | M
|  |  |  | 2. Equipment not placed in suitable position, causing equipment to roll/ fall. | Damage to Property/Equipment | ▪ Equipment to be placed in position that allows secure placement and securing of load. ▪ Load rating of truck/ trailer not to be exceeded. |  | C | 3 | M
|  |  |  | 3. Heavy machinery operation | Lost Time Injury | ▪ Competent, trained person to operate machinery. ▪ Non- essential personnel cleared from area. |  | D | 2 | M
|  |  |  | 4. Vehicle interaction with other machinery | Fatality, Damage to Property/Equipment | ▪ Competent, trained person to operate machinery. ▪ Signalling clear between operators. ▪ Reversing signals audible. ▪ Spotters utilised if necessary. ▪ Under control of Traffic Management Plan - Access via Seawall Road HDD1 – Traffic Control Plans in place (Reviewed and Approved) |  | D | 3 | M
|  |  |  | 5. Injuries sustained to bystanders, caused by falling loads | Fatality | ▪ Non-essential personnel cleared from area. ▪ Area fenced/ barricaded off if necessary. ▪ delininated work site fenced off as above ▪ use of spotter and safety signaged erected |  | C | 3 | M
| 12.4 | Health & Safety | Connecting/ disconnecting trailer from Trucks | 1. Equipment damage to Prime Mover Turntable or trailer king pin | Damage to Property/Equipment | ▪ Before reversing Prime Mover under semi-trailer, ensure turntable height matches king pin height on trailer ▪ Reverse truck in slowly ▪ Spotter in place if possible ▪ Avoid using air bags to connect truck to trailer as misalignment can lead to damage to both pieces of equipment ▪ Only licensed competent staff, or personnel under supervision of a licensed, competent person are to operate trucks | Inductions; Driver licence obligations; Permit requirements; Subcontract requirements; Pre-mobilisation inspections; | C | 4 | M
|  |  |  | 2. Damage to airlines/ power leads | Damage to Property/Equipment | ▪ Ensure airlines. Power leads are disconnected before driving truck away from trailer |  | D | 3 | M
|  |  |  | 3. Trailer sinking into unstable ground | Damage to Property/Equipment | ▪ Sleepers, or similar, placed under jackleg on potentially soft surfaces |  | D | 4 | L
|  |  |  | 4. Uncontrolled movement of trailer | Fatality, Damage to Property/Equipment | ▪ Wheel chocks placed under wheel when parked where potential for movement exists or as per site conditions ▪ Ensure trailer brakes are applied before take off |  | C | 4 | M
|  |  |  | 5. Manual handling | Lost Time Injury | ▪ As per Material and Manual handling procedure ▪ PPE to include gloves. ▪ Gear selection of Jack legs as required |  | D | 3 | M
| 12.5 | Health & Safety | Loading track mounted equipment onto trailer/ truck | 1. Unanticipated movement of equipment during loading/ unloading, potentially exposing persons to serious injury or death, should the equipment roll of the ramps or los of grip. | Fatality | ▪ Taking local conditions into consideration, e.g. loading ramps, natural sloping ground and weather conditions. ▪ Only experienced, competent operators to undertake the task, having spotters in place, who are located in a safe position. ▪ Operator to wear safety critical equipment when operating machinery like seatbelts. ▪ Clear communication/ visual with spotters. ▪ Steel runs welded along ramps to allow gripping off tracks, or suitable non-slip materials in place. | Inductions; Driver licence obligations; Permit requirements; Subcontract requirements; Pre-mobilisation inspections; | C | 3 | M
|  |  |  | 2. Environmental factors, incl. gradient of surface, overhead services and slippery conditions | Lost Time Injury, Damage to Property/Equipment, Environmental Impact, Erosion and Heavy Dust | ▪ Assess environmental factors like wet weather, natural or man-made loading ramps, overhead services and implement suitable controls on site. ▪ Loading preferably not to be conducted in slippery conditions, near power lines or on unsuitable gradient of surface. |  | D | 3 | M
| 12.6 | Health & Safety | Lifting loads | 1. SWL of equipment exceeded | Fatality, Damage to Property/Equipment | ▪ Equipment inspection conducted prior to conducting tasks by a competent person | Inductions; Driver licence obligations; Permit requirements; Subcontract requirements; Pre-mobilisation inspections; Safety Essential #5 Mobile Crane and #6 Lifting Equipment | D | 2 | M
|  |  |  | 2. Faulty equipment | Lost Time Injury, Damage to Property/Equipment | ▪ Equipment inspection conducted prior to conducting tasks by a competent person ▪ Visual inspection of all lifting equipment prior to use, and inspected quartly (ie. as per test and tag requirements) ▪ Use desiganted lifitng points |  | C | 4 | M
|  |  |  | 3. Incompetent person conducting task | Fatality, Damage to Property/Equipment | ▪ Competent, trained operator operating excavator or forklift or similar, Lift Plan |  | D | 4 | L
|  |  |  | 4. Equipment damage due to lift | Damage to Property/Equipment | ▪ Competent person (.e.g. dogger) to attach lifting devices and organise lift |  | D | 4 | L
|  |  |  | 5. Suspended load | Lost Time Injury | ▪ Exclusion zone erected to prevent non-essential personnel entering area, ▪ Tag lines to be used where applicable. ▪ No person to be located under suspended load. |  | D | 3 | M
| 12.7 | Health & Safety | Securing loads | 1. Load secured insufficiently, causing load to move or fall resulting in equipment damage or personal injury to personnel or road traffic | Lost Time Injury, Damage to Property/Equipment | ▪ Competent, experienced personnel to secure loads taking into consideration the current Chain of Responsibility laws. ▪ Load chains and straps to be used to secure equipment, taking sharp edges and different shapes and weights of material to be secured into consideration. ▪ All items to be secured appropriately against accidental drop or fall from vehicle. ▪ Use of suitablly rated straps and restraining equipment | Inductions; Driver licence obligations; Permit requirements; Subcontract requirements; Pre-mobilisation inspections; Nacap Safety Essential #18 Chain of Responsibility Safety Essential #12 - HAZ Substances | C | 4 | M
|  |  |  | Hazardous substances not protected from environment sufficiently causing leaks or spills through wind , rain etc. | Lost Time Injury, Environmental Impact | ▪ Cements, muds and other substances that can be affected by water, rain, wind etc. to be covered and be secured so as to avoid environmental spills or leaks. ▪ Liquid material to be stored so as to minimise environmental effects if leakage or spoil occurs. |  | C | 4 | M
Pre-Start
| 12.8 | Health & Safety | All tasks | 1. PPE requirements to reduce Injuries from exposure to Flying Dust and debris UV exposure and heat, impacts, cuts stabs or punctures from materials, Noise, And to increase visibility to reduce likelihood of being struck by plant or equipment. Slips, trips and falls | Lost Time Injury, Environmental Impact | ▪ 100% cotton Hi Vis long sleeve shirt sleeves to be rolled down and buttoned at cuff ▪ 100% cotton full length pants ▪ steel cap safety boots ▪ Safety Glasses – clear and tinted. ▪ Hard hat ▪ Gloves – worn when manual tasks are being conducted. ▪ Hearing protection – on person and worn as required. ▪ Wet weather and cold weather wear will be made available to all workers before weather conditions require it. ▪ Sunscreen is to be available in crib rooms, amenities and vehicles ▪ Good housekeeping to be maintained at all times | SWMS, Prestarts, Toolboxes | D | 4 | L
| 12.9 | Health & Safety | Select Plant for task/activity | 1. ▪ Plant used for task/activity not up to required standard ▪ On site plant failure/breakdown ▪ Refuelling of plant | Environmental Impact, Loss of Production | ▪ Correct type and capacity of plant selected for the task ▪ Plant operators to complete a daily checklist before startup ▪ Immediate action to be taken on identified deficiencies ▪ Servicing/maintenance as per manufactures instructions ▪ Reversing alarms on all major plant ▪ Orange vision alert lights on all major plant and construction vehicles (including delivery trucks) ▪ Pump and nozzle to be manned at all time and spill kit to be available ▪ Excavators to be utilized where necessary for various lifting procedures. All slings and chains must be certified and current. ▪ Licensed and competent rigger or dogman to perform daily inspection of all lifting gear prior to use and document ▪ A lifting register must be maintain for all lifting equipment by rigger or dogman ▪ Plant risk assessments must be completed and kept in plant/cab at all times ▪ UHF radio fitted and serviceable for useAll relevant guarding must be in place. ▪ All relevant guarding must be in place. | SWMS, Prestarts, Toolboxes | D | 4 | L
| 12.1 | Health & Safety | Select labour for task/activity | 1. Personnel not understanding the task and hazards. | Lost Time Injury, Loss of Production | ▪ All personnel to undergo specific training (site and general industry inductions, task/activity awareness, other training as required) before commencing on site ▪ Delivery drivers made ware of entry/exit points to the work area ▪ Certified/competent personnel (or trainees under supervision) for prescribed occupations (excavator operator etc) ▪ Licensed/competent drivers of construction traffic ▪ Pre▪start meeting to be held every morning before commencing work. Toolbox meetings to be held weekly. Regular site inspections undertaken by Supervisors and HSE department. | SWMS, Prestarts, Toolboxes | D | 4 | L
| 12.11 | Health & Safety | Access to site | 1. Landholder, public, traffic impact | Impact on Third Party Relationship, Loss of Production | ▪ Ensure approvals or permits, access permissions are granted prior to entry into any landholder property, traffic maangment setup. ▪ Only authorised entry/exit points and associated access tracks/paths are to be travelled in accordance withapprovals ▪ Maintain all gates and fences in accordance with approval / permit requirements ▪ Vehicles are to meet all specific weed/seed decontamination requirements prior to entry, i.e. be washed & certified clean on entry and have a current weed seed certificate ▪ Ensure limited disruption and interaction with public / landholders all times | SWMS, Prestarts, Toolboxes | D | 4 | L
| 12.12 | Health & Safety | Security of site | 1. Presence of unauthorised people onsite | Impact on Third Party Relationship, Industrial Relations Issue, Loss of Production | ▪ Site delineation through use of barricading, fencing and or signage – ▪ including radio frequency, Site office signs are to be erected. ▪ Personnel are to notify Supervisor of any unauthorized persons and ensure that work in vicinity stops until supervisor arrives ▪ If unauthorised person leaves worksite or is removed the Project Manager must approve works to recommence. ▪ All personnel will be informed during pre▪start meetings or toolboxes, as required to site and project security concerns, anticipated protest activities and additional actions to take in the event of unauthorised person entering site. | SWMS, Prestarts, Toolboxes | D | 4 | L
| 12.13 | Health & Safety | Plant/truck/vehicle travel and material deliveries | 1. Collision with other construction traffic/personnel Other road/traffic accidents/collisions with pedestrians | Fatality, Damage to Property/Equipment, Impact on Third Party Relationship | ▪ General road rules apply on site (includes obeying all signs) – some specifics are also to be obeyed (lower speed when driving through existing work areas) ▪ Seat belts to be worn at all times when vehicles/plant mobile ▪ Drivers to be very aware of road conditions and vehicle/plant performance ▪ Drivers backing into deliver points must be directed by spotter if required. If the driver loses sight of this person, the reversing operation must be ceased until direct visual contact is regained (e.g. reversing to deliver material onto site). Be aware of pedestrians at all times ▪ Reversing alarms to be activated when reversing ▪ Orange vision alert light to be activated when accessing or leaving site from/to public roads ▪ All personnel driving or operating must be authorised and competent ▪ Vehicle/plant pre▪starts must be completed prior to start up of vehicle/plant ▪ authroised and provided site Traffic Management Plan - conveyed to work crews at Pre-start ▪ Dedicated easement access to Gas Terminal SIte (HDD01 applicbale to) ▪ Approved Traffic Mangement Plan by Stakeholder | SWMS, Prestarts, Toolboxes Nacap Safety Essential #10 Worksite Traffic Nacap Traffic Management (Construction in Public Thoroughfares) Procedure 3904-OPS-017-3 | C | 4 | M
| 12.14 | Health & Safety | Isolate work area and delineate for pedestrian and public vehicle travel | 1. Contact with pedestrians/public vehicles | Fatality, Impact on Third Party Relationship, Production Delays | ▪ Traffic control plan to be completed for works area ▪ Traffic controller in place as required ▪ Traffic devices e.g. signage etc to be in place as per traffic control plan ▪ Access and egress to site for construction vehicles planned ▪ Entry points to be closed off at all times when not in use ▪ Mandatory construction signage in place at compounds e.g. Construction Site – Authorised persons only etc | SWMS, Prestarts, Toolboxes Nacap Safety Essential #10 Worksite Traffic Nacap Traffic Management (Construction in Public Thoroughfares) Procedure 3904-OPS-017-3 | C | 3 | M
HDD Operations
| 12.15 | Health & Safety | Excavate material for rig anchor (if applicable), entry, exit, return and spoil pits using excavator | Damage to existing property | Damage to Asset, Damage to Property/Equipment, Impact on Third Party Relationship | Dilapidation survey to be completed where necessary before wok commence Applicable Management Plans Approved prior to commencement of works | SWMS, Prestarts, Toolboxes Nacap Safety Essential #7 Safe Working With Electricity Essential #9 Foreign Services Safety Essential #2 Excavation | D | 3 | M
|  |  |  | Contact with underground services | Damage to Asset, Impact on Third Party Relationship, Loss of Production | ▪ Verify location of all underground services (Dial before you dig etc) before commencing excavation ▪ Ensure Permit to Dig completed before commencing work (emergency procedures to be highlighted) ▪ DBYD and excavation permit to remain onsite at all times |  | C | 3 | M
|  |  |  | Contact with overhead services | Damage to Asset, Damage to Property/Equipment, Loss of Production | ▪ Authorised person/spotter with audible warning device to be in place if plant boom is likely to go within the 3m restricted zone ▪ Overhead Lines crossing work area laterally are to be marked on ground with paint or other warning devices and spotter to be in place 6 metres prior to line and remain in place till 6 metres clear of line ▪ If required, the electrical spotter to wear orange hard hat and orange vest. Spotter to have UHF, whistle and have visual at all times with the operator ▪ No loading or unloading of machines directly under power lines. No stockpile of spoil or equipment under power lines. |  | C | 3 | M
|  |  |  | Personnel struck by plant | Fatality | ▪ Reversing alarms to be installed and working on major plant ▪ Restrict access to area to be excavated to key personnel only ▪ Operators to be aware of location of all personnel ▪ All personnel to wear hard hat, steel cap boots, long sleeve shirt and pants, gloves, ear protection and protective glasses ▪ Safety pin to be in bucket assembly to prevent loss of bucket (Quick HItch in lock position) ▪ All personnel to observe the 3 metre rule when working around plant ▪ Ensure excavators are operated by certified and competent operators, only ticketed and experienced operators will be allowed to operate plant and equipment Nacap SPIN Program ▪ NO use of mobile devices during any plant operations and activities (exclcuding UHF radios, as applicable) |  | C | 3 | M
|  |  |  | Plant collisions | Damage to Property/Equipment | ▪ Operators advised on dangers of major plant working in the same area ▪ Reversing alarms to be activated |  | D | 3 | M
|  |  |  | Cave in of trench | Environmental Impact, Production Delays | ▪ Authorised personnel only in area ▪ Nominated competent person to inspect and assess ground conditions before trench is entered. ▪ Shore, bench and batter as required. As a minimum, excavations below 1.2m require benching require 1 vertical to 1 horizontal or battering of 1:1 or a combination of both ▪ Excavated spoil to be placed so that there is no likelihood of it falling to excavated area i.e. 600mm away ▪ Heavy machinery to be kept away from the top of excavated surfaces to avoid slope failure ▪ On the working side of the open trench greater than 1.2m deep a 2metre exclusion zone must be maintained for personnel at all times. All plant and equipment must maintain the two metres from the edge of the working side of the trench at all times. On the spoil side of the trench (when stockpiling near trench) a 1 metre exclusion zone must be maintained at all times. Excavator operators must ensure that no loose rock or any spoil breaches the 1 metre ▪ Excavation Permit in place prior to excavation commencement |  | D | 3 | M
|  |  |  | Environmental impact | Environmental Impact | ▪ Sediment fence to be erected and maintained as required ▪ If identified as acid sulphate soil, precautions to be taken to mitigate risk e.g. bund area and treated with agricultural lime to ensure ph is maintained within specified range. Testing to be undertaken ▪ All vehicles and plant to be effectively maintained and in serviceable condition ▪ Vehicles to only use public roads, pipeline ROW or approved access tracks ▪ All vehicles and plant must be weed and seed inspected prior to mobilisation to site ▪ A high quality of housekeeping must be maintained on▪site ▪ Transport, storage and disposal of wastes must only be conducted by a licensed contractor to a licensed facility where necessary ▪ All equipment maintenance and cleaning will be carried out within a bunded area, at least 10m from drainage lines, to ensure soil and water contamination does not occur ▪ All refuelling is to be conducted a minimum of 10m from any drainage lines or watercourse where applicable ▪ In the event of a chemical/fuel spill report immediately to NACAP. Containment and clean up action will be undertaken immediately with all contaminated waste disposed of by a licensed contractor |  | D | 3 | M
|  |  |  | Community Complaints | Impact on Third Party Relationship, Production Delays | ▪ Confirm the Managing Contractor has consulted with the local community ▪ Consult with local property owners in respect to access provisions ▪ Housekeeping on and around site to be maintained (includes temporary signage, barriers etc.) |  | D | 4 | L
|  |  |  | Security | Impact on Third Party Relationship, Loss of Production, Security Breach | ▪ All personnel onsite are to be inducted by NACAP prior to commencing works onsite |  | D | 4 | L
| 12.16 | Health & Safety | Set up site | Heavy machinery/ Truck movement on site | Fatality, Damage to Property/Equipment | ▪ Reversing beepers installed in most vehicles ▪ Spotters utilised when applicable ▪ Clear communication between crew members ▪ Visitors inducted onto site, site rules communicated | SWMS, Prestarts, Toolboxes Nacap Safety Essential #14 Emeregency Preparedness and Response | C | 3 | M
|  |  |  | Movement/ lifting of heavy loads | Fatality, Damage to Property/Equipment | ▪ Clear communication with all stakeholders ▪ Rated equipment used for task (incl. excavator, forklift, hook, chain, lifting chain) ▪ Competent operator conducting task ▪ Path clear of obstructions ▪ Ground conditions allow movement of loads |  | C | 4 | M
|  |  |  | Uneven ground | Lost Time Injury | ▪ Ground inspected prior to conducting tasks ▪ Spotter utilised when applicable ▪ PPE, including boots that provide ankle support |  | D | 3 | M
|  |  |  | Emergency occurring | Medical Treatment Injury | ▪ Emergency Preparedness, incl. pre spud/ emergency drill, ▪ Muster point established, ▪ First Aider available on site, safety critical equipment available on site and inspected |  | D | 4 | L
|  |  |  | Manual handling | Lost Time Injury | ▪ As per Material and Manual handling procedure ▪ Mechanical aids utilised when required ▪ PPE, including gloves and steel capped boots |  | C | 4 | M
|  |  |  | Excavation on site | Lost Time Injury | ▪ Excavation conducted by a competent person, enquiring about underground services, (dbyd, permit) prior to excavation being carried out ▪ Excavations fenced off appropriately as to avoid wildlife or people falling into excavations ▪ All known undergorund services to be positivley identified prior to ground breaking activities |  | D | 3 | M
| 12.17 | Health & Safety | Hot Works | Explosion, Fire, Burns and personal injury Unmaintained equipment | Lost Time Injury | ▪ Works in open well ventilated areas with easy access to fire extinguishing equipment. ▪ Additional PPE including: Double Eye Protection, Welding Jacket or apron. ▪ Regular checks of welding and cutting equipment hose and gas components ▪ Hot Works Permit in place | SWMS, Prestarts, Toolboxes | D | 4 | L
| 12.18 | Health & Safety | Confined Spaces | Overcome by toxic gases | Fatality | ▪ Gas detection set up if gas presence is likely ▪ Risk Assessment conducted prior to entry ▪ Spotter in place ▪ Potentially dangerous energy sources isolated and locked prior to entry ▪ Rescue plan developed prior to entry | SWMS, Prestarts, Toolboxes Nacap Confined Space Entry Procedure 3904-OPS-019-3 | D | 4 | L
|  |  |  | Entrapment in confined space | Fatality | ▪ Risk Assessment conducted prior to entry ▪ Spotter in place ▪ Potentially dangerous energy sources isolated and locked prior to entry ▪ Rescue plan developed prior to entry |  | D | 4 | L
| 12.19 | Health & Safety | Tool Up | Manual Handling | Lost Time Injury, Medical Treatment Injury, First Aid Injury, Permanent Disability | ▪ Use mechanical lifting aids ▪ All employees and contractors to attend crew prestart and sign document. SWMS and prestart to document controls and hazards of manual handling tasks | SWMS, Prestarts, Toolboxes | C | 4 | M
| 12.2 | Health & Safety | Mix Drilling Fluid | Incorrect procedures used when handling hazardous products | Medical Treatment Injury | Select experienced personnel for the task ensure they have read the SDS (and is availble onsite) and the appropriate PPE is used | SWMS, Prestarts, Toolboxes Safety Essential #12 | C | 4 | M
|  |  |  | Incorrect disposal of hazardous products impacting on the environment | Environmental Impact | Ensure all workers are aware of disposal methods for all waste |  | C | 4 | M
|  |  |  | Workers do not know where documentation is located | Lost Time Injury | All personnel are to be site inducted regarding the location of SDS and appropriate PPE |  | D | 4 | L
| 12.21 | Health & Safety | Vacuum Truck / Trailer Operations | Vacuum hose/ suction causing injury or damage to equipment | Lost Time Injury, Damage to Property/Equipment | ▪ Equipment inspected prior to operation ▪ Competent operator operating vacuum hose/ unit ▪ Vacuum hose never to be aimed at people/ animals | SWMS, Prestarts, Toolboxes | D | 4 | L
|  |  |  | Rotating parts/ crush injuries | Lost Time Injury | ▪ Ensure all guarding in place ▪ Body parts kept well away from rotating parts |  | C | 3 | M
|  |  |  | Reversing trailer/ site traffic | Lost Time Injury, Damage to Property/Equipment | ▪ Spotter utilised when applicable ▪ Clear communication between site staff |  | C | 4 | M
|  |  |  | Equipment damage | Lost Time Injury, Damage to Property/Equipment | ▪ Pre Start inspection conducted on vacuum unit prior to start up ▪ Damage during operation reported to supervisor for rectification |  | C | 4 | M
| 12.22 | Health & Safety | Poly welding of mud return line | Crush/ Pinch/cuts | Lost Time Injury | ▪ PPE to include gloves, safety glasses ▪ Positive communication ▪ Only use fixed controls to operate unit ▪ Refer to Poly Welder Risk Assessment ▪ Poly welder set up on level and stable ground and apply wheel brake and/or chock wheels to eliminate uncontrolled movement. | SWMS, Prestarts, Toolboxes | C | 3 | M
|  |  |  | Electrical | Fatality | ▪ Pre Start inspection completed on equipment ▪ RCD Protected circuit |  | D | 4 | L
|  |  |  | Chemical (burns, ingestion, inhalation) | Lost Time Injury | ▪ SDS available at point of use and all operators made aware of the MSDS recommendations regarding handling of the chemicals used. ▪ Operators to wear PPE in accordance with SDS (including gloves and protective eyewear). ▪ Ensure area is well ventilated and chemical cannot be inhaled or ingested. ▪ First AId - inclduing eye wash / saline bottles available |  | D | 4 | L
|  |  |  | Slips, trips and falls | Lost Time Injury | ▪ Housekeeping requirements adhered to ▪ PPE to include steel capped bots |  | C | 3 | M
|  |  |  | Burns | Lost Time Injury | ▪ PPE to include gloves, long sleeved, cotton shirts, long work trousers ▪ Contact with heat generating parts to be avoided |  | D | 3 | M
|  |  |  | Hydraulic pressure | Damage to Property/Equipment, Environmental Impact | ▪ Preventative maintenance schedule on all lines, hoses and pipes. ▪ Advise operator and maintenance staff of the pressure the lines, pipes and hoses are under. ▪ Implementation of tag-out procedures, ▪ Completion of SWMS’s prior to any potentially hazardous activity. ▪ Employ correct manual handling techniques when moving Poly welder. |  | C | 3 | M
| 12.23 | Health & Safety | Install mud return Line | Equipment damage/ uncontrolled movement of pipeline | Lost Time Injury, Damage to Property/Equipment, Environmental Impact | ▪ Install pulling head to move mud return line across the Right of Way ▪ Rated equipment used to pull return line through Right of Way, utilising excavator or similar. ▪ Push/ pull method used (excavator or similar) to finalise installation of return line, utilising tagline or similar to steer return line into space. | SWMS, Prestarts, Toolboxes | D | 3 | M
| 12.24 | Health & Safety | Install surface coil for steering | Manual handling | Lost Time Injury | ▪ PPE to include gloves, steel capped boots and safety glasses ▪ Mechanical aids or team lifting prefered method of handling items | SWMS, Prestarts, Toolboxes | D | 3 | M
|  |  |  | Pinch points/ slips, trips, falls | Lost Time Injury | ▪ PPE to include gloves, steel capped boots and safety glasses |  | D | 4 | L
|  |  |  | Obstacles between rig- and pipe side (incl. road traffic, water traffic, wide water streams etc.) | Lost Time Injury, Damage to Property/Equipment | ▪ Assessment of the location to be conducted and appropriate controls to be implemented on site ▪ Competent person to undertake assessment. |  | D | 3 | M
| 12.25 | Health & Safety | Drilling the pilot hole | Bad Ground/Loss of drilling fluid | Environmental Impact | ▪ Stop drilling and assess the situation | SWMS, Prestarts, Toolboxes | C | 4 | M
|  |  |  | Fluid Loss/Frac-out/spill | Environmental Impact | ▪ Earth bund to confirm ▪ Monitoring of bore line |  | C | 3 | M
|  |  |  | Failure of fluid line/ Environment Damage | Environmental Impact | Inspect lines before use, ensure adequate slit fencing earth bund |  | C | 3 | M
|  |  |  | Drill Pipe failure/ Equipment damage and equipment failure | Lost Time Injury, Environmental Impact | Use only premium grade pipe. Inspect pipe before use for visible signs of wear |  | C | 3 | M
|  |  |  | Trip out drill rods/ Struck by drill rod | Lost Time Injury | Keep clear of drill pipe being removed from rig |  | D | 4 | L
|  |  |  | Over Head Power lines | Fatality | ▪ Authorised person/spotter with audible warning device to be in place if plant boom is likely to go within the 3m restricted zone ▪ Overhead Lines crossing work area laterally are to be marked on ground with paint or other warning devices and spotter to be in place 6 metres prior to line and remain in place till 6 metres clear of line ▪ If required, the electrical spotter to wear orange had hat and orange vest. Spotter to have UHF, whistle and have visual at all times with the operator ▪ No loading or unloading of machines directly under power lines. No stockpile of spoil or equipment under power lines |  | C | 4 | M
|  |  |  | Wrong locating of drill string | Environmental Impact, Impact on Third Party Relationship, Loss of Production | ▪ Locating as per Drilling Operations Procedure, with calibrated equipment, by a competent person |  | D | 4 | L
|  |  |  | Impact of unknown buried service |  |  |  | D | 4 | L
| 15.25 | Health & Safety | Changing rods | Rods moving uncontrollably, damaging equipment or injuring personnel | Lost Time Injury, Damage to Property/Equipment | ▪ Tag line or similar to be used to control rods when suspended ▪ Lifting device, e.g. pipe handler, sling to be sufficiently rated for lift to be undertaken. ▪ Competent staff to undertake task ▪ Rods guided into position by experienced staff. Having clear communication with pipe handler operator and other team members if applicable. | SWMS, Prestarts, Toolboxes Safety Essential #6 Lifting Equipment | C | 4 | M
|  |  |  | Lifting devices failing | Lost Time Injury | ▪ Lifting device, including excavator, hook, chains, shackles to be sufficiently rated for lift to be undertaken and tagged quartly as required ▪ Pre Start undertaken on lifting equipment prior to undertaking task ▪ Exclusion zone to be established for non-essential personnel ▪ burst protection on hydraulic lines where excavator is used for lifting |  | D | 3 | M
|  |  |  | Suspended load | Lost Time Injury | ▪ No person to be located under suspended load! ▪ Tag line or similar to be used to control rods when suspended |  | D | 4 | L
|  |  |  | Site traffic interaction | Fatality | ▪ Reversing beepers installed in most vehicles ▪ Spotters utilised when applicable ▪ Clear communication between crew members ▪ Visitors inducted onto site, site rules communicated ▪ Traffic management plan in place |  | D | 3 | M
| 12.26 | Health & Safety | Reaming | Tooling up/personnel injury/equipment damage | Lost Time Injury, Damage to Property/Equipment | ▪ Competent personnel to undertake task ▪ Mechanical aids or team lift preferred method of manually handling items ▪ Non-essential personnel cleared from area | SWMS, Prestarts, Toolboxes | C | 4 | M
|  |  |  | Controlling tail string personnel injury/equipment damage | Lost Time Injury, Damage to Property/Equipment | ▪ Competent personnel to undertake task ▪ Mechanical aids or team lift preferred method of manually handling items ▪ Non-essential personnel cleared from area ▪ Barricading/ fencing to be erected if required |  | C | 4 | M
|  |  |  | Breaking out tail string | Lost Time Injury | ▪ Competent personnel to undertake task ▪ Mechanical aids or team lift preferred method of manually handling items ▪ Non-essential personnel cleared from area |  | D | 4 | L
|  |  |  | Removing reamers | Lost Time Injury, Damage to Property/Equipment | ▪ Competent personnel to undertake task ▪ Mechanical aids or team lift preferred method of manually handling items ▪ Non-essential personnel cleared from area |  | C | 4 | M
|  |  |  | Loading and unloading drill rods beneath overhead power lines | Fatality, Damage to Asset, Damage to Property/Equipment, Impact on Third Party Relationship, Loss of Production | ▪ Authorised person/spotter with audible warning device to be in place if plant boom is likely to go within the 3m restricted zone ▪ Overhead lines crossing work area laterally are to be marked on ground with paint or other warning devices and spotter to be in place 6 metres prior to line and remain the place till 6 metres clear of line ▪ Tag lines used to control loads ▪ If required, the electrical spotter to wear orange hard hat and orange vest. Spotter to have UHF, whistle and have visual at all times with the operator ▪ No loading or unloading of machines directly under power lines. No stockpile of spoil or equipment under power lines ▪ Only competent and licensed dogman/rigger to performing lifting duties and perform daily inspection of all lifting gear prior to use and document ▪ A lifting register must be maintain for all lifting equipment by rigger or dogman |  | C | 3 | M
| 12.27 | Health & Safety | Pipe pull back | Connecting swivel to pulling head/personnel injury | Lost Time Injury | Use only qualified personnel. Maintain good communication | SWMS, Prestarts, Toolboxes | D | 3 | M
| 12.28 | Health & Safety | Site clean-up and demobilisation | Personnel struck by plant (includes general public) | Fatality | ▪ Reversing alarms to be installed and working on major plant ▪ Restrict access to area to be reinstated to involved personnel only ▪ Operators to be aware of location of all personnel ▪ All personnel to wear hard hat, steel cap boots, long sleeve shirt and pants, ear protection and protective glasses | SWMS, Prestarts, Toolboxes | C | 4 | M
|  |  |  | Plant collisions | Lost Time Injury, Damage to Property/Equipment | ▪ Operators advised on dangers of major plant working in the same area ▪ Reversing alarms to be activated ▪ Spotter to direct the reversing of trucks ▪ Relevant traffic control plans must be in place and approved |  | C | 3 | M
|  |  |  | Contact with overhead power lines | Fatality, Damage to Asset, Damage to Property/Equipment, Impact on Third Party Relationship | ▪ Truck Drivers to be made aware of location of overhead power lines ▪ Authorised person/spotter with audible warning device to be in place if plant boom is likely to go within the 3m restricted zone ▪ Overhead lines crossing work area laterally are to be marked on ground with paint or other warning devices and spotter to be in place 6 metres prior to line and remain in place till 6 metres clear of line ▪ If required, the electrical spotter to wear orange hard hat and orange vest. Spotter to have UHF, whistle and have visual at all times with the operator ▪ No loading or unloading of machines directly under power lines. No stockpile of spoil or equipment under power lines |  | D | 4 | L
| 12.29 | Health & Safety | Remove mud return line | Clean out mud return line / pressurized air/ chemicals | Lost Time Injury, Environmental Impact | ▪ Remaining fluid cleared out of return line using foam and pressurized air ▪ Positive communication ▪ Personnel cleared from exit side of return line ▪ Non-essential personnel cleared from area | SWMS, Prestarts, Toolboxes | C | 4 | M
|  |  |  | Pulling return line onto Right of Way | Lost Time Injury, Damage to Property/Equipment | ▪ Rated equipment used to pull return line onto right of way to avoid equipment damage ▪ Positive communication on/ between rig and pipe side ▪ Path of return line cleared from obstacles |  | D | 3 | M
|  |  |  | Laceration/ personnel injury cutting return line | Lost Time Injury | ▪ Return line cut in approx. 12 metre length by competent operator ▪ PPE to include gloves, eye protection and ▪ Additional controls as per tool used (e.g. handsaw etc.) ▪ Manual aids/ team lift preferred method of handling items |  | C | 3 | M
Environmental
| 12.3 | Environment | Erosion, Sediment and Drainage | Movement of soil off site and erosion/riling on site leading to topsoil loss/degradation and increased turbidity in water catchments | Environmental Impact, Erosion and Heavy Dust | ▪ Site vehicles are restricted to defined roadways and designated access tracks/paths wherever possible to prevent unnecessary destabilisation of surfaces ▪ Maintain clean roadways wherever possible, particularly at site entry/exit points. Any material that is tracked onto a sealed public road is cleaned using a sweeper or similar device | SWMS, Prestarts, Toolboxes, CEMP | C | 4 | M
| 12.31 | Environment | Vegetation Management | Native vegetation destruction/loss of habitat/loss of protected flora | Environmental Impact | ▪ Only authorised and approved areas to be disturbed/cleared for construction related purposes are to be clearly marked and delineated (using flagging tape, markers, pegs) in accordance with site alignment sheets, drawings and GIS data ▪ Protected vegetation is not damaged or disturbed and is to be clearly marked/flagged in the field ▪ Additional work spaces or alignment changes (areas located outside of the original alignment) will require additional approval | SWMS, Prestarts, Toolboxes, CEMP | D | 4 | L
| 12.32 | Environment | Historical Heritage Management | Protected areas and artifact damage and destruction | Environmental Impact | ▪ Only authorised and approved areas to be disturbed/cleared for construction related purposes are to be clearly marked and delineated (using flagging tape, markers, pegs) in accordance with site alignment sheets, drawings and GIS data ▪ Heritage areas/or sites are not to be damaged or disturbed and are to be clearly marked/flagged in the field ▪ Additional work spaces or alignment changes (areas located outside of the original alignment) will require additional approval | SWMS, Prestarts, Toolboxes, CEMP | D | 4 | L
| 12.33 | Environment | Air Quality | Air pollution and Dust generation | Environmental Impact, Erosion and Heavy Dust | ▪ Dust suppression is to be implemented where dust is generated and when required – ie use of water cart ▪ Reduce and maintain speeds in accordance with site speed signage in order to minimize dust generation. ▪ Clearing of spillages from side rails, tail gates and draw bars of vehicles prior to leaving site | SWMS, Prestarts, Toolboxes, CEMP | D | 4 | L
| 12.34 | Environment | Noise Management | Elevated noise impacts | Community Complaints, Environmental Impact | ▪ All survey activities are generated within approved allocated hours, 0600 – 1800HRS. Approval required from the primary contractor Site Superintendent for any survey works proposed to be performed outside of standard operating hours ▪ Adherence to prescribed speed limits in accordance with site signage ▪ Vehicles are frequently maintained and serviced to ensure noise levels associated with the operation are minimal ▪ Any excessively noisy vehicle is to be reported to supervisor to organise a check to be conducted by Plant Maintenance team. ▪ All noise complaints are reported to the supervisor | SWMS, Prestarts, Toolboxes, CEMP | C | 4 | M
| 12.35 | Environment | Heat/ sun Management | Dehydration, heat illness, cancer | Medical Treatment Injury | ▪ Fluid intake to be sufficient for perspiration ▪ Shade available if required ▪ PPE, including hard hat with brim or full brim hard hat, sun screen, long shirt and pants worn on all sites ▪ Task alternation considered in some conditions | SWMS, Prestarts, Toolboxes, CEMP | C | 4 | M
| 12.36 | Environment | Pest and Weed Management | Contamination and spread of weeds/seeds to surrounding RoW due to lack of decontamination procedures | Environmental Impact | ▪ Only authorised entry/exit points and associated access tracks/areas are to be travelled in accordance with landowner requirements ▪ Vehicles are to meet all specific landowner weed/seed decontamination requirements prior to entry, i.e. be washed & certified clean on entry and have a current weed seed certificate ▪ Only Competent weed and seed inspectors are to issue weed hygiene certificates. Weed hygiene certificates must be kept in the vehicle at all times ▪ Declared plants and significant weeds are flagged/marked with flagging tape in the field (In accordance with the primary contractor Ecologist/Botanist survey and pegging party walkthrough) | SWMS, Prestarts, Toolboxes, CEMP | C | 4 | M
| 12.37 | Environment | Fauna Management | Fauna Injury/Death/Sickness | Environmental Impact | ▪ Fauna habitat is not damaged or disturbed and are clearly marked/flagged in the field (in accordance with the primary contractor Ecologist/Botanist/Fauna Spotter survey & pegging party walkthrough) ▪ Contact the Nacap Supervisor and Drilling Subcontractor for any fauna that requires relocation or is considered to be sick or injured ▪ Use of a licensed fauna spotter/catcher during all fauna handling and relocations ▪ Reduce speed and adhere to speed signage posted on site ▪ No hunting equipment, traps and finishing activities are permitted ▪ No gathering and collection of native fauna permitted | SWMS, Prestarts, Toolboxes, CEMP | C | 4 | M
| 12.38 | Environment | Livestock Management | Livestock disturbance/Injury/Death/Sickness | Community Complaints, Environmental Impact, Impact on Third Party Relationship | ▪ Give way to livestock at all times and minimizing speeds in accordance with site signage. ▪ No feeding, handling or disturbance to any livestock. ▪ Property fences and gates are maintained in accordance with landowner requirements.. ▪ Vehicles, machinery adhere strictly to designated and approved access points, paths/areas and boundary limits. ▪ No toxic edible material is to be used during survey and instead is to be replaced with biodegradable/non toxic materials – ie biodegradable flagging tape. | SWMS, Prestarts, Toolboxes, CEMP | C | 4 | M
| 12.39 | Environment | Waste Management | Inappropriate waste segregation/waste contamination | Community Complaints, Environmental Impact | ▪ All areas are to be maintained in an orderly and hygienic standard. Strict no littering and burning policy at all times. ▪ All waste materials associated with the works are to be disposed of appropriately - No waste is to be disposed and buried on site . ▪ Tracking of waste required in NSW. | SWMS, Prestarts, Toolboxes, CEMP | D | 4 | L
| 12.4 | Environment | Fuel, Chemicals and Dangerous Goods Management | Spill release to land and water resulting in contamination, explosions/combustion due to unacceptable storage | Community Complaints, Environmental Impact, Impact on Third Party Relationship | ▪ SDS’s are kept on site and are available at all times for all dangerous and hazardous materials used - i.e. spray paint for marking. ▪ All chemicals are stored in an upright position, bunded and appropriately stored. ▪ All chemicals are to be returned to the designated storage area following completion of each shift. ▪ All refuelling activities at fixed and mobile locations are to have adequate containment measures (i.e. drip trays) in place to capture any spillages during refuelling. | SWMS, Prestarts, Toolboxes, CEMP | C | 3 | M
| 12.41 | Environment | Spills Management | Contaminated Land- Spill or release of hydrocarbon contaminants due to plant failure / accident (e.g. breakage of hydraulic hose), exposes personnel and environment. | Community Complaints, Environmental Impact, Impact on Third Party Relationship | ▪ Vehicle mounted spill kits are to be serviceable and available. Spill kits to be of adequate size and type. ▪ All spills are contained, absorbed and cleaned up using absorbent pads/ecosweep absorbent located in the spill kits. Refer to SDS if needed for further information. ▪ Following containment, place all contaminated spill response materials (ie pads/ecosweep) into a plastic sealed waste bag and place bag of waste into the oily waste spill kit bin. ▪ All spills are to be reported to the direct supervisor and HSEQ department as they occur. ▪ Spill kits are to be restocked immediately following use. | SWMS, Prestarts, Toolboxes, CEMP | C | 3 | M
| 12.42 | Environment | Bushfire Management | Ignition to surrounding vegetated areas and impact to employees/general public | Community Complaints, Environmental Impact, Impact on Third Party Relationship | ▪ Open fires are banned. ▪ Cigarette butts are not to be thrown at all into any area and are to be collected and disposed appropriately. ▪ All vehicles are equipped with a portable fire extinguisher. ▪ Undertake regular maintenance and inspection of vehicles. ▪ Report all fires to Supervisor/Contact 000 if required. | SWMS, Prestarts, Toolboxes, CEMP | D | 4 | L

## 18.0 FOC Installation (hidden)
18.0 FOC Installation
IDENTIFY THE TASK or PROCEDURE, DESCRIBE THE HAZARDS AND RISKS, LIST THE CONSEQUENCES AND WHAT ARE THE EXISTING CONTROLS. | [5 empty] | EXISTING RISK |  |  | Recommendations | Responsibility | RISIDUAL RISK |  |  | STATUS | DATE Closed | TARGET LEVEL OF RISK |  | DATE RISK ADDED
ID | TASK or PROCEDURE What are the Job Steps | HAZARDS and RISKS What are they | CONSEQUENCES Resulting in | EXISTING CONTROLS | Consultation Method | Consequence | Likelihood | Level Of Risk |  |  | Consequence | Likelihood | Level Of Risk |  |  |  | RISK REVIEW DATE
18.1 | Prestart checks of equipment | 1. Slips, trips, fall when checking oils, fluids and greasing. Slippery surfaces ( dust, wet) | Medical Treatment Injury | 1. Clean surfaces of excessive dust / dirt: - 3 points of contact when climbing access steps. - Clean steps and platforms. | SWMS, SDS Prestart Checklists, VOC, PHA, Prestarts, Toolboxes. | D | 4 | L | [7 empty] | Low
|  | 2. Exposure to Dangerous Goods / Hazardous Substances | First Aid Injury, Allergic Reaction, Burns to skin, Respiratory Issues | 2. Review SDS , handle, store Dangerous Goods / Hazardous substances and wear PPE in accordance with SDS. |  | E | 4 | L | [7 empty] | Low
|  | 3. Oil and Fuel leaks | Environmental Impact, Spill | 3. Contact fitter, contain leaks with spill kit advise LECH of all spills, park vehicle 100m from a watercourse. |  | E | 3 | L | [7 empty] | Low
|  | 4. Wildlife ( snakes) | First Aid Injury, Wildlife Injury/Fatality | 4. Call fauna handler if snake spotted on machine or near machine. |  | E | 3 | L | [7 empty] | Low
|  | 5. Ground conditions – uneven ground | First Aid Injury | 5. Check for any obstacles or potholes when walking around machine. |  | E | 4 | L | [7 empty] | Low
|  | 6. Damaged/dangerous equipment – guards / handrails / E-stop / lights, Electrocution from generators, etc. | Medical Treatment Injury | 6. Prestart log book to be completed daily, PHA to be read by operator and signed. Competent operator to conduct checks. LOTO and report unsuitable equipment. Electrical Test and Tag, RCD operational. |  | D | 4 | L | [7 empty] | Low
|  | 7. Other vehicles driving through work area – no call up | Damage to Property/Equipment, Impact on Third Party Relationship, Vehicle Incident | 7. Operator ID Magnets placed on each machine with UHF Channel displayed. |  | E | 3 | L | [7 empty] | Low
|  | 8. Inadequate firefighting equipment | Damage to Property/Equipment, Environmental Impact, Fire, Impact on Third Party Relationship | 8. Ensue firefighting equipment is adequate i.e. 9kg extinguishers, knapsacks in good condition. |  | E | 3 | L | [7 empty] | Low
|  | 9. Untrained / inexperienced operators. | First Aid Injury, Lack of Attention - Error, Production Delays | 9. Only qualified , VOC’d and supervisor approved operators to inspect and operate any machines. |  | E | 4 | L | [7 empty] | Low
18.2 | Install FOC Conduit / pits and CP posts | 1. Tangled in Spool head, strains / sprains, Struck by conduit | Medical Treatment Injury | 1. Spool to be set up on spool correctly and inspected by driver | SWMS, Lift Plan, VOC, Prestarts, Toolboxes. | D | 5 | L
|  | 2. Dropping spool when loading | Medical Treatment Injury | 2. Lift plan completed, dogman VOC'd, check lifting gear |  | D | 5 | L
|  | 3. Falling in trench | Medical Treatment Injury | 3. Visual inspect travel path, housekeeping |  | D | 5 | L
|  | 4. Poor communication with driver, Plant and people interaction | Medical Treatment Injury, Damage to Property/Equipment, Vehicle Incident | 4. Radio communication and maintain visual contact |  | D | 4 | L
|  | 5. Cuts | First Aid Injury | 5. Use correct tools – conduit cutters and hole saw, PPE |  | E | 5 | L
|  | 6. Conduit installed in incorrect position. | First Aid Injury | 6. Use of appropriate tools for repositioning conduit. |  | E | 5 | L | Consider design of mobile cage to go over top of trench. | Nacap | E | 5 | L | Closed | 2015-04-01
18.3 | Testing Conduit | 1. Noise. | Permanent Disability | 1. Hearing protection. | SWMS, VOC, Prestarts, Toolboxes. | B | 4 | M
|  | 2. Damaged hoses clamp. | Damage to Pipe , Damage to Property/Equipment | 2. Inspect hoses and fittings. |  | E | 4 | L
|  | 3. Struck by hose. | Medical Treatment Injury | 3. Pins, whip-checks. |  | D | 5 | L
|  | 4. Compressed air – dust / eye injuries, airborne debris. | Lost Time Injury | 4. Do not blow / dust off with compressed air, eye protection, PIG catcher on end of conduit. |  | C | 5 | L | [7 empty] | Low
18.4 | Trailer check | 1. Pinch points | First Aid Injury | 1. Keep hands and body parts clear of pinch points | SWMS, Prestarts, Toolboxes, | D | 5 | L | [7 empty] | Low
|  | 2. Trailer rolling onto personnel or vehicle | Medical Treatment Injury, Damage to Property/Equipment | 2. Good communication and clear line of sight with driver. Keep personnel clear of backing vehicle. |  | D | 5 | L
|  | 3. Not hitched properly | Medical Treatment Injury, Collision, Damage to Property/Equipment, Vehicle Incident | 3. Trailer hitch to be locked in place, chains attached, test manually |  | B | 4 | M
|  | 4. Conduit tangled on cradle | Damage to Property/Equipment | 4. Ensure conduit is not caught and stored correctly |  | E | 5 | L
|  | 5. Obscured vision when aligning trailer to tow bar | First Aid Injury, Collision, Damage to Property/Equipment | 5. Ensure mirrors are clear and clean. Communicate with Spotter. |  | C | 5 | L

## 13.0 Foreign Service Crossings
13.0 Foreign Service Crossings
IDENTIFY THE TASK or PROCEDURE, DESCRIBE THE HAZARDS AND RISKS, LIST THE CONSEQUENCES AND WHAT ARE THE EXISTING CONTROLS. | [5 empty] | EXISTING RISK |  |  | Recommendations | Responsibility | RISIDUAL RISK |  |  | STATUS | DATE Closed | TARGET LEVEL OF RISK |  | DATE RISK ADDED
ID | TASK or PROCEDURE What are the Job Steps | HAZARDS and RISKS What are they | CONSEQUENCES Resulting in | EXISTING CONTROLS | Consultation Method | Consequence | Likelihood | Level Of Risk |  |  | Consequence | Likelihood | Level Of Risk |  |  |  | RISK REVIEW DATE
13.1 | Foreign Services (above and below ground) | 1. Contact with utilities services (eg overhead powerlines and underground cables or pipes | Fatality, Damage to Asset, Damage to Reputation, Project Stopped | 1. Spotter to be in place at all time when lifting pipes., Pipe to be secured correctly before lifting. Foreign Service to located and marked prior (refer to 5.0 Foreign Service Location) | Nacap Safety Essential # 7 Safe Working with Electricty and #9 Foreign Services | A | 5 | M
13.2 | Excavating Bell holes in built up area | 1. Unauthorised access by a member of the public, e.g. children, falling into bell hole, . | Fatality, Damage to Reputation, Impact on Third Party Relationship, Project Stopped | 1. Fencing of site generally, security fencing in areas deemed necessary - Jersey barriers. Minimise open excavations in the vicinity of areas with risk of public access. Signage, public/land owner consultation. | Induction, JSA, Prestart, Toolbox, Site Security Plan, Safety Essential # 2 Excavation, Traffic Management Procedure(Construction in Public Thoroughfares) 3904-OPS-017-3 | A | 5 | M | [7 empty] | Low
13.3 | Lower in Pipe | 1. Unsecured load – drop pipe | Fatality, Crush Injury, Damage to Pipe , Damage to Property/Equipment | 1. Intermediate Rigger (VOC) to control lift and sling or check load , lift plan developed, prestart meeting with crew prior to lifting, personnel to sign lift plan | Lift Plan, VOC, JSA, Prestart, Toolbox | A | 5 | M | [7 empty] | Low
|  | 2. Fall in trench – struck by pipe when lowering in pipe and repair / jeep pipe | Fatality, Crush Injury, Damage to Pipe , Damage to Property/Equipment | 2. Do not stand between pipe and trench when raised off skids to lower in, when jeeping or repairing pipe all plant to stop operators to remain in cab to support load, once jeeped or repaired personnel are not permitted to stand between pipe and trench when lowering in commences |  | A | 5 | M | [7 empty] | Low
|  | 3. Plant tip over | Fatality, Crush Injury, Damage to Pipe , Damage to Property/Equipment | 3. Check ground conditions, only plant rated for capacity of lift to be used, lift plan |  | A | 5 | M | [7 empty] | Low
|  | 4. Lack of communication when lifting and placing pipe | Fatality, Crush Injury, Damage to Pipe , Damage to Property/Equipment | 4. Intermediated rigger to supervise and coordinate lift, hand signals or radio communication to be used, operators to remain in cab |  | A | 5 | M | [7 empty] | Low
|  | 5. Electrocution when jeeping | Lost Time Injury, Burns to skin | 5. Earth cable connected to jeeper |  | C | 5 | L | [7 empty] | Low
|  | 6. Removing slings in trench > 1.5m | Fatality, Crush Injury | 6. Don not enter a trench greater than 1.5m deep, tag line to remove sling in trench greater than 1.5m deep. |  | A | 5 | M | [7 empty] | Low
13.4 | Carrying pipe for set up | 1. Machine rollover | Fatality, Damage to Pipe , Damage to Property/Equipment | 1. Seatbelts, operators not to exceed specified slope degree limitations of plant per scope of work and manufacturers specifications. | Induction, Prestart, JSA, PHA, VOC, Prestart Safety Essential #6 Lifting Equipment and #5 Mobile Crane | A | 5 | M
|  | 2. Load not tied properly/Sling breaks | Fatality, Crush Injury, Damage to Pipe , Damage to Property/Equipment | 2. Load to be slung by qualified dogman. Slings to be checked for date test and tag prior to use |  | A | 5 | M
|  | 3. Mechanical failure | Damage to Property/Equipment | 3. All machines to be inspected prior to working. |  | E | 4 | L
13.5 | Pipe stab on | 1. Pipe movement. | Medical Treatment Injury, Crush Injury, Damage to Pipe | 1. Pipe to be securely choked by dogman. | Induction, Prestart, JSA, PHA, VOC, Prestart | E | 3 | L
|  | 2. Confusion with communication. | Medical Treatment Injury, Crush Injury, Damage to Pipe , Damage to Property/Equipment | 2. Spotter required for assistance. Positive communication between truck driver and winch operator to be established prior to commencement. |  | D | 4 | L
|  | 3. Inexperienced operator. | Medical Treatment Injury, Crush Injury, Damage to Pipe , Damage to Property/Equipment | 3. Only qualified and VOC person to operate plant |  | D | 4 | L
13.6 | Weld pipe | 1. Unable to weld pipe properly. | Damage to Pipe , Loss of Production, Production Delays | 1. Cut out of slope for step so as welders can stand securely. | Induction, JSA, Prestart, Property Management Plan Nacp PTW Procedure 3904-OPS-018-3 | E | 4 | L
|  | 2. Inexperienced welder. | Permanent Disability, Burns to skin, Eye Injury, Lack of Attention - Error, Loss of Production, Rework (dig up) | 2. Only qualified welders to weld pipe. |  | E | 4 | L
|  | 3. Fire. | Environmental Impact, Fire | 3. Ensure firefighting gear is on hand, and tested. |  | E | 3 | L
|  | 4. Trench Collapse on personnel. | Fatality, Crush Injury | 4. Inspect Bell hole prior to entry. Benched, shored, battered excavation. Trench Shields if required. Minimise below ground tie-ins. ERP. |  | A | 5 | M
|  | 5. Stored Energy in pipe. | Fatality, Crush Injury | 5. Experienced personnel, stay out of the line of fire. Allow two pipe lengths (where practicable) on the incoming side of each bend. |  | A | 5 | M
|  | 6. Operator error resulting in personnel being crushed between trench wall or trench shield. | Fatality, Crush Injury, Loss of Production, Production Delays, Project Stopped | 6. Machinery holding pipe in position. Bell hole size appropriate for the works to be conducted. Personnel not to stand between pipe and pipe. Once pipe externally clamped machinery to be shutdown prior to welding being commenced. |  | A | 5 | M
|  | 7. External clamp fails. | Fatality, Crush Injury, Loss of Production, Production Delays, Project Stopped | 7. Ensure clamps are not modified and regularly inspected. |  | A | 5 | M | [7 empty] | Low
13.7 | Field Joint Coating | 1. Refer to 12.0 Grit Blasting Coating & Painting |  | 1. Refer to 12.0 Grit Blasting Coating & Painting | [11 empty] | Low
13.8 | Coating Repairs | 1. Cuts, abrasions, eye injuries from grinding / sanding with flapper disc | First Aid Injury, Eye Injury | 1. Eye protection worn, gloves , long sleeves and pants | Induction, JSA, ERP, SDS, Prestart Checks, Safety Essential #12 Hazardpus Chemicals - Storage , Handling and Use. | E | 3 | L
|  | 2. Burns or fire when preheating pipe from gas torch | First Aid Injury, Burns to skin, Environmental Impact, Fire | 2. Fire -fighting equipment available, turn off torch when not in use, housekeeping, PPE ( mandatory) |  | E | 3 | L
|  | 3. Fumes, skin irritation when handling coating chemicals | First Aid Injury, Exposure, Respiratory Issues | 3. Handling and storage of chemical in accordance with MSDS |  | E | 3 | L
13.9 | Padding and Backfill | 1. Unstable spoil pile | Damage to Pipe , Damage to Property/Equipment | 1. Spoil to be levelled prior to padding or made stable | Induction, JSA, Prestart, Property Management Plan | E | 4 | L | [7 empty] | Low
|  | 2. Trench conditions – sandy, rocky, wet , width | Damage to Pipe , Damage to Property/Equipment | 2. Competent (VOC) operator and supervisor to assess trench and soil conditions prior to backfill |  | D | 4 | L | [7 empty] | Low
|  | 3. Insufficient room to manoeuvre, Interaction with other machinery / people | Damage to Pipe , Damage to Property/Equipment, Vehicle Incident | 3. Exclusion zone established, positive communication |  | D | 4 | L | [7 empty] | Low
|  | 3, Overhead powerlines - LFI |  | 1. Earth stake to be maintained when working under overhead high voltage powerlines until pipe is tied in.
4. Falling objects from canopy
5. Burns/Radiation/Hot welding rods
6. Noxious fumes when welding
7. Moving plant from joint to joint
8. Fatigue from welding without rest breaks
9. Dust/dirt, grinding
10. Eye injury – Arc flash
11. Exposure to bad weather/lightning

## 14.0 Open Cut Road Crossings
14.0 Open Cut Road Crossings
IDENTIFY THE TASK or PROCEDURE, DESCRIBE THE HAZARDS AND RISKS, LIST THE CONSEQUENCES AND WHAT ARE THE EXISTING CONTROLS. | [5 empty] | EXISTING RISK |  |  | Recommendations | Responsibility | RISIDUAL RISK |  |  | STATUS | DATE Closed | TARGET LEVEL OF RISK |  | DATE RISK ADDED
ID | TASK or PROCEDURE What are the Job Steps | HAZARDS and RISKS What are they | CONSEQUENCES Resulting in | EXISTING CONTROLS | Consultation Method | Consequence | Likelihood | Level Of Risk |  |  | Consequence | Likelihood | Level Of Risk |  |  |  | RISK REVIEW DATE
14.1 | Foreign Services (above and below ground) | 1. Contact with utilities services (eg overhead powerlines and underground cables or pipes | Fatality, Damage to Asset, Damage to Reputation, Project Stopped | 1. Spotter to be in place at all time when lifting pipes., Pipe to be secured correctly before lifting. Foreign Service to located and marked prior (refer to 5.0 Foreign Service Location) | Nacap Safety Essential # 7 Safe Working with Electricty and #9 Foreign Services | A | 5 | M
14.2 | Bitumen and Concrete Cutting | 1. Kick Back causing injury | Permanent Disability, Medical Treatment Injury, Damage to Property/Equipment, Injury, Lack of Attention - Error | 1. Selecting equipment specifically designed for the job Carefully consulting foreign services plans to avoid embedded objects Exclusion zone established to ensure bystanders are at a safe distance from your work area All guards on the machine shall never be removed. Tag out defective items. Appropriate PPE is provided and worn Pre-start check carried out in accordance with manufacturer’s instructions. | JSA, SDS Prestart Checklists, VOC, PHA, Prestarts, Toolboxes. | E | 5 | L | [7 empty] | Low
|  | 2. Excessive Noise |  | Refer to Section 0.0 General for noise | [11 empty] | Low
14.3 | Welding and Pipe Movement / install | 1. Refer to 15.0 Foreign Service Crossings |  | 1. Refer to 13.0 Foreign Service Crossings | [11 empty] | Low
14.4 | Field Joint Coating | 1. Refer to 12.0 Grit Blasting & Coating |  | 1. Refer to 9.0 Grit Blasting & Coating | [11 empty] | Low
14.5 | Road Surface Reinstatement (concrete & asphalt) | 1. Hand and leg Injury from protruding Rebar and installation | Lost Time Injury, Crush Injury | 1. Workers cutting rebar will wear face shields, gloves, hearing protection, and hard hats. Grinder guards must be in place and fully operational prior to use. Handles to be present on all grinders regardless of size. If handle is to be remove further risk assessment and supervisor acknowledgement is required. Construction debris will be removed on a daily basis. All rebar ends shall be capped to protect workers from impalement/laceration hazards. | JSA, SDS Prestart Checklists, VOC, PHA, Prestarts, Toolboxes. Traffic Management Procedure(Construction in Public Thoroughfares) 3904-OPS-017-3 | E | 5 | L
|  | 2. Placing Concrete causing burns and access issues | Lost Time Injury, First Aid Injury | 2. Qualified traffic management to ensure a clear path to the work zone. Only the truck's operator will place the chute and run the mixer / flo con. PPE. Any excess concrete / asphalt to be removed from skin as soon as possible |  | E | 5 | L
|  | 3. Traffic - other road users impacting on worksite | Collision, Community Complaints, Damage to Property/Equipment, Impact on Third Party Relationship, Vehicle Incident | 1. Traffic control, TMP, barriers installed to delineate and fence off worksite from public |  | E | 5 | L
|  | 2. Pedestrians impacting worksite | Fatality, Lost Time Injury, Community Complaints | 2. Signage, Communication, designated walkways |  | A | 5 | M
|  | 3, Overhead powerlines - LFI |  | 1. Earth stake to be maintained when working under overhead high voltage powerlines until pipe is tied in.
4. Falling objects from canopy
5. Burns/Radiation/Hot welding rods
6. Noxious fumes when welding
7. Moving plant from joint to joint
8. Fatigue from welding without rest breaks
9. Dust/dirt, grinding
10. Eye injury – Arc flash
11. Exposure to bad weather/lightning

## 15.0 Reinstatement
15.0 Reinstatement
IDENTIFY THE TASK or PROCEDURE, DESCRIBE THE HAZARDS AND RISKS, LIST THE CONSEQUENCES AND WHAT ARE THE EXISTING CONTROLS. | [6 empty] | EXISTING RISK |  |  | Recommendations | Responsibility | RISIDUAL RISK |  |  | STATUS | DATE Closed/Sign Off
ID | TASK or PROCEDURE What are the Job Steps | HAZARDS and RISKS What are they | CONSEQUENCES Resulting in | EXISTING CONTROLS | Consultation Method | 3rd Party Liaison? | Consequence | Likelihood | Level Of Risk |  |  | Consequence | Likelihood | Level Of Risk
17.1 | Assess Worksite | 1. Foreign services | Fatality, Damage to Asset, Damage to Property/Equipment | 1. If unsure about foreign services check with your supervisor, Check alignment sheets, catenaries and signage. Permit to Work, conduits remain until permanent fencing reinstated. | Induction, Prestart, Toolboxes, JSA, VOC, TMP Nacap Safety Essential # 7 Safe Working with Electricty and #9 Foreign Services, Nacap PTW Procedure 3904-OPS-018-3 Traffic Management Procedure(Construction in Public Thoroughfares) 3904-OPS-017-3 |  | A | 5 | M
|  | 2. Damage to pipe | Damage to Pipe | 2. Avoid un-necessary travelling close to installed pipe. |  |  | D | 4 | L
|  | 3. Slippery conditions due to rain | Medical Treatment Injury, Damage to Property/Equipment, Environmental Impact | 3. Move to a dryer section. |  |  | D | 4 | L
15.1 | Kerb and Channel | 1. Finger / hand injuries | Medical Treatment Injury | 1. Trained and experienced crew engaged Mandatory PPE requirements Communication with other trades and barricading where required. Housekeeping maintained. | Induction, Prestart, Toolboxes, JSA, Lift Plans, PTW, VOC, TMP |  | C | 3 | M
|  | 2. Eye injuries - use of hammers, nips and small hand tools. | Medical Treatment Injury | 2. Trained and experienced crew engaged Mandatory PPE requirements Communication with other trades and barricading where required. Housekeeping maintained. |  |  | C | 3 | M
|  | 3. Manual handling injuries (lifting heaving equipment) | Medical Treatment Injury | 3. Team lift for heavy / awkward items. PPE including gloves (cut and puncture proof rated) to prevent splinters and lacerations. Unload supplies close to worksite to reduce carrying distance. |  |  | C | 4 | M
|  | 4. Uneven surfaces and exposed Reo bar causing injury to legs. | First Aid Injury | 1. Trained and experienced crew engaged Mandatory PPE requirements Communication with other trades and barricading where required. Housekeeping maintained. Spotter engaged as required (no person to stand behind reversing vehicle) Hold down bolts, exposed reo to be capped and monitored Agi truck fitted with reversing alarm / flashing beacon and spotter No Agi washout on site |  |  | D | 4 | L
|  | 5. Personnel in close proximity to Agi Truck movements | Fatality, Crush Injury, Damage to Property/Equipment |  |  |  | D | 5 | L
|  | 6. Chemical exposure to cement and lime based products | Burns to skin |  |  |  | C | 5 | L
15.2 | Line Marking 1. Paint handling 2. Working with machinary - trapped fingers | 1. Inhilation / airborne particles | Allergic Reaction, Environmental Impact, Lost Time Injury, Medical Treatment Injury | 1. SDS and Chemical assessment completed and available. PPE to be worn as per risk assessment. | Induction, Prestart, Toolboxes, JSA,VOC, Safety Essential #12 Hazardpus Chemicals - Storage , Handling and Use |  | D | 5 | L
|  | 2. Body Impact injuries | Lost Time Injury, First Aid Injury, Medical Treatment Injury | 2. PPE to be worn compatible with noise advice from mahine. Signage to be in place. |  |  | C | 4 | M
|  | 3. Burns to skin from product or machine | Lost Time Injury, First Aid Injury, Medical Treatment Injury | 3. PPE to be worn. Signage to be in place. Chemical asssessment to be completed. |  |  | D | 4 | L
15.3 | Topsoiling and re-seeding | 1. Heavy vehicle movement | Medical Treatment Injury, Collision, Damage to Property/Equipment, Vehicle Incident | 1. Clear communication, Have a line of sight with the operator | Induction, Prestart, Toolboxes, JSA, PTW, VOC, TMP |  | D | 4 | L
|  | 2. Dusty, slippery, soft ground | Medical Treatment Injury, Damage to Property/Equipment, Environmental Impact | 2. Move to a dryer section, Reduce speed |  |  | E | 3 | L
|  | 3. Underground services | Damage to Asset, Damage to Property/Equipment | 3. Check foreign services register, Locate trench by grading subgrade, Exclusion zones, pothole signage & conduits to remain in place. |  |  | D | 5 | L
15.4 | Asphalting | 1. Contact with bitumen based product | Permanent Disability, Medical Treatment Injury | 1. eliminate skin contact - gloves, long sleeves, trousers etc (as per SDS) 2. Use shovels | Induction, Prestart, Toolboxes, JSA, PTW, VOC, TMP |  | C | 4 | M
|  | 2. Burns from laying asphalt | Medical Treatment Injury, First Aid Injury | 3. PPE |  |  | D | 4 | L
|  | 3. Fumes from laying asphalt | First Aid Injury, Medical Treatment Injury, First Aid Injury | 4. Ensure product is at correct temperature to prevent excessive fuming |  |  | E | 4 | L
|  | 4. Use of roller/plant (overturning due to drop off) | First Aid Injury, Medical Treatment Injury, First Aid Injury | 5. VOC, trained operators, Maintain safe distance from edge of drop off (assess and communicate distance during toolbox and site risk assessment meeting), Select low amplitude, Use vibrating plate or smaller roller near drop offs, All rollers to be fitted with ROPS, Seatbelts to be worn at all times |  |  | E | 4 | L
|  | 5. Damage to underground service when using rollers | Damage to Asset | 6. Review of pipeline depths and consultation with third party owners for requirements. |  |  | B | 5 | M
15.5 | Removing Sediment Controls and Construction Rubbish/Reinstatement Prep. | 1. Slips, trips and falls | First Aid Injury | 1. Be aware, Housekeeping | Induction, Prestart, Toolboxes, JSA, PTW, TMP |  | E | 3 | L
|  | 2. Manual handling | First Aid Injury | 2. Correct PPE, Use proper lifting technique, Use mechanical assistance |  |  | E | 3 | L
|  | 3. Working around mobile plant | Fatality, Crush Injury | 3. Maintain eye contact, Communication |  |  | A | 5 | M
|  | 4. Eye injury from pressure washer | Medical Treatment Injury, Eye Injury | 4. Eye protection |  |  | E | 4 | L
3, Overhead powerlines - LFI
4. Falling objects from canopy
5. Burns/Radiation/Hot welding rods
6. Noxious fumes when welding
7. Moving plant from joint to joint
8. Fatigue from welding without rest breaks
9. Dust/dirt, grinding
10. Eye injury – Arc flash
11. Exposure to bad weather/lightning
Note on G3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is there a need to liaise with/notify client/public/other entities to implement a HIRAC process for any hazards impacting any of the parties?

## 16.0 Hydrostatic Testing
16.0 Hydrostatic Testing
IDENTIFY THE TASK or PROCEDURE, DESCRIBE THE HAZARDS AND RISKS, LIST THE CONSEQUENCES AND WHAT ARE THE EXISTING CONTROLS. | [5 empty] | EXISTING RISK |  |  | Recommendations | Responsibility | RISIDUAL RISK |  |  | STATUS | DATE Closed | TARGET LEVEL OF RISK |  | DATE RISK ADDED
ID | TASK or PROCEDURE What are the Job Steps | HAZARDS and RISKS What are they | CONSEQUENCES Resulting in | EXISTING CONTROLS | Consultation Method | Consequence | Likelihood | Level Of Risk |  |  | Consequence | Likelihood | Level Of Risk |  |  |  | RISK REVIEW DATE
18.1 | Pre- Cleaning | 1. Compressed air injury | Fatality, Damage to Property/Equipment | 1. All hoses to be tested annually, Register to be maintained, Use only experienced personal for task. | Induction, Prestart, JSA, PTW, VOC. | A | 5 | M
|  | 2. Hose failure | Fatality, Damage to Property/Equipment | 2. Whip socks/checks to be on all pressurised hoses, adequate supervision, Pre start checks on all equipment, All fittings and hoses to be rated above compressor capability, Non return valves to be fitted at pipe connection for every bull hose |  | A | 5 | M
|  | 3. Uncontrolled cleaning pig | Permanent Disability | 3. Ensure valves that are not required to be operated are isolated and tagged out, No workers in bell hole when catcher is open, launcher / catcher (clam shell pig catcher) to be constructed to enable controlled process, Establish exclusion zones as per AS2885.5 Appendix Z. |  | B | 4 | M
|  | 4. Injuries from poor manual handling practices | Medical Treatment Injury | 4. Use correct lifting methods |  | D | 4 | L
|  | 5. Break down in communications leading to dangerous situation | Injury | 5. Site radios in all vehicles to be checked prior to commencement of task, No lone work |  | D | 4 | L
|  | 6. Dust and noise | Medical Treatment Injury, Respiratory Issues | 6. All workers to stand up wind of receiver, Wear dust masks as required, Appropriate hearing protection to be selected. Receiving end to be located in appropriate location away from public where possible. |  | D | 4 | L
|  | 7. Slips, Trips and Falls | First Aid Injury | 7. Bell holes/test ends to have safe access and egress at all times. |  | E | 4 | L
18.2 | Filling and Gauging Pipe | 1. Chemical used incorrectly. | Medical Treatment Injury, Allergic Reaction, Burns to skin, Exposure | 1. Appropriate PPE selection of gloves to be available for task, Ref: to SDS. Eye station to be made available and filled, SDS to be available on site and communicated to crew. First aid on crew | Induction, Prestart, JSA, Site Security Plan | D | 4 | L
|  | 2. Falling into water source | Fatality | 2. Suitable means of accessing water source to be established, Risk assessment to be undertaken. |  | A | 5 | M
|  | 3. Fitting or hose fracture / failure. | Fatality, Damage to Property/Equipment | 3. Non return valve to be fitted on pipe side of all flexible hoses, All pipes, flanges, hoses and gaskets to be pressure rated, All equipment to be checked during use on a regular basis, ERP to be in place. |  | A | 5 | M
|  | 4. Fuel spills. | Environmental Impact, Spill | 4. All pumps bunded, Spill kits to be located at bunded areas. Specific training for personnel |  | E | 4 | L
18.3 | Hydro Test | 1. Pipe, Fitting or Hose failure | Fatality, Damage to Property/Equipment, Environmental Impact | 1. All hoses to be tested annually to test pressure plus 5000Kpa and recorded on a register, Hoses and temporary equipment to be service tested prior to operation. | Induction, Prestart, JSA | A | 5 | M
|  | 2. Pipe leaks or rupture | Fatality, Damage to Property/Equipment, Environmental Impact | 2. Emergency Response Plan, Notification, Land Liaison, JSA, quality processes complete. |  | A | 5 | M
|  | 3. Pressurised water | Medical Treatment Injury | 3. Exclusion zones to be established with barricades and signage as per test pack requirements Refer to pressure specifications, NATA representative to be in control during squeeze, All personal including 3rd parties to be notified prior to hydro test, No personnel to enter restricted area during squeeze and strength test. Overpressure protection to be addressed in JSA, Hydro checklist completed prior to pressure testing. Whip socks in place. Hydrotest Plan in place |  | D | 4 | L
|  | 4. Depressurising Hoses | Fatality, Damage to Property/Equipment, Environmental Impact | 4. Bleed down hose to be located back into break tank, Whip socks in place |  | A | 5 | M
18.4 | Dewatering pipe | 1. Pipe and fitting failure | Damage to Property/Equipment, Environmental Impact, Erosion and Heavy Dust | 1. Suitable pipe to be used between header and control valve at break tank, Exclusion zone established with warning signage as per Exclusion Zone Diagram, No lone work. | JSA | D | 4 | L
18.5 | Drying (same as cleaning) Include dew point time | 1. Compressed air injury | Fatality, Damage to Property/Equipment | 1. All hoses to be tested annually, Register to be maintained, Use only experienced personal for task. | Induction, Prestart, JSA | A | 5 | M
|  | 2. Hose failure | Fatality, Damage to Property/Equipment | 2. Whip socks/checks to be on all pressurised hoses, adequate supervision, Pre start checks on all equipment, All fittings and hoses to be rated above compressor capability, Non return valves to be fitted at pipe connection for every bull hose |  | A | 5 | M
|  | 3. Uncontrolled cleaning pig | Permanent Disability | 3. Ensure valves that are not required to be operated are isolated and tagged out, No workers in bell hole when catcher is open, Launcher / catcher to be constructed to enable controlled process, Establish exclusion zones. |  | B | 4 | M
|  | 4. Musculoskeletal injuries from poor manual handling practices | Medical Treatment Injury | 4. Assess weight of pigs prior to lifting, Use team lifting or mechanical assistance where practical. |  | D | 4 | L
|  | 5. Break down in communications | Injury | 5. Site radios in all vehicles to be checked prior to commencement of task, No lone work. |  | D | 4 | L
|  | 6. Excessive dust and noise | Medical Treatment Injury, Respiratory Issues | 6. All workers to stand up wind of receiver, Wear dust masks as required, Appropriate hearing protection to be selected. |  | D | 4 | L
|  | 7. Tips, Slips and Falls | First Aid Injury | 7. Bell holes to have safe access and egress at all times. |  | E | 4 | L
|  | 3, Overhead powerlines - LFI |  | 1. Earth stake to be maintained when working under overhead high voltage powerlines until pipe is tied in.
4. Falling objects from canopy
5. Burns/Radiation/Hot welding rods
6. Noxious fumes when welding
7. Moving plant from joint to joint
8. Fatigue from welding without rest breaks
9. Dust/dirt, grinding
10. Eye injury – Arc flash
11. Exposure to bad weather/lightning

## 17.0 CP Installation
17.0 CP Installation
IDENTIFY THE TASK or PROCEDURE, DESCRIBE THE HAZARDS AND RISKS, LIST THE CONSEQUENCES AND WHAT ARE THE EXISTING CONTROLS. | [5 empty] | EXISTING RISK |  |  | Recommendations | Responsibility | RISIDUAL RISK |  |  | STATUS | DATE Closed | TARGET LEVEL OF RISK |  | DATE RISK ADDED
ID | TASK or PROCEDURE What are the Job Steps | HAZARDS and RISKS What are they | CONSEQUENCES Resulting in | EXISTING CONTROLS | Consultation Method | Consequence | Likelihood | Level Of Risk |  |  | Consequence | Likelihood | Level Of Risk |  |  |  | RISK REVIEW DATE
24.1 | Sand Blast coating on pipe to expose steel and prepare for weld | 1. Refer: 16.0 Grit Blasting & Coating |  | 1. Refer: 16.0 Grit Blasting & Coating | [11 empty] | Low
24.2 | File smooth and wipe back with Citrus clean | 1. Contact with hazardous substances | Medical Treatment Injury | 1. SDS’s read, signed and understood. Wear all required PPE depending on work environment. | SWMS, SDS VOC, Prestarts, Toolboxes. | D | 4 | L
|  | 2. Manual Handling | Medical Treatment Injury | 2. Adopt proper manual handling practices. |  | D | 4 | L
|  | 3. Fumes | Medical Treatment Injury, Allergic Reaction, Exposure | 3. Ensure adequate ventilation or wear appropriate PPE. |  | D | 4 | L
|  | 4. Splash | First Aid Injury, Allergic Reaction, Burns to skin, Eye Injury | 4. Eye protection to be worn as per SDS. |  | E | 4 | L
24.3 | Exposing wire and wrap around pipe to weld onto CP point | 1. Cuts | First Aid Injury | 1. Use approved project knifes and cut away from the body. Ensure ribbon and wire supported. | SWMS, Prestarts, Toolboxes, Inductions | E | 4 | L
|  | 2. Manual Handling | Medical Treatment Injury | 2. Adopt proper manual handling techniques while wrapping wire around pipe. Use glove while handling materials. |  | D | 4 | L
24.4 | Load crucible with powder and feed in ribbon wire end to be welded onto the CP point | 1. Hazardous substances | First Aid Injury, Allergic Reaction, Exposure | 1. Read SDS for product prior to using. | SWMS, SDS, Prestarts, Toolboxes, Inductions | E | 4 | L | [7 empty] | Low
|  | 2. Fire | Fire | 2. Keep all ignition sources away from powder at all times. Ensure product used as instructed. |  | D | 4 | L | [7 empty] | Low
|  | 3. Explosion | Explosion | 3. Store away from work front. Only take as much as is required for the activity to the work front. All other supplies to be maintained in a safe and dry location. No ignition sources within 5m of activity. No smoking within 5m of activity. |  | D | 4 | L | [7 empty] | Low
24.5 | Fire the powder | 1. Burns. | Medical Treatment Injury, Burns to skin | 1. Do not touch weld unless cooled by water etc. Wear gloves while handling ribbon or wire. Ensure gloves worn when firing crucible. | SWMS, SDS, Prestart Checklists, Prestarts, Toolboxes, Inductions | D | 4 | L
|  | 2. UV radiation. | Medical Treatment Injury, Allergic Reaction | 2. Only pack crucible with required amount to complete weld. |  | D | 4 | L
|  | 3. Fire | Fire | 3. Do not get in close proximity to weld while firing. Do not look directly at flare while firing. |  | D | 4 | L
|  | 4. Explosion. | Explosion | 4. Keep supplies dry and away from any potential ignition sources. No smoking or ignition sources within 5m of works. Fire extinguisher to be within 10m of activity |  | D | 4 | L
|  | 5. In-complete firing | Damage to Pipe , Damage to Property/Equipment | 5. Ensure firing complete prior to releasing crucible. |  | E | 4 | L
24.6 | Test weld is holding as per quality requirements with 1kg hammer | 1. Manual handling. | Medical Treatment Injury | 1. Adopt proper manual handling techniques. | SWMS, Prestarts, Toolboxes, Inductions | D | 4 | L
|  | 2. Struck by flying particle | First Aid Injury | 2. Use prescribed weighted hammer to test security of weld to ribbon and wire as per QA specs. Keep hands away from strike zone while testing. |  | E | 4 | L

## Risk Matrix
RISK MATRIX
|  |  | COLOUR RATING | Low | Medium | High
CONSEQUENCE
|  |  | A | B | C | D | E
|  |  | Fatality or permanent disability | Long term injury or illness | Lost time injury | Restricted or alternative duties | Medical treatment or first aid
LIKELIHOOD | Probable | 1 | I | I | H | H | M
| Highly credible | 2 | I | I | H | M | M
| Credible but infrequent | 3 | H | H | M | M | L
| Unlikely | 4 | H | M | M | L | L
| Remote | 5 | M | M | L | L | L
[8 empty] | Consequence |  | Likelihood
[8 empty] | input | output | input | output
[8 empty] | A | 1 | 1 | 1
[8 empty] | B | 2 | 2 | 2
[8 empty] | C | 3 | 3 | 3
[8 empty] | D | 4 | 4 | 4
[8 empty] | E | 5 | 5 | 5

## Delegation of Authority
Approval authority and notification requirements are actions that must be closed
The HIRAC team must seek out and obtain the approval from the delegated authority and maintain a record of the approval
Likewise, a delegated approval authority is responsible for ensuring the relevant higher authority is notified of the high consequence risks

## Data (hidden)
A | 1 | Fatality | 1 | High | Open
B | 2 | Permanent Disability | 2 | Medium | Closed
C | 3 | Lost Time Injury | 3 | Low
D | 4 | Medical Treatment Injury
E | 5 | First Aid Injury
Allergic Reaction
Anti-social Behaviour
Burns to skin
Carcinomas
Collision
Community Complaints
Crush Injury
Damage to Asset
Damage to Pipe
Damage to Property/Equipment
Damage to Reputation
Dehydration
Disability
Environmental Impact
Erosion and Heavy Dust
Explosion
Exposure
Eye Injury
Fatigue
Fire
Flooding
Health Effects
Heat Stress/Stroke
Hyperthermia
Hypothermia
Impact on Third Party Relationship
Industrial Relations Issue
Injection Injury
Injury
Lack of Attention - Error
Loss of Production
Production Delays
Project Stopped
Property Lock Out
Respiratory Issues
Rework (dig up)
Security Breach
Spill
Stock Loss
Stress
Vehicle Incident
Wildlife Injury/Fatality
Object Across Road
Dust
Hand Injury