## Sheet1
NGR Part 10, Rule 101B 5(b) - Service and Access Information: Matters Expected to Affect Capacity
This table contain matters (projects or matinenance activities) that have the potential to affect the capacity of JGN's Large Distribution Mains. For completion, other significant projects that do not affect capacity may also be included.
Indentifier | Date From | Date to | Project Name | Asset Effected | Matters Effecting Capacity | Expected capacity reduction during the period (TJ) | Commentary | Last Updated
YY-### | Date DD/MM/YY | Date DD/MM/YY | Project Name | List one or more assets | What is causing the change to capacity or where no change to capacity | TJ (if known) | Further explanation | Date DD/MM/YY
23-001 | 2024-03-01 | 2024-04-01 | Licence 2a - Washaway Remediation & Integrity Dig | Wilton PLS / Mt Keira TRS / Wollongong PRS | In order to carry out the integrity dig and repair of the pipeline where the pipeline will be exposed, a reduction of pressure may be required to safety assess / repair the site with personnel. | 10 | Exact timing will be confirmed closer to the works and dependant on project and contractor availability. | 2023-12-21
23-002 | 2024-05-01 | 2024-10-01 | Licence 3, 7, 8a & 8b Validation Digs | Wilton to Kooragang Island TRS facilities | In order to carry out the validaiton dig and possible repairs of the pipeline where the pipeline will be exposed, a reduction of pressure may be required to safety validate / repair the site with personnel. | 30 | Exact timing will be confirmed closer to the works and dependant on project and contractor availability. | 2023-12-21
23-003 | 2024-09-01 | 31/10/24 | Licence 1 - Pigging Activities | Wilton PLS to Wollongong PRS facilities and Wilton PLS to Kooragang Island TRS facilities | The operating pipeline pressure may be required to be reduced to achieve the desired velocities for successful pigging data. | 30 | Exact timing will be confirmed closer to the works and dependant on project and contractor availability. | 2023-12-21